## Index
TAM 2.0 ¦ Enterprise Sequencing
Section | Sheet
Enterprise | NA
RoW (excl. LATAM)
Back-book Considerations
Migration considerations |  | Operating principles
Funding windows | Confirm that settlement timing and funding windows do not shift in a way that disrupts merchants who rely on early funding | Payment flows are the critical path | Focus on CP & e-commerce transaction flows need real design work; We move merchants to the target rails by migrating how they are funded (their BIN and ICA). Once funding moves, boarding, servicing and CRM follow
Pricing | SMB merchants are mostly on fixed pricing; Where interchange-plus applies, the cost per transaction must not rise after the back-end changes | No net-new on non-target platforms | We will not add features to Evo/e-service, GMAS Europe or Greenhouse; New capability is built only on the target rails
Feature-parity assessment | Segment the book by MCC and by volume (CP vs. CNP), and use usage data to confirm which capabilities merchants actually rely on | Work on exiting platforms needs an exception | Any engineering effort spent on a non-target platform must go through an exception process, so we do not extend its life
Statements | Be transparent with merchants about what changes on their statements after migration | Parity is not the goal | We accept that a small tail of capabilities will not be rebuilt before sunset
Re-papering and Re-CDD | Re-papering is generally not required; Avoid repeated CDDs | Consolidation is not decommissioning | We commit to switching platforms off, not just moving volume, so the estate actually shrinks
Merchant Retraining | Plan for merchant retraining, which matters more for stable businesses than for high-turnover ones such as restaurants | Resiliency scales with consolidation | As volume concentrates on fewer platforms, the impact of any outage grows; Invest in resiliency, observability and faster fail-over for target platforms
Data-programme alignment | Use this migration to accelerate the homogenised data and statements work (the BFS data programme)
Settlement Options | Beneficial for savings but may require re-papering
Banking relationships / other contractual relationships | Account for existing banking and contractual relationships, e.g., HSBC and BOI
Third-party gateways | Decide the disposition for third-party gateway merchants, whether to sell off the book, migrate, or pursue other options
Ecommerce software | Assess the ecommerce software merchants use, since the ability to migrate depends on it
Trailing activity | Plan for trailing activity such as chargebacks and refunds that arrives after a merchant has migrated, ensuring it is processed correctly across the target platforms

## NA
Enterprise — NA Sequencing
|  |  |  | Focus for discussion |  | Not focus for today
Boulder | Rock | Proposition | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities | Corporate priorities | Consolidated Dependencies
1 · Single in | Global API |  | VAP cnpAPI, RAFT native/ISO, GPAPI, Portico, WPG XML, Access Worldpay | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | Global API on GG hybrid (Access-WPG-VAP) |  | Global API |  |  |  | 1 · Single in | Confirm Access → WPG → Raft pilot results before scaling the Enterprise NA API path. Resolve payouts gaps tied to Enterprise win/loss needs, especially gaming. Align proprietary protocol unwind with the switch / Global Gateway roadmap. Confirm which direct-to-WPG partner / APM connections can move to Access without merchant disruption. Coordinate with Payment Processing / Gateway for VAP and Raft implications, but keep VAP-specific migration out of Single-in.
| PayApps |  | UPA, triPOS, OEM/3rd party apps | Build — deliver TAM in-person payment app | UPA, OEM/3rd party payment apps | [5 empty] | 2 · Boarding | Confirm the Enterprise NA target instance for boarding and how it connects to Enterprise CRM / e-commerce workflows. Define whether MuleSoft / bidirectional sync is needed to preserve Core automation while moving operational process into one place. Complete the actor + PIL / hierarchy translation design before scaling automated Enterprise boarding. Align with Data / MDM on customer hierarchy, product, pricing, and merchant configuration inputs. Treat FICO → UCM as a limited Enterprise NA dependency; Enterprise boarding is still largely manual, so UCM replacement should not be the main Enterprise NA boarding driver.
| MDM/TMS |  | OEM, in-house | Build — deliver TAM deployment-as-a-service (DaaS) platform (ScaleFusion) | OEM, in-house | [5 empty] | 3 · Payment processing | Validate Raft / Core parity before moving VAP-dependent traffic, especially for recurring / subscription optimization and enterprise-scale controls. Resolve the currency gap: VAP supports ~18 currencies, while Core / Raft support is materially narrower today. Align with VAS on dynamic payouts, FX, ACH / e-check, and net settlement before opening migration conversations. Plan for duplicated compliance / scheme-mandate work across VAP and Raft while both platforms remain active during the transition.
| Developer Portal | Omnichannel | hGP Developer Portal hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migreate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc. |  |  | 4 · Sales and servicing | Define the full workflow delta to get all Enterprise NA sales / servicing activity into the Enterprise CRM. Decide where MuleSoft / bidirectional sync is needed to preserve downstream boarding / fulfillment automation. Align with Boarding on Enterprise CRM → downstream Core / Express activation plumbing.
| SDKs | Omnichannel | SDKs - connected to Access - connected to GP-API | Build - Connect Server-Side SDKs to Global API See also CP / Genius S & N below | SDKs - connected to Access - connected to GP-API | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc. |  |  | 5 · VAS | Resolve multi-currency / FX target design: VAP supports ~18 currencies, while Raft / Core coverage is materially narrower today. Accept interim duplicate support across VAP and Raft while target VAS capabilities and billing/eventing paths mature.
| 3rd Party Software Extensions | eComm | Extensions - connected to Access - connected to WPG - connected to GP-API | Build - Connect Target State Extensions to Global API | Extensions - connected to Access - connected to WPG - connected to GP-API | Build - Merge Extensions to single instance Migrate - Customers on non-Global API stacks to Global API via Extensions Decomm - Non-Global API Extensions |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc. |  |  | 6 · Single-out | Coordinate with portals team so IQ, RoW enterprise portal work, and the wrapper experience converge. Confirm the Enterprise portal ownership model; the direction is a single worldwide Enterprise portal owner, not separate regional portal ownership. Resource the Core billing eventing work; the WPG / VAS event-consumption work was not fully factored into current plans. Maintain IQ continuity for major NA Enterprise customers such as TJ Maxx and Kroger while UI uplift and global portal integration progress.
| Unified Prop |  | N/A | N/A | N/A
Hosted Solutions
| CP / Genius N | [5 empty] | TriPOS / Nucleus Combined solution | 25% volume on VAP for CP; Large merchants (e.g., Disney) presenting high migration risk
| CNP |  | Access / WPG; Access API | Build — Build API 2.0 (continue supporting the Access API for a defined period) Build - Global Gateway US instance of Access (24+ months) Build - Close out build for Access -> WPG -> RAFT (direct to WPG connections need to go to direct to Global gateway) Assess - Non RESTful protocol formats that directly connect to RAFT go from Switch to GG | Continue to support Access and thinned WPG/VAP and RAFT API |  | Unified Global API | Follow-up where does pane on glass fit? All multi-currency solutions and dynamic payouts , Net settlement, ACH / e-check, FX are under VAP currently Direct to WPG volume still exists for select partners alternative flow to consider VAP to CORE
| Hosted |  | Access / WPG; Access API eProtect | Build — conform HPP to global API standard Build — feature parity on HPP Access with HPP WPG Build — Components SDK on Access Align — PBL engine | eProtect |  | hWP hosted platform
2 · Boarding | Orchestration |  | Manually boarded to back-end platforms via forms (w/exception of Thermos for NAP and Fast Track for VAP) | Direction = BUILD Actor and PIL on UBA supporting GPI as a proof point (risk is some work may be redundant) BUILD - - Build Helix MVP (CNP Access Worldpay EMEA) - Build UBA OpenEdge MVP (required to move away from SF GPI to USI and no longer rely on legacy BAT flows) - Commence alignment of GP services and processes to main core DB's- Centralised Product Catalogue terminology and taxonomy, Subscription Service, single merchant hierarchy (party model). - Helix Flow to make amendments to utilise Workstream manager: - Boarding Gateway call to Workstream Manager - Workstream manager to connect to Party model, Subscription Service, Subscription Discovery Service, Solution Actor - Create solution actors for GP (CNP and CP) solutions since their use case covers both - Create PIL's to connect to Edge GW, GSAP, GMAS - Integrate with centralised data source (MDM) to consume from core databases such as Party Model, Subscription Service, Subscription Discovery Service, Centralised Product Catalogue (Expose API/Kafka endpoints for MDM team to consume) - Migrate Merchant data on Openedge that were boarded through UBA DECOM - - Once workstream manager replaces Order Management, look to decommission Order Management for Enterprise flows. Note: still need for SMB until SMB flows are built on HUB - Potentially commence UBA decommissioning MIGRATE - - Migrate UBA open edge flow onto HUB single boarding flow. |  |  | HUB (Boarding Gateway Workstream Manager Product/Party Model Actor/PIL Kafka MuleSoft) | • Resourcing is a challenge, with neither the right skills nor the capacity • Need Product Management resources to gather detailed requirements (~3-5 people) • Some shortfall in engineering resourcing for PIL implementation, for example Payouts, APMs, and Disputes • Helix and UBA resource (contractor based) funding ends EOY '26 EXPLORE - Identify priority for migrating - build more PILs (under-resourced), Defining new solutions' boarding activation & fulfilment (under-resourced - PM resources are immediate bottleneck) For new business ~<10% leveraging automated solutions on iNASA; Rest manual boarding Focus has been RoW (EMEA) and needs to begin for NA Consideration - how can boarding work for SMB tie to enterprise needs over ~2Yr horizon
| CPQ |  | Salesforce CPQ (native) |  |  |  | RCA
| Experience |  | Launchpad/Horizon | Build toward the convergence of Launchpad & Horizon (Ignition) | Launchpad/Horizon | Decom Launchpad & Horizon after the new application (Ignition) is built and live | Ignition | Requirements have not yet begun
| Underwriting |  | UCM/FICO | Build gap functionalities into UCM Decom FICO | UCM/FICO | Decom FICO | UCM | Limited usage of FICO in current state (manual process) Potentially limited upside of UCM work for enterprise segment
3 · Payment processing | Gateways |  | Access / WPG, XiPay, Portico, VAP, Express, RAFT (direct eComm support) | BUILD - Terminate any terminal connections that are D2H (to faciliate flow through GG and decomms down the line) | ENT still likely to use WPG-VAP for 'next' as target rails will focus on RAFT/Core in interim |  | Global Gateway | Note - arch. will be deprecating terminal to auth direct connections
| APMs |  | VAP eCheck, WPG/Access-GPPaaS | Release back end support for Access-Klarna and PBB. Start strategic eCheck (ACH) solution |  |  | TBD
| Switch |  | (Native support on auth) |  |  |  | Supercheckout - Global Gateway
| Acquiring / Funding |  | SAS/NAP; RAFT/Core; GSAP; GNAP; Exchange; VAPS; RS2 (Latam), FEVO/BEVO (Latam) | Build RAFT to GIMS interaction for Interac. Build — clear & settle largely unchanged (Core, RS2 in place) Continue to thin VAP (Services, Clearing) Build - Daily Scheme fee calculation component; Centralise rules engine Build: Event driven architecture to publish scheme cost and fee data (TBD) BUILD currency support for 16 currencies (besides CAD, USD) to RAFT / CORE |  | GNAP -> GSAP | CORE / RAFT | KAFKA upgrade (AVRO) Network fee business teams to define Card brand rules Clearning being moved from VAP to core under Helixx Access->WPG-> RAFT is in pilot RAFT only supports US and CAD (vs. VAP supporting 18 currencies); Core supports both CAD and USD Follow-up: Chris, Degiorgio, John (WP) - VAP (what needs to be true if we were to close out VAP) -
Transaction monitoring
4 · Sales and servicing | CRM |  | hWP Enterprise Salesforce (native Salesforce CPQ), iNASA (~1%) | MIGRATE - 1% traffic currently flowing through iNASA needs to be moved to Enterprise SF Assess - Leverage soln like MuleSoft to support downstream boarding flows |  |  | hWP Enterprise Salesforce (native Salesforce CPQ) | • Common SF Module for HUB integration
| Servicing |  | hWP Enterprise Salesforce (native Salesforce CPQ), iNASA (~1%) | MIGRATE - 1% traffic currently flowing through iNASA needs to be moved to Enterprise SF |  |  | hWP Enterprise Salesforce (native Salesforce CPQ)
5 · VAS | Routing |  | RTR (hGP), PRIME/Dynamic Routing (hWP) | EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning | RTR (hGP), PRIME/Dynamic Routing (hWP) |  | Dynamic Routing 2.0
| Gifts |  | hWP Premier, hWP Valutec, hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Premier, Valutec, Engage | Migrate - Premier to Engage | Engage, Valutec | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration
| Loyalty | [5 empty] | COMO
| Payment tokens |  | See Credential Management | See Credential Management | See Credential Management |  | Unified credential vault
| Managed Optimization (incl. nw payment tokens) |  | Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 Build — Revenue Boost 2.0; standardize to single-in standards | Revenue Boost Microservice |  | Revenue Boost 2.0
| DCC | [5 empty] | Target-state DCC (FX + BIN lookup) | Offered direct to RAFT (also via freedompay) Follow-up DCC <> POS strategy for ENT; Reduced volume from freedompay
| 3DS |  | 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  | VAP using Scheme settlement rates | TBD requirements for multi-currency pricing/settlement on Core to support VAP thinning |  |  | hWP FX
| Risk / compliance | [5 empty] | TBD
| Cred management |  | Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API | Access tokens | Unified credential vault
6 · Single-out | Portals |  | iQ Core | Release MVP Enterprise Portal by eoy and migrate to MyAccount++ platform in 2027 |  |  | MyAccount 2.0 | iQ serves currently as one stop shop for all enterprise needs (disputes, VT, billing, etc.) needs UI uplift Assess - enterprise cx that cut across NA and RoW to ensure they have consistent Portal exp
| Reporting |  | Bankcard (produces mainframe reports) VAP (produces SSR files) | Export data from CORE to datalake (Capturing payments, servicing, onboarding events) Connect to hGP reporting solution that forms part of target BUILD MFE and expose into Enterprise Portal Assess - is SFG (secure file gateway) replacement for EMAF reports that currently exist | GP reporting layer |  | hGP SMB / Partner reporting platform (incl Enterprise use cases) SFG (for file delivery) | Part of data strategy to enable customers to bring their own BI tools
| Billing |  | Core Billing | Build (On Core billing) - Transaction level fee data for all daily fees supporting SURF standards - Kick off EDA on Core billing: Write Billable, Billed events to downstream data layer (dependency on infra availability) - Kick off Daily Net Settlement (to support TSA exit and VAP) Build (On Core billing- specific for VAP) - Consume VAS events from upstream WPG to bill for 3ds, fraudsight etc for facilitating a single-out experience (Currently this work is also happening in VAP to consume events from WPG->KAFKA) Design and Build - NAP B&F: Kick off PoC for NA Billing Migrate: Create migration strategies for GMAS/TMAS | Core Billing | Build (core billing) - Complete "no regrets" build until NAP B&F Pilot proving successful for Enteprise Build - NAP B&F for Enteprise: NA Billing Migrate: Kick off GMAS/TMAS migrations | CORE+ (Supporting back book until NAP B&F is ready) NAP B&F - Target state-Front book initially followed by migrations | KAFKA upgrade (AVRO) Only after the NA integrated NAP B&F instance pilot for Enterprise succeeds, the core billing investment can reduce. Resourcing PODS to be considered broadly and including VAP Raji to update based on VAP work (DONE)
| Funding |  | Bankcard / VAP | (TBD) BUILD currency support for 16 currencies (besides CAD, USD) to RAFT / CORE | Bankcard
| Disputes | [5 empty] | WDP (to be renamed)
| Payouts |  | Dynamic payouts on VAP Fast Access Funding IQ Portal | DPO and FAF end of sale Frontbook via Access Worldpay P2X BUILD - close gaps on payouts capability in US (e.g., in gaming push to card) |  | • WPAP (DPO & FAF) parity | hWP WPAP (target state is a P2X platform that utilises existing WPAP assets) | • Confirm the DPO and FAF migration strategy for final decom • Dynamic payouts feature on VAP - needs to be addresssed • Helix Payout Consolidate and Super Ledger back in scope
| Residuals |  |  | Residuals pending assessment - Gap analysis workshops initiated |  |  | hWP EPI solution
7 · Data | MDM (Master Data) |  | Informatica MDM, Reltio | Build - Establish a trusted enterprise identity foundation by aligning the Party Model with Onboarding (HUB), strengthening data quality, governance, stewardship, enrichment, and identity management capabilities. Operationalize MDM: Embed trusted identity into onboarding, CRM, and priority business processes through standardized integration patterns, governance, and enterprise adoption. Publish mastered identity and relationships to the data platform. Migrate - Transition to a single enterprise MDM platform by migrating priority consumers to Reltio, consolidating capabilities, and enabling a unified identity strategy across Global Payments. Retire - Eliminate new development on Informatica and execute a phased sunset plan to retire legacy MDM capabilities and reduce operational complexity. | Reltio (D&B Marketplace for data) |  | Reltio (MDM)
| Data Acquisition including real-time |  | Custom data pipelines, Snowpipe, Kafka (EDIA), Fivetran, GoldenGate, Confluent, AWS MSK, GCP MSK, Attunity, DataStage, Nimbus, DPaaS, Global Token Service, Mulesoft | Build - Stand up target platform​; Iceberg materialization​; Flink SQL standard for stateful transforms​; Reference pipeline templates + CI\CD​, implement schema evolution, schema management and replay\reprocessing mechanism​; NRT Iceberg Ingestion + Audit logs + SLOs,​ Capture RT events from event types, front end and back end platforms, standardize target state tokenization platform, ingest from data producers (batch and real-time), real-time ingest from data producing system into lakehouse; pilot for relational SLA workloads (1-2 identified), build MVP ODS (dev/test/prod provisioned); Platform Deployment & Core Configuration​; Standard Ingestion Pattern Definition​; Connector Gap & Extensibility Strategy​; Establish governance frameworks (data ownership, onboarding standards) Migrate: Move <1hour latency batch processes, consolidate fragmented clusters; consolidate existing OLTP stores Retire: existing OLTP stores | Snowpipe, Fivetran, Kafka, Tokenization platform (Databolt), Kafka stream (TBD) |  | Resilient real-time ingestion
| Data foundational build |  | hWP CDP, hWP NDP, hGP Caspian, hGP TIDAL, Snowflake, GCP BQ, Databricks | Build - implement data sharing framework between hGP and hWP, data contract approach, build 11 core domains (out of 26), align with new eventing architecture, unified enterprise data model, integrate with EDC, reusable enterprise data products through semantic layer​; Establish separate dbt Cloud projects; Configure foundational core metrics ​; Enforce dbt model schemas & contracts Migrate - CDP to NDP and Caspian to TIDAL, Connect independent dbt Cloud projects to separate GLOBAL_PROD and WORLDPAY_PROD Snowflake databases Retire - CDP and Caspian | NDP, TIDAL, Snowflake, Databricks
| Reporting |  | Business Objects, Cognos, SSRS, Kepler, Oracle BI, Microsoft AX, Power BI (Oceania), MicroStrategy, Tableau (Partner Portal) | Build - reusable enterprise data products through semantic layer, establish dbt Cloud projects, configure foundational core metrics Migrate - connect independent dbt Cloud projects to Snowflake databases, migrate reports away from MicroStrategy and SSRS Retire - MicroStrategy, SSRS Use cases: Authorization executive dashboard, Reporting 2.0, Customer 360 | Cognos, Looker SaaS, Power BI, Tableau, Sisense, TBD [target BI tool], in-house tool (Pulse) |  | Semantic layer
| Data Risk & Data Trust |  | Informatica, Alation | Build - Stewardship framework, end-to-end workflow ownership, risk-tier rules, data lineage and data catalog/context expansion, agentic governance framework/tooling (TBD), embedded data trust into domains and products Migrate - prepare Alation to Informatica migration Retire - Sunset duplicate intake paths and manual status tracking, stop unmanaged governance processes | Informatica, Alation |  | TBD
| AI |  | GCP, AWS, Azure, Snowflake, Databricks | Build - build and productionalize sandbox, stand up AI Gateway MVP, identify and develop reusable components and golden path of operationalization Migrate - prepare for cloud platform migration, align teams to standardized tooling and architecture platforms Retire - potential retirement of Azure, decommission non-strategic experimentation environments | GCP, AWS, Snowflake, Databricks - TBD |  | TBD

## RoW (excl. LATAM)
Enterprise — RoW Sequencing
|  |  |  | Focus for discussion |  | Not focus for today
Boulder | Rock | Proposition | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities
1 · Single in | Global API |  | Access / WPG; Access API; WPAP, GPAPI | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | Global API (Access codebase) - WPG | Migrate — merchants onto v2 Decomm "Access version" — v1 (later) | Global API
| PayApps |  | OEM/3rd party apps, WPT Nucleus Enterprise EDPS Comercia | Build — Nucleus (PayApp 2.0) Migrate — migrate WPT book to triPOS | OEM/3rd party apps, WPT Migrate - EDPS, WPT
| MDM/TMS |  | OEM, in-house | Build — deliver TAM deployment-as-a-service (DaaS) platform (ScaleFusion) | OEM, in-house
| Developer Portal | Omnichannel | hGP Developer Portal hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migreate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | SDKs - connected to Access - connected to GP-API | Build - Connect Server-Side SDKs to Global API See also CP / Genius S & N below | SDKs - connected to Access - connected to GP-API | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | Extensions - connected to Access - connected to WPG - connected to GP-API | Build - Connect Target State Extensions to Global API | Extensions - connected to Access - connected to WPG - connected to GP-API | Build - Merge Extensions to single instance Migrate - Customers on non-Global API stacks to Global API via Extensions Decomm - Non-Global API Extensions |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| Unified Prop |  | WPT, FreedomPay, other 3rd party solutions (WPG, GPAPI, GP acquirers) | Phase 1: Build - EMBOSS feed into Access query DB (unified reporting & cross channel payment flows) Build - POS data availability in Enterprise Portal Phase 2: Build - Terminal concentrator capability > WPG Build - Payment app 2.0 integration>Global API>WPG Build - POS VAS on > Global API > WPG Migrate - WPT BB migration | EMBOSS, WPG | Phase 2: Build - Terminal concentrator capability > WPG Build - Payment app 2.0 integration>Global API>WPG Build - POS VAS on > Global API > WPG Migrate - WPT (Decomm) |  |  |  | Migrate - WPT (Decomm) for UK/I
| Hosted Solutions |  | Access / WPG; Access API | Build — conform HPP to global API standard Build — feature parity on HPP Access with HPP WPG Build — Components SDK on Access Align — PBL engine
| CP |  | Direct to SAS; Tansxpay, WPT, WPG POS Partners (e.g., Freedompay) | Build - Taking legacy protocol mapping and surfacing through supercheckout | Genius N, Freedompay & other partners, Direct to auth merchants |  | TriPOS / Nucleus Combined solution API access point Supercheckout | • Tesco and Walmart may be exceptions as direct-to-acquirer |  | Get off TMAS / GMAS
| CNP |  | Access / WPG; Access API; WPAP | Build — Build API 2.0(reduce dependency on legacy over time) EXPLORE - Replicate AP exercise for GMAS EU ent customers - Assess path off GMAS for Non-Taiwanese, Non-IPP customers - Understand IPP feature gaps and how to solve EXPLORE - How to solve for Taiwan EXPLORE - Identify single out work to prioritize for JV customers |  |  | Unified Global API | • Slow development on WPG and move customers onto Access • Taiwan needs a focused conversation (follow up) • Confirm the cuts needed, for example volumes and verticals, to assess first-mover enterprise customers; no information is currently available • Over the next 18 months, replicate the AP exercise for GMAS EU enterprise customers and identify single-out work to prioritise for JV customers |  | Get off Cybersource and MPGS
| Hosted | [5 empty] | TBD |  |  | Dependency on Cayan TSA exit for identity (Identity has board implications and needs alignment)
2 · Boarding | Orchestration |  | Manually boarded to back-end platforms via forms (w/exception of Thermos for NAP and Fast Track for VAP) | BUILD - - Build Helix MVP (CNP Access Worldpay EMEA) - Build UBA OpenEdge MVP (required to move away from SF GPI to USI and no longer rely on legacy BAT flows) - Commence alignment of GP services and processes to main core DB's- Centralised Product Catalogue terminology and taxonomy, Subscription Service, single merchant hierarchy (party model). - Helix Flow to make amendments to utilise Workstream manager: - Boarding Gateway call to Workstream Manager - Workstream manager to connect to Party model, Subscription Service, Subscription Discovery Service, Solution Actor - Create solution actors for GP (CNP and CP) solutions since their use case covers both - Create PIL's to connect to Edge GW, GSAP, GMAS - Integrate with centralised data source (MDM) to consume from core databases such as Party Model, Subscription Service, Subscription Discovery Service, Centralised Product Catalogue (Expose API/Kafka endpoints for MDM team to consume) - Migrate Merchant data on Openedge that were boarded through UBA DECOM - - Once workstream manager replaces Order Management, look to decommission Order Management for Enterprise flows. Note: still need for SMB until SMB flows are built on HUB - Potentially commence UBA decommissioning MIGRATE - - Migrate UBA open edge flow onto HUB single boarding flow. |  |  | HUB (Boarding Gateway Workstream Manager Product/Party Model Actor/PIL Kafka MuleSoft) | • Resourcing is a challenge, with neither the right skills nor the capacity • Need Product Management resources to gather detailed requirements (~3-5 people) • Some shortfall in engineering resourcing for PIL implementation, for example Payouts, APMs, and Disputes EXPLORE - Identify priority for migrating - build more PILs (under-resourced), Defining new solutions' boarding activation & fulfilment (under-resourced - PM resources are immediate bottleneck)
| CPQ |  | Salesforce CPQ (native) |  |  | Next — begin transition to RCA (paced to contract exit) | RCA
| Experience |  | Launchpad/Horizon/Tuza/Takepayments | • [BUILD] Convergence application - Ignition | Launchpad/Horizon/Tuza/Takepayments |  | Ignition | Gap analysis needed for Tuza vs Horizon Requirements needed for Ignition (convergence of Launchpad & Horizon)
| Underwriting |  | Currently manual | EXPLORE - Complete assessments manual boarding, pKYC ~3mo (details in notes) |  |  | UCM | • Assessment needed to understand the current process and ensure UCM is fit for purpose for SMB and integrated, can service enterprise, and supports pKYC (underway)
3 · Payment processing | Gateways |  | CNP - Access / WPG (incl. BG) CP - Transxpay, WPT for hGP majority on GP eComm, 3P gateways (e.g., MPGS) | Build — Start build to support routing through Global Gateway Build — Thin WPG (as it sits behind access and will need eng. effort to dis-integrate) BUILD - Continue modernization efforts - Cloudification :) | Access, WPG, Transxpay, WPT | Drop WPG components to 5-0% Converge WPT into global gateway | Global Gateway Maintain due to local requirements: - C2.0 - APF (as auth platform for Latam) - EDPS (as auth platform for Greek networks) | • WPG to support a small tail of traffic; the rest use the Global Gateway
| APMs |  | Primarily GPaaS, WPAP GpeComm, GPE APM Svc., EFTpay | BUILD - Single-out for APMs Converge existing APMs from WPG to GPAS |  |  | GPPaaS (TBC)
| Eventing |  |  | BUILD - support for APMs BUILD - Eventing for NAP
| Switch |  | Supercheckout | BUILD - Protocol messaging and using SC for legacy protocols | Supercheckout |  | Supercheckout
| Switch |  | SAS; NAP hGP - ACI consolidation, GMAS EU, AP | BUILD - Auth switch move from Base24 MMS to PowerZac (small volume) EXPLORE - Migration planning for GMAS EU and AP Continue Helix path - build for Amex single out for NAP, new LPMs settled and billed, improve interfaces into NAP (bulk files to individual messaging serving as integration pt. for Powerzac) |  | BUILD - Auth switch move from Postillion to PowerZac / NAP | NAP / PowerZac | • Align on the engagement model with Legal, Risk, Compliance, and Tax • Stand up a cross-functional working group on acquiring licensing, legal-entity cleanup, and dedup • Point person from Legal is Melissa Perreira • Helix support model uses existing resources plus Endava contractors (funded to Jun '28, with a gradual ramp-down) • Confirm the ramp-down, as we may want to retain resourcing to accelerate (baked into the build sheet)
| Transaction monitoring |  | IBM Safer Payments / Brighterion / sanction screening / Activimize |  |  |  | TBC
4 · Sales and servicing | CRM |  | hWP Enterprise Salesforce | BUILD: - Salesforce integration w/Product Catalog (inc. RCA) |  |  | hWP Enterprise Salesforce (native Salesforce CPQ) | • Migration planning for cross-segment movement, for example SMB to Enterprise into Enterprise SF
| Servicing |  | hWP - SIEBEL (used for NAP), VAP servicing, Treasury manager WPAP | Already planned: BUILD - Remove front-end and migrate into svc cloud BUILD - decouple database behind; connect DBs as part of API created for TAM 2.0 boarding target state |  |  | Enterprise SF | • Amendments orchestrated via HUB
5 · VAS | Routing |  | N/A - None today | EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning |  |  | Dynamic Routing 2.0
| Gifts |  | N/A | N/A | N/A | N/A | N/A
| Loyalty |  |  | BUILD - COMO integration to target |  |  | COMO
| Payment tokens |  | See Credential Management | See Credential Management | See Credential Management | See Credential Management | Unified credential vault | • BAU; accelerate the unified credential vault architecture
| Managed Optimization (incl. nw payment tokens) |  | Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 | Revenue Boost Microservice |  | Revenue Boost 2.0
| DCC |  |  | BUILD - isolate DCC svc. From WPG EXPLORE - DCC svc. From WPT to Genius |  |  | Target-state DCC (FX + BIN lookup)
| 3DS |  | 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  |  | EXPLORE - Fx pricing prop for hGP customers (GMAS EU, GMAS AP) - per note across 2 traches |  |  | hWP FX
| Risk / compliance | [5 empty] | TBD
| Cred management (Provision & Vaulting) |  | Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API |  | Unified credential vault
6 · Single-out | Portals |  | WP Dashboard, others | BUILD - Enterprise portal for access (similar to WPG) Continue HELIX roadmap | Interim WP dashboard |  | MyAccount 2.0 (MFE is Enterprise Experience Portal)
| Reporting | [5 empty] | hGP SMB / Partner reporting platform SFG (for file delivery) | • Follow up with Vikrant Gupta on the reporting solutions being built out
| Billing | [5 empty] | NAP Billing
Funding
| Disputes | [5 empty] | WDP (to be renamed)
| Payouts |  | WPAP (with AWP infront) Dynamic payouts on VAP Fast Access Funding Payout Portals | Decomm APMs out of WPAP Complete cloud migration of WPAP (imp for inc. elasticity) Stop sell dynamic payouts on VAP thinning reporting, billing, fx out of WPAP |  |  | hWP WPAP (target state is a P2X platform that utilises existing WPAP assets) | • Operational support needed on the Treasury Management side • Dependency on transaction management • Need to include Marketplaces assets • Confirm if Payouts is the single bankling integration for all acquiring capabilities
| Residuals | [5 empty] | hWP EPI solution
7 · Data | MDM (Master Data) |  |  | data routing beneath access |  |  | Reltio (MDM)
| Real-time data |  |  | BUILD - Capture RT events for 18 event types from NAP into Lakehouse
| Reporting |  |  | EXPLORE - Datalake for EU approach aligned to critical reporting use-cases
Others
8 · Infrastructure | Design system |  | Worldpay Vega Index | Consolidate into one system | Continue maintenance of three, pilot teams to adopt consolidated system (My Account, Genius) | Decomm Vega and Index | Global Design System (Worldpay as Foundation, leveraging, Vega and Index assets) | Risks and mitigations: Risk: TSA / access constraints: Sequence pilots around feasible access and repository constraints Migration must be design driven and start with front loading 0-6 months for standards. Implement design gates before scale; standards council owns component acceptance