## Index
TAM 2.0 ¦ Integrated Sequencing
Section | Sheet
Integrated | NA
RoW
Back-book Considerations
Migration considerations |  | Operating principles
Funding windows | Confirm that settlement timing and funding windows do not shift in a way that disrupts merchants who rely on early funding | Payment flows are the critical path | Focus on CP & e-commerce transaction flows need real design work; We move merchants to the target rails by migrating how they are funded (their BIN and ICA). Once funding moves, boarding, servicing and CRM follow
Pricing | SMB merchants are mostly on fixed pricing; Where interchange-plus applies, the cost per transaction must not rise after the back-end changes | No net-new on non-target platforms | We will not add features to Evo/e-service, GMAS Europe or Greenhouse; New capability is built only on the target rails
Feature-parity assessment | Segment the book by MCC and by volume (CP vs. CNP), and use usage data to confirm which capabilities merchants actually rely on | Work on exiting platforms needs an exception | Any engineering effort spent on a non-target platform must go through an exception process, so we do not extend its life
Statements | Be transparent with merchants about what changes on their statements after migration | Parity is not the goal | We accept that a small tail of capabilities will not be rebuilt before sunset
Re-papering and Re-CDD | Re-papering is generally not required; Avoid repeated CDDs | Consolidation is not decommissioning | We commit to switching platforms off, not just moving volume, so the estate actually shrinks
Merchant Retraining | Plan for merchant retraining, which matters more for stable businesses than for high-turnover ones such as restaurants | Resiliency scales with consolidation | As volume concentrates on fewer platforms, the impact of any outage grows; Invest in resiliency, observability and faster fail-over for target platforms
Data-programme alignment | Use this migration to accelerate the homogenised data and statements work (the BFS data programme)
Settlement Options | Beneficial for savings but may require re-papering
Banking relationships / other contractual relationships | Account for existing banking and contractual relationships, e.g., HSBC and BOI
Third-party gateways | Decide the disposition for third-party gateway merchants, whether to sell off the book, migrate, or pursue other options
Ecommerce software | Assess the ecommerce software merchants use, since the ability to migrate depends on it
Trailing activity | Plan for trailing activity such as chargebacks and refunds that arrives after a merchant has migrated, ensuring it is processed correctly across the target platforms

## NA
Integrated — NA Sequencing
|  |  |  | Focus for discussion |  | Not focus for today
Boulder | Rock | Proposition | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies | Summarized dependencies | Business priorities | Corporate priorities
1 · Single in | Global API |  | • Payrix API • ProPay API • Assist Widgets • hWP integrated stack - TriPOS & Express - RAFT/CORE - iQ + Launchpad - Includes BYOD for Full EMV Cert - Further detail in Gateways, PayApps and Hosted sections • TAPI (Meet in the Cloud & Payfields) • hGP integrated legacy integrations - Merchantware (OG Genius, Transport Web, Genius Checkout) - Edge (EdgeExpress, XCharge, OpenEdge Host Pay) - Further detail in Gateways, PayApps and Hosted sections • Mercury Pay • Direct to gateway integrations | Focus on Front-book priorities and activities [Build] TAPI API to go overTriPOS and Express for integrated NA. [Build] Unlock Canada through TAPI [Build] Integrate Assist Widgets to Global API 2.0 [Migrate] Work towards ProPay to be Support/Maintain by Jan '27 - ProPay -TBC - Ian/James checking with Bill [Build] Define Single-in guardrails/guidelines/timeline for TAPI/ relations to Global API & TriPos [Build] Single IN to share the standards/guidelines for Global API [Migrate] Determine Payrix Payfields migration/decom plan (e.g., integrate within TAPI) (Migrate and Decomm) Innovo (Migrate) MercuryPay - Shim to Express TBD [Build] Build OAuth Authentication for Global API [Build] Global API for Express | Sell • TAPI to TriPos & Express + CX • Global API to TriPos & Express + HPP + CX (Contingent on deliverables) Support/Maintain • Payrix API • ProPay API (TBD, Proxy to Payrix?) • hWP integrated stack (TriPOS & Express, iQ + Launchpad) • hGP integrated stack (TAPI, et al) | • [BUILD] Align both IP books to the API 2.0 / Global API federated standard — converging hGP and hWP integration front doors • [MIGRATE] Begin converging duplicate integration stacks — enabling the 2027 priority to fully integrate the merchant lifecycle [Migrate] Migrating Merchantware, and Edge | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on API 2.0 • [EXIT] Decommission duplicate integration front doors once partner migration completes •[Migrate] Migrate From TAPI towards global API | First mover decision: TAPI, TriPOS, Express Dependent on Cross Domain Deliverables meeting Platforms Requirements Migration plans are dependent on how we plan on supporting existing integrations, are we going to create Proxies to route transactions to the Target State Platform, for example like we did between TSYS TXP and TransIT? For Propay API/Propay gateway: JR to have follow up convo for cross-company access ~95% new integrations over last 5 years have been to TAPI | Single-in Dependencies: - Validate cloud / network architecture for TAPI-to-TriPOS, including the GCP-to-Azure connection, hop count, and five-nines availability requirements. -Assess Meet-in-the-Cloud versus TriPOS messaging as part of the target architecture. - Ensure boarding and servicing readiness, as TAPI-to-Express cannot fully succeed if partners cannot board or service merchants on the new path. - Complete UCM / FICO unwind, UBA / USI interim flows, and longer-term iNASA convergence. - Deliver MDM / master data plumbing for product, pricing, merchant, customer, and partner hierarchy. - Determine the merchant / MID migration strategy: migrate merchants to the target host path or accept duplicative interim work to minimize disruption. - Complete token vault / credential migration to enable e-commerce and gateway migrations without disrupting partner or merchant experiences. - Implement OAuth pass-through to eliminate downstream credential and boarding dependencies during partner migrations.
| PayApps |  | • Cayan Terminal App (Non-POS) • Remote Client Manager (RCM) • TriPos • UCI (leverages UPA) | Build - TAM payapp (triPOS/Nucleus hybrid) Build - TAM cloud integration platform (triPOS cloud/MitC hybrid) Build - TAM payapp SDK (merge triPOS SDK/GPSDK) Migrate - UPA SI to TAM payapp | Sell • triPOS Cloud via TAPI/Global API • triPOS SDK payapp Support/Maintain • RCM • Cayan Terminal App |  | Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience | Migration plans are dependent on how we plan on supporting existing integrations, are we going to create Proxies to route transactions to the Target State Platform, for example like we did between TSYS TXP and TransIT? Critical decision point: Option A — migrate merchants to the target host (mid-migration). Accept some level of "manageable attrition" as merchants move Option B — avoid migration by building and integrating boarding pathways to multiple different hosts/back-ends; throwaway, duplicative work whose only purpose is minimizing attrition
| MDM/TMS |  | • Merchantware TMS • Scalefusion & Sightstream • OEM TMS (Ingenico, et al) • Edge Phone Home Server | Build - Scalefusion boarding integrations with TAM boarding platform(s) | Sell • Scalefusion & Sightstream Support/Maintain • Merchantware TMS & Sightstream • OEM TMS • Edge Phone Home Server
| Developer Portal | Omnichannel | • hGP Developer Portal • hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migreate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | • OpenEdge Mobile SDK • Innovo SDKs • Yazara SoftPos SDK | Build - Connect Server-Side SDKs to Global API | Sell • TriPos SDK • Yazara SoftPos SDK Support Maintain • OpenEdge Mobile SDK Decommission • Innovo SDKs | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | • Salesforce Commerce Cloud | [Build] Integrated Salesforce Commerce Cloud to Global API | Support Maintain • Salesforce Commerce Cloud
Unified Prop
| CP |  | • Cayan Terminal App (Non-POS) • Remote Client Manager (RCM) • TriPos • UCI (leverages UPA) | [Build] TAPI API to go overTriPOS and Express for integrated NA. [Build] Unlock Canada through TAPI [Migrate] Work towards ProPay to be KTLO by Jan '27 | Sell • triPOS Cloud via TAPI/Global API • triPOS SDK payapp Support/Maintain • RCM • Cayan Terminal App |  | TriPOS / Nucleus Combined solution
| CNP |  | • Express • TAPI | [Build] TAPI API to go overTriPOS and Express for integrated NA. [Build] Build OAuth Authentication for Global API [Build] Define Single-in guardrails/guidelines/timeline for TAPI/ relations to Global API [Build] Single IN to share the standards/guidelines for Global API and TRIPOS [Build] Global API for Express | Sell • TAPI to Express + HPP + Hosted Components • Global API to Express + Hosted Components (Contingent on deliverables) | Migrate merchants off Express directly to API on GG | Unified Global API
| Hosted |  | • Express HPP (legacy) • OEHP • EdgeExpress CNP • PayFields • HPV3 • TUI • Transport Web • Genius Checkout • SecureSubmit (For ProPay) | [Migrate] Determine Payrix Payfields migration/decom plan (e.g., integrate within TAPI) [Build] conform HPP to global API standard [Build] feature parity on HPP Premium Express to Decomm Legacy HPP and migrate back book [Build] Components SDK session support on Express [Build / Migrate /Decomm] Merge TUI / OEHP functionality and migrate TUI merchants [Align] PayByLink (PBL) engine [Build] Converge implementation -hGP Payfields / Hosted Components | Sell HPP+ / Hosted Components Support/Maintain OEHP EdgeExpress CNP Payfields Transport Web Genius Checkout TUI EOL HPV3 | Legacy Express HPP, Payfields | Hosted Platform
2 · Boarding | Orchestration |  | Boarding • Launchpad (hWP) • Payrix boarding • ProPay Boarding • Payfac RAFT Boarding • GPI SF.com (consolidating into hCorp SF.com) - Including GPI Onboarding API • UBA * StoreBuilder/EdgeBuilder | • [MIGRATE] GPI SF.com → hCorp/ISI SF.com consolidation — cutover September 21st with surcharging and auto-boarding enablement [IP] • [BUILD] Launchpad seamless self-enrolment — low-code embed of the enrollment process, enabling the partner-led growth priority • [Migrate] Investigate the Merchantware back-book migration plans and/or legacy front-book • ASSESS - Single API for Onboarding for Payfac, IP Referral and Payrix | Sell • LaunchPad • Payrix • Assist • RAFT (Payfac) Support/Maintain • HCorp/USI SF Onboarding • UBA • ProPay Boarding EOL • StoreBuilder/EdgeBuilder | • [BUILD] Parallel onboarding and faster funding [EFE] • [BUILD] Converge boarding onto Ignition / the hWP party model as the target experience lands | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM |  | Boarding dependencies: TAPI → Express readiness is a gating dependency: boarding, CRM, servicing, and sales need to move at the same pace so new MIDs can route to Express without operational breaks. Transaction API standards / Global API 2.0 need to be defined first, but onboarding API must follow quickly so partners can actually move merchants. CRM convergence is tightly linked: USI / UBA must work as the interim path, while iNASA remains the longer-term convergence point. UCM enablement depends on pulling out FICO and deciding how credit / underwriting workflows should operate in the target model. MDM strategy is a first-mover dependency, especially for customer master, partner / merchant hierarchy, product master, pricing, and how Salesforce reads that data. Merchant / MID migration strategy must be resolved because it determines whether onboarding can point to the target host path or whether temporary duplicate onboarding paths are needed. Servicing implications need to be defined with onboarding, because any change to where partners and merchants land will change how they are serviced post-boarding.
| CPQ |  | Oracle CPQ | • [BUILD] l-GP CAN for RCA | RCA CPQ | • [BUILD] l-WP for US/CAN/UK/I for RCA • [BUILD] RCA for USI/GPI merge into iNASA | RCA
| Experience |  | Payrix US Payrix AU Payrix UK IntegraPay Launchpad |  | Launchpad |  | Ignition
| Underwriting |  | FICO | Migrate off FICO |  |  | UCM
3 · Payment processing | Gateways |  | • Edge • Merchantware • Express • Innovo • Payrix • ProPay | • [BUILD] Resolve the pan-segment ACH/eCheck gap — decide between retaining VAP as an ACH-only platform behind Core/Express, or mirroring VAP with Fifth Third as ODFI behind Core (~$1.4M scope); VAP serves NA only and this gates its retirement • [BUILD] Push to Account needs to be at parity with Dynamic Payout — single global payouts solution [PayFac] * (Migrate and Decomm) Innovo * [Migrate] Utilize TAPI / Global API over Express as front-book payments API for Payrix/Assist * [ASSESS] Align on ACH Service, create a workstream | Sell • Express • Global Gateway (Contingent on Deliverables) Support/Maintain • Edge • Merchantware • Payrix • [MIGRATE] VAP → Core migrations once the ACH path lands [Stop] Stop-sell Payrix Gateway for front-book (dependent on ACH/eCheck gap closure) EOL • Innovo |  | Global Gateway GG to support Platforms to RAFT by H1 28 with same API implementation (via Hybrid GG) for ROW | Migration plans are dependent on how we plan on supporting existing integrations, are we going to create Proxies to route transactions to the Target State Platform, for example like we did between TSYS TXP and TransIT? ACH workstream to kick off (Soltan, Laurie) | Validate TAPI-to-TriPOS cloud / network architecture, including dedicated GCP-to-Azure connectivity, hop count, latency, and five-nines availability. Resolve Meet-in-the-Cloud vs. TriPOS messaging, including terminal recertification and performance implications. Decide card-present merchant / MID migration strategy: migrate merchants to the target host path or build duplicative / throwaway integrations to reduce disruption. Define host migration paths across Sierra, GSAP, Express, Raft, GMAS, and TMAS without re-papering, pricing limitations, or funding-window disruption. Complete credential / token vault migration so Edge, MerchantWare, and Express can use shared credential management for e-commerce and gateway migrations. Align boarding, servicing, sales, CRM, and downstream operations with TAPI → Express so partners can board, service, and manage merchants on the new path. Standardize switch / gateway / host / authorization platform definitions from Chris Gaseltine’s work before locking direct-to-host unwind, core acquiring migration, and gateway consolidation decisions.
| APMs |  | • Nuvei Check Commerce • DCS ACheck21 • Paya ACH • Valutec • Gift/Loyalty Processors on Merchantware • DelayPay (TuaPay) | • [BUILD] Resolve the pan-segment ACH/eCheck gap — decide between retaining VAP as an ACH-only platform behind Core/Express, or mirroring VAP with Fifth Third as ODFI behind Core (~$1.4M scope); VAP serves NA only and this gates its retirement *Migrate and decomm Delay in favor of target BNPL solution | Sell • Check Commerce • VAP (Contingent on ACH Platform decision) • Valutec • Engage Support/Maintain • DCS ACheck21 • Paya ACH • Gift/Loyalty Processors on Merchantware |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
| Switch | [5 empty] | Supercheckout
| Acquiring / Funding |  | • RAFT/Core • VAP • GSAP/GMAS • Sierra/TMAS • Payrix | • [BUILD] Target ACH eCheck solution with single out on Core • [BUILD] Resolve the pan-segment ACH/eCheck gap — decide between retaining VAP as an ACH-only platform behind Core/Express, or mirroring VAP with Fifth Third as ODFI behind Core (~$1.4M scope); VAP serves NA only and this gates its retirement • [BUILD] Push to Account needs to be at parity with Dynamic Payout — single global payouts solution [PayFac] | Sell • RAFT/Core • VAP (Contingent on ACH Platform decision) • Payrix Support Maintain • GSAP/GMAS • Sierra/TMAS | (Point TAPI, Payrix shim, Innovo and Express/Mercury shim to Global Gateway - RAFT in target); Migrate clients off Edge, Mware legacy. Use gateway switching to move merchants off GMAS/TMAS • [MIGRATE] VAP → Core migrations once the ACH path lands [Stop] Stop-sell Payrix Gateway for front-book (dependent on ACH/eCheck gap closure) [Migrate] Utilize TAPI over Express as front-book payments API for Payrix/Assist | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | Decisioning on migrating front and back-end together or not. If done separately the merchants have potential migration issue 2x vs 1. HWP have traditionally done a migration in full. Ability to migrate in a timely fashion should be centered on no regret must have gaps.
Transaction monitoring
4 · Sales and servicing | CRM |  | • iNASA • ISI • USI • GPI • IPCRM | • [BUILD] l-GP CAN sale flows for iNASA with going to new boarding TAM • [BUILD] Progress hGP CRM consolidation in line with the pending CRM 2/3 decision * Migrate/Decomm IPCRM | • iNASA • iSI • USI (aka H-Corp) | • [BUILD] USI/GPI for iNASA to sunset USI • [BUILD] l-WP into new boarding TAM | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) iNASA = NA/Canada/UK ISI = ROW Servicing tools • (to be defined) Risk monitoring • Merchant & transaction | Will have work with Payrix/Assist sunset to pull partner and merchant records in. Need to figure out where in sequencing that goes. | Boarding dependency: Launchpad, UBA, StoreBuilder / EdgeBuilder, Payrix / ProPay / RAFT onboarding, single onboarding API, and FICO → UCM sit under Boarding, but Sales & Servicing depends on them to support end-to-end partner / merchant flow. Single-out dependency: gateway reporting, virtual terminal, partner portals, OpenEdge commissions / residuals, EPPE / EPI, and partner payment experiences sit under Single-out, not Sales & Servicing. CRM decision dependency: the pending CRM 2/3 decision determines the longer-term target CRM architecture beyond iNASA-at-launch. Data / MDM dependency: customer master, partner / merchant hierarchy, product configuration, pricing configuration, and risk monitoring data need to feed CRM and servicing workflows. Single-in / payment dependency: TAPI → Express and merchant / MID migration require sales, boarding, and servicing to move in parallel so partners can be sold, onboarded, and supported on the new path.
| Servicing | [5 empty] | iNASA
5 · VAS | Routing |  | Embedded finance & VAS • EFE (hWP) • Fee Assist / surcharge • Payrix VAS set (fraud, tokens, payouts) • CX Suite • RTR (hGP) • PRIME/Dynamic Routing (hWP) | [Build] ProPay issues debit cards to fund card accs for several customers. Determine capability coverage to a new target-state platform [Build] Enable CX suite on go-forward integrated solution in NA [TBD] Gifts on go-forward integration solution [Build] Build Loyalty to go-forward integration solution EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning | Sell • EFE • PRIME • CX Suite • FeeAssist • Payrix VAS set (fraud, tokens, payouts) Support/Maintain • RTR (hGP) |  | Dynamic Routing 2.0 Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization |  | ACH path decision is the critical dependency: align Lori Sheehan / Mike Clark’s ACH effort with Curtis, Andre, Soltan, and team before locking VAP, core reporting, and ODFI integration plans. VAP retirement depends on the ACH decision, including whether VAP remains ACH-only behind Core / Express or whether the Fifth Third ODFI pattern behind core can replace the capability. Core dependency for Fee Assist: some Fee Assist logic depends on core from a routing perspective, including state-level MCC restrictions. Push to Account parity with Dynamic Payouts is needed before converging to a single global payouts solution. Single ecosystem / platform convergence is needed before VAS can scale broadly to more partner types, including IP referral and other partners that do not have current access. Acquiring / funding and migration decisions must align with ACH, push-to-account, and broader GSAP / GMAS / Sierra / TMAS decisions. Engage commercialization must be available to Integrated platforms before moving off existing gift / loyalty services such as X Gift / MerchantWare processors.
| Gifts |  | • hWP Premier • hWP Valutec • hGP Engage • hGP OptiCard • xGift | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration * Migrate and Decomm XGift | Sell • Premier • Engage Support/Maintain • OptiCard EOL • XGift | Migrate - Premier to Engage | Engage, Valutec | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration Opticard migration wrapping up currently for hGP on MW
| Loyalty |  | • Valutec • COMO | [Build] Build Loyalty to go-forward integration solution | Sell • Valutec |  | COMO
| Payment tokens |  | • OmniToken • PASS Token • Network Token • Gateway Specifc Tokens | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) | Support Maintain • OmniToken • PASS Token • Network Token • Gateway Specifc Tokens |  | Unified credential vault • hWP credential management | First mover decision
| Managed Optimization (incl. nw payment tokens) |  | • Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 | Sell • Revenue Boost Microservice |  | Revenue Boost 2.0 • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud
| DCC | [5 empty] | Target-state DCC (FX + BIN lookup)
| 3DS |  | • 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | • FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | • FraudSwitch Microservice |  | FraudSight • Fraudsight (powered by Ravelin)
| FX |  | • VAP using Scheme settlement rates | TBD requirements for multi-currency pricing/settlement on Core to support VAP thinning |  |  | hWP FX FX / DCC • hWP
| Risk / compliance | [5 empty] | TBD
| Cred management |  | • Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) [Build] Build a shared tokenization/replication service to ease future Migration efforts between GP Platforms EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | • Credential API |  | Unified credential vault
6 · Single-out | Portals |  | • IQ Core • IQ SMB • OmniFlex • Payrix Portal • ProPay Portal • VAP Portal • OpenEdge View Portal • Merchantware Portal • Global Merchant Portal | [Build] Align Payrix portal, EFE-customer facing portal towards common single-out portal [Build] OEV & MSH -> myAccount for non-gateway admin features [Build] MW Portal -> myAccount ASSESS - Gateway Level Reporting and Virtual Terminal? Will this be incorporated into Single Out? | Sell • hWP integrated stack (iQ) • Payrix Portal • Global Merchant Portal Support/Maintain • ProPay Portal • Omniflex • OpenEdge View Portal • Merchantware Portal | • [MIGRATE] Converge onboarding, payments and reporting experiences — reducing duplicate stacks per the 2027 priority - [MIGRATE] To enable support for EFE outside of Integrated platforms, Partner facing portal to be aligned with MyAccount (go-forward portal) | MyAccount 2.0 Portal • MyAccount++ (Need to support MX, PX, and Gateway use cases for reporting and VT) Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending) | IQ Functionality is a very important value proposition for the Platforms business so we need to ensure that that shift to MyAccount provides the same functionality to Platforms Partners, and Merchants Follow up convo to en sure virtual terminals gateway reporting are solved in <18 months | TAPI → Express and merchant / MID migration drive the single-out unlock; reporting, portal, disputes, and merchant management depend on merchants landing on the target path. ProPay → Payrix migration depends on closing flexible split funding gaps before major partners can reintegrate. OpenEdge HPP, XCharge, and RCM movement through TAPI is a gating dependency for migrating related portal, reporting, disputes, and merchant-management experiences. Gateway reporting and virtual terminal taxonomy need to be clarified, including where these sit in the new subdomain model. Partner experience / residuals ownership must confirm whether EPE / EPPE covers Integrated partner residuals and platform needs, including any gaps from current Marketo-based residual handling. Target portal design must account for Integrated partner needs, not just merchant authorization / settlement data. Reporting, disputes, and merchant management APIs need to follow transaction APIs quickly; Curtis called these fast followers around Q4 / Q1 so partners are not left with transaction access but no operating capabilities.
| Reporting |  | Reporting • EMAF • Payrix reporting & reconciliation (Cornerstone remediation) • Pazien • TAPI Reporting API • TAPI iFrame Reporting API • Global Merchant Portal API | Data platforms • Snowflake + Iceberg Master data • MDM • [BUILD] Enhanced reporting intelligence layer — uniform data codification for reporting and reconciliation, aligned with Pazien direction • [BUILD] Automated merchant migration tooling — processor-to-processor moves for software platforms [Build] Utilize a target-state CDP data platform for consistent reporting | Sell • EMAF • Payrix reporting & reconciliation (Cornerstone remediation) • TAPI Reporting API Support/Maintain • Global Merchant Portal API • TAPI iFrame Reporting API |  | hGP SMB / Partner reporting platform SFG (for file delivery) | We need to provide consistent Reporting API and File Feeds with standardized Reports as well as custom query capabilities via API
| Billing |  | • Payrix • CORE • VAP • GMAS • USI • TMAS |  | Sell • Payrix • CORE • VAP Support/Maintain • GMAS • USI • TMAS |  | CORE+
| Disputes | [5 empty] | WDP (to be renamed)
| Payouts |  | • Payrix -Dynamic Payouts • Payfac - Core/VAP • integrated-Core/VAP | • (Build) Split more Flexibile Funding Capabilities/Vendor Payouts on Payrix that willl allow ProPay Partners to migrate to Payrix • Integrate Payrix to WPAP P2X - drive Payfac to WPAP P2X - integrated to follow Payouts/wallets for SMB | • Sell | • Migration and dcom DPO integration | hWP WPAP | • Confirm the scope for Payrix US • Dependemcy on P2A party-boarding, T0, debit ACH
| Funding |  | • CORE • VAP • Payrix • ProPay • GMAS • TMAS/Broomfield | (Build) Split more Flexibile Funding Capabilities/Vendor Payouts on Payrix that willl allow ProPay Partners to migrate to Payrix leverage hWPAP Payouts and P2X experiences | Sell • CORE • Payrix • VAP (Contingent on ACH Platform decision) Support/Maintain • ProPay • GMAS • TMAS/Broomfield | migration of backbook to payouts experiences | hybrid. hWPAP for payout experiences.
| Residuals |  | • Marketo • EPPE • OpenEdge Commissions | Migrate + Decomm OpenEdge Commissions | • Marketo • EPPE ? |  | hWP EPI solution | Confirm david P & raji - ensure residuals accounted for across SMB & Partners
7 · Data | MDM (Master Data) | [5 empty] | Reltio (MDM)
| Real-time data | [5 empty] | Resilient real-time ingestion | First mover decision
| Reporting | [5 empty] | Semantic layer
| Others |  |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure) |  |  |  | We need to ensure that Data Centers and dependent platforms, and reporting portals are in an environment that provides high availability, and low latency for our Partners and Customers
Data from Enterprise sequencing plan
7 · Data | MDM (Master Data) |  | Informatica MDM, Reltio | Build - Establish a trusted enterprise identity foundation by aligning the Party Model with Onboarding (HUB), strengthening data quality, governance, stewardship, enrichment, and identity management capabilities. Operationalize MDM: Embed trusted identity into onboarding, CRM, and priority business processes through standardized integration patterns, governance, and enterprise adoption. Publish mastered identity and relationships to the data platform. Migrate - Transition to a single enterprise MDM platform by migrating priority consumers to Reltio, consolidating capabilities, and enabling a unified identity strategy across Global Payments. Retire - Eliminate new development on Informatica and execute a phased sunset plan to retire legacy MDM capabilities and reduce operational complexity. | Reltio (D&B Marketplace for data) |  | Reltio (MDM)
| Data Acquisition including real-time |  | Custom data pipelines, Snowpipe, Kafka (EDIA), Fivetran, GoldenGate, Confluent, AWS MSK, GCP MSK, Attunity, DataStage, Nimbus, DPaaS, Global Token Service, Mulesoft | Build - Stand up target platform​; Iceberg materialization​; Flink SQL standard for stateful transforms​; Reference pipeline templates + CI\CD​, implement schema evolution, schema management and replay\reprocessing mechanism​; NRT Iceberg Ingestion + Audit logs + SLOs,​ Capture RT events from event types, front end and back end platforms, standardize target state tokenization platform, ingest from data producers (batch and real-time), real-time ingest from data producing system into lakehouse; pilot for relational SLA workloads (1-2 identified), build MVP ODS (dev/test/prod provisioned); Platform Deployment & Core Configuration​; Standard Ingestion Pattern Definition​; Connector Gap & Extensibility Strategy​; Establish governance frameworks (data ownership, onboarding standards) Migrate: Move <1hour latency batch processes, consolidate fragmented clusters; consolidate existing OLTP stores Retire: existing OLTP stores | Snowpipe, Fivetran, Kafka, Tokenization platform (Databolt), Kafka stream (TBD) |  | Resilient real-time ingestion
| Data foundational build |  | hWP CDP, hWP NDP, hGP Caspian, hGP TIDAL, Snowflake, GCP BQ, Databricks | Build - implement data sharing framework between hGP and hWP, data contract approach, build 11 core domains (out of 26), align with new eventing architecture, unified enterprise data model, integrate with EDC, reusable enterprise data products through semantic layer​; Establish separate dbt Cloud projects; Configure foundational core metrics ​; Enforce dbt model schemas & contracts Migrate - CDP to NDP and Caspian to TIDAL, Connect independent dbt Cloud projects to separate GLOBAL_PROD and WORLDPAY_PROD Snowflake databases Retire - CDP and Caspian | NDP, TIDAL, Snowflake, Databricks
| Reporting |  | Business Objects, Cognos, SSRS, Kepler, Oracle BI, Microsoft AX, Power BI (Oceania), MicroStrategy, Tableau (Partner Portal) | Build - reusable enterprise data products through semantic layer, establish dbt Cloud projects, configure foundational core metrics Migrate - connect independent dbt Cloud projects to Snowflake databases, migrate reports away from MicroStrategy and SSRS Retire - MicroStrategy, SSRS Use cases: Authorization executive dashboard, Reporting 2.0, Customer 360 | Cognos, Looker SaaS, Power BI, Tableau, Sisense, TBD [target BI tool], in-house tool (Pulse) |  | Semantic layer
| Data Risk & Data Trust |  | Informatica, Alation | Build - Stewardship framework, end-to-end workflow ownership, risk-tier rules, data lineage and data catalog/context expansion, agentic governance framework/tooling (TBD), embedded data trust into domains and products Migrate - prepare Alation to Informatica migration Retire - Sunset duplicate intake paths and manual status tracking, stop unmanaged governance processes | Informatica, Alation |  | TBD
| AI |  | GCP, AWS, Azure, Snowflake, Databricks | Build - build and productionalize sandbox, stand up AI Gateway MVP, identify and develop reusable components and golden path of operationalization Migrate - prepare for cloud platform migration, align teams to standardized tooling and architecture platforms Retire - potential retirement of Azure, decommission non-strategic experimentation environments | GCP, AWS, Snowflake, Databricks - TBD |  | TBD
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm if required.

## RoW
Integrated — RoW Sequencing
|  |  |  | Focus for discussion |  | Not focus for today
Boulder | Rock | Proposition | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies | Business priorities | Corporate priorities
1 · Single in | Global API |  | • Integrapay • EZDebit (various) • TakePayments | Focus on Front-book priorities and activities • (Build) Expand Verifone Card Present Integration for Oceania • (Build) Reconciliation Transformation for IntegraPay Card Present Transactions • Integrate front Book to IntegraPay Platform • Decomm TakePayments ISV • Wrap international payments with API 2.0 • ASSESS - Opportunity for funneling EZDebit Traffic to WPG/NAP • ASSESS - Proprietary Card Present Solution for Platforms International (SMB Genius Work with TriPos may unlock this) | Sell • Integrapay • EZDebit (Deal Review Process Required) | • [EXIT] Decommission duplicate integration front doors once partner migration completes •[Migrate] Migrate From TAPI towards global API" | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on API 2.0 | Long Term International Strategy and Migrations aligns with TAM 2.0 and dependent on Cross Domain Deliverables to Target State Follow up with Lucy on how to remap APTM 1.0 and make for Australia sepcifically (JR to follow up in person in~ 2 weeks)
| PayApps |  | • Verifone (3rd Party) • Quest Cloud API (3rd Party) • SmartPay (3rd Party) | • (Build) Expand Integrapay Verifone Card Present Integration for Oceania | Sell • Verifone (3rd Party) Support/Maintain • Quest Cloud API (3rd Party) • SmartPay (3rd Party) |  | Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience
| MDM/TMS |  | • Verifone (3rd Party) • Quest (3rd Party) • SmartPay (3rd Party) | • (Build) Expand Integrapay Verifone Card Present Integration for Oceania | Sell • Verifone (3rd Party) Support/Maintain • Quest Cloud API (3rd Party) • SmartPay (3rd Party) |  | Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience
| Developer Portal | Omnichannel | hWP IntegraPay Developer Portal EZDebit Developer Portal | Build - Net new experience (nGP) for front book | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc. Near Term, we need to maintain the existing IntegraPay and EZDebit Portals Longer Term, we will leverage the developer portal thar aligns with Single In
| SDKs | Omnichannel | SDKs - connected to Integrapay | Build - Connect Server-Side SDKs to Global API | Sell • Integrapay SDK | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs | Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm
Unified Prop
| Hosted Solutions |  | • Integrapay HPP • Ezidebit HPP • Takepayments HPP | Evaluate path to replace Integrapay HPP with HPP+ [Align] PBL engine | Sell • Integrapay HPP Support/Maintain • Ezidebit HPP • Takepayments HPP |  | HPP+, Hosted Components
| CP |  | • Verifone (3rd Party) • Quest Cloud API (3rd Party) • SmartPay (3rd Party) | (Build) Expand Integrapay Verifone Card Present Integration for Oceania [BUILD] Close single in front-book gaps (API, paymentapp/SoftPOS, CP) for Ezidebit/Integrapay (Assess) whether API 2.0 model via TAPI can work for current in market MitC equivalent | Sell • Verifone (3rd Party) Support/Maintain • Quest Cloud API (3rd Party) • SmartPay (3rd Party) |  |  | • Tesco and Walmart may be exceptions as direct-to-acquirer |  | Get off TMAS / GMAS
| CNP |  | • Integrapay • Ezidebit • Takepayments | • [BUILD] Close single in front-book gaps (API, paymentapp/SoftPOS, CP) for Ezidebit/Integrapay | Sell • Integrapay Support/Maintain • Ezidebit • Takepayments |  |  | • Slow development on WPG and move customers onto Access • Taiwan needs a focused conversation (follow up) • Confirm the cuts needed, for example volumes and verticals, to assess first-mover enterprise customers; no information is currently available • Over the next 18 months, replicate the AP exercise for GMAS EU enterprise customers and identify single-out work to prioritise for JV customers |  | Get off Cybersource and MPGS
| Hosted | [8 empty] | Dependency on Cayan TSA exit for identity
2 · Boarding | Orchestration |  | Salesforce Digital App | • [BUILD] Align UK partner boarding to Ignition / the hWP party model as it lands • [Build] Build boarding capabilities for Oceania needs |  |  | See TAM target state | • Resourcing is a challenge, with neither the right skills nor the capacity • Need Product Management resources to gather detailed requirements (~3-5 people) • Some shortfall in engineering resourcing for PIL implementation, for example Payouts, APMs, and Disputes
| CPQ |  | Oracle CPQ | • [BUILD] l-GP UK/I for RCA in ISI and iNASA | Oracel CPQ RCA |  | • [BUILD] eWay & eziDebit in RCA for ROW Salesforce) | RCA
| Experience |  | • Launchpadx • Horizon • Tuza • Takepayments | • [BUILD] Convergence application - Ignition | • Launchpadx • Horizon • Tuza • Takepayments |  | Ignition | Gap analysis needed for Tuza vs Horizon Requirements needed for Ignition (convergence of Launchpad & Horizon)
| Underwriting |  | • Salesforce Risk Engine • HealthMonitor (Appian, et al) |  |  |  |  | • Assessment needed to understand the current process and ensure UCM is fit for purpose for SMB and integrated, can service enterprise, and supports pKYC (underway)
3 · Payment processing | Gateways |  | • Integrapay (IntegraPay connects to WPG) • EZDebit • TakePayments • Cybersource | • [MIGRATE] Consolidate Ezidebit — onto Integrapay or TAM 2.0 target-state rails (decision required; interim hop vs wait-for-target trade-off) • [STOP] Constrain new builds on eWay and Ezidebit to critical maintenance • [Migrate] move eway/ezidebt off Cuzcao • [Build] Enable Multi-MID for functionality • [Build] close front-book gaps for Ezidebit and Integrapay to enable Integrapay front-book sales • [Migrate] Move to acquiring via NAP for eWay/ezidebit • [STOP] Research/investigate eWay/ezidebit decom plan | Sell • Integrapay Support/Maintain • Ezidebit • Takepayments • Cybersource |  | "Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on API 2.0 • [EXIT] Decommission duplicate integration front doors once partner migration completes •[Migrate] Migrate From TAPI towards global API" | • WPG to support a small tail of traffic; the rest use the Global Gateway
| APMs |  |  | -Evaluate how existing ROWS APMs could be leveraged for channel
Eventing
| Switch |  | • Olympus -> to Schemes | Assess - Integration from Olympus to WPG->NAP | Olympus -> WPG -> NAP |  |  | Need decision now on WPG connection
| Acquiring / Funding |  | • Integrapay - NAP • eWAY stack (Auth - Cuscal and eftpos, Settlement - Highlander) |  | Sell • Integrapay: NAP Support/Maintain ezidebit & eway: WPG->NAP + Highlander |  | TAM 2.0 target state | • Align on the engagement model with Legal, Risk, Compliance, and Tax • Stand up a cross-functional working group on acquiring licensing, legal-entity cleanup, and dedup • Point person from Legal is Melissa Perreira • Helix support model uses existing resources plus Endava contractors (funded to Jun '28, with a gradual ramp-down) • Confirm the ramp-down, as we may want to retain resourcing to accelerate (baked into the build sheet)
Transaction monitoring
4 · Sales and servicing | CRM |  | • Salesforce Sales Cloud (EZDebit) • Salesforce Sales Cloud (IntegraPay) • HubSpot | • [BUILD] l-GP UK sale flows for iNASA with going to new boarding TAM | iNASA ROW Salesforce (ISI) eWay EziDebit | • [BUILD] eWay & eziDebit (AUS) for ROW Salesforce • [BUILD] l-WP into new boarding TAM | iNASA (NA + UK) ROW Salesforce | Will have work with Payrix/Assist sunset to pull partner and merchant records in. Need to figure out where in sequencing that goes.
| Servicing |  | • Salesforce Service Cloud (multiple)
5 · VAS | Routing | [5 empty] | Dynamic Routing 2.0 | Debit Routing right now is exclusive to NA. Future state is to enable this to interoperate across int’l b-schemes like EFTPOS, JCB, etc (further reason in the need to decouple as a micro service.
| Gifts |  | • hWP Premier • hWP Valutec • hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Sell • hWP Premier • hWP Valutec • hGP Engage | Migrate - Premier to Engage [no impact to RoW] | Engage, Valutec | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration
Loyalty
| Payment tokens |  |  | Does integrapay passthrough to WPG today? |  |  |  | • BAU; accelerate the unified credential vault architecture
| Managed Optimization (incl. nw payment tokens) |  | • Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 | Revenue Boost Microservice |  | Revenue Boost 2.0
| DCC |  | GPE DCC | Leveraging GPE DCC for PL (Greece)
| 3DS |  | • 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | • Kount • FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  | • VAP using Scheme settlement rates | TBD requirements for multi-currency pricing/settlement on Core to support VAP thinning |  |  | hWP FX
| Risk / compliance |  | • Health Monitor
| Cred management |  | • Salesforce Risk Engine • HealthMonitor (Appian, et al) • Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API | Access tokens | Unified credential vault
6 · Single-out | Portals |  | • Highlander • NAP • Takepayments portal • Ezidebit Portal • Integrapay Portal | Migrate/Decomm Integrapay Portal |  |  | Align Payrix,Assist and Integrapay Partner/PFaaS capabilities and embed into myAccount++
| Reporting |  | • Highlander • NAP |  |  |  |  | • Follow up with Vikrant Gupta on the reporting solutions being built out
| Billing |  | • Highlander • Netsuite |  |  |  | TAM 2.0 target state
| Disputes |  | • Integrapay Console
| Payouts |  | • Highlander • NAP • hWPAP payouts | hWPAP payouts and P2X flows | Sell • NAP • hWPAP payouts Support/maintain • Highlander |  | hWP WPAP | • Operational support needed on the Treasury Management side • Dependency on transaction management • Payrix/Integrapay analysis
| Funding |  | • eWAY stack (Auth - Cuscal and eftpos, Settlement - Highlander)Highlander (hGP) • NAP (hWP for IntegraPay) | hWPAP payouts and P2X flows | Sell • NAP • hWPAP payouts Support/maintain • eWAY stack (Auth - Cuscal and eftpos, Settlement - Highlander) |  | hWP WPAP
| Residuals |  | • Aperia • Integrapay Console |  | Sell • Integrapay Console Support/maintain • Aperia |  | TAM 2.0 target state
7 · Data | MDM (Master Data)
Real-time data
| Reporting |  | Highlander NAP |  |  |  | TAM 2.0 target state
Others
8- Global Infrastructure & Security (incl. data centres) |  |  |  | [Migrate] Migrate Integrapay towards Cloud |  |  | TAM 2.0 target state
| Design system |  | Worldpay Vega Index | Consolidate into one system | Continue maintenance of three, pilot teams to adopt consolidated system (My Account, Genius) | Decomm Vega and Index | Global Design System (Worldpay as Foundation, leveraging, Vega and Index assets) | Risks and mitigations: Risk: TSA / access constraints: Sequence pilots around feasible access and repository constraints Migration must be design driven and start with front loading 0-6 months for standards. Implement design gates before scale; standards council owns component acceptance
Note on F6: Karel Jára: @scvo
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm if required.