## Index
TAM 2.0 ¦ SMB Sequencing
Section | Sheet
UK&I | Back-book - Approach
UK&I Sequencing
UK&I Front-book Sequencing
North America | NA Direct
NA Wholesale
NA Indirect
NA ISO
Rest of World | RoW (excl. UK&I)
Back-book Considerations
Migration considerations |  | Operating principles
Funding windows | Confirm that settlement timing and funding windows do not shift in a way that disrupts merchants who rely on early funding | Payment flows are the critical path | Focus on CP & e-commerce transaction flows need real design work; We move merchants to the target rails by migrating how they are funded (their BIN and ICA). Once funding moves, boarding, servicing and CRM follow
Pricing | SMB merchants are mostly on fixed pricing; Where interchange-plus applies, the cost per transaction must not rise after the back-end changes | No net-new on non-target platforms | We will not add features to Evo/e-service, GMAS Europe or Greenhouse; New capability is built only on the target rails
Feature-parity assessment | Segment the book by MCC and by volume (CP vs. CNP), and use usage data to confirm which capabilities merchants actually rely on | Work on exiting platforms needs an exception | Any engineering effort spent on a non-target platform must go through an exception process, so we do not extend its life
Statements | Be transparent with merchants about what changes on their statements after migration | Parity is not the goal | We accept that a small tail of capabilities will not be rebuilt before sunset
Re-papering and Re-CDD | Re-papering is generally not required; Avoid repeated CDDs | Consolidation is not decommissioning | We commit to switching platforms off, not just moving volume, so the estate actually shrinks
Merchant Retraining | Plan for merchant retraining, which matters more for stable businesses than for high-turnover ones such as restaurants | Resiliency scales with consolidation | As volume concentrates on fewer platforms, the impact of any outage grows; Invest in resiliency, observability and faster fail-over for target platforms
Data-programme alignment | Use this migration to accelerate the homogenised data and statements work (the BFS data programme)
Settlement Options | Beneficial for savings but may require re-papering
Banking relationships / other contractual relationships | Account for existing banking and contractual relationships, e.g., HSBC and BOI
Third-party gateways | Decide the disposition for third-party gateway merchants, whether to sell off the book, migrate, or pursue other options
Ecommerce software | Assess the ecommerce software merchants use, since the ability to migrate depends on it
Trailing activity | Plan for trailing activity such as chargebacks and refunds that arrives after a merchant has migrated, ensuring it is processed correctly across the target platforms

## UK&I Sequencing
Tab title (save and calculate to sync)
|  |  |  | Focus for discussion |  | Not focus for today
Boulder | Rock | Proposition | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities
1 · Single in | Global API |  | WP eCom (Access); GP API (BOIPA) | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | GPAPI / Access current versions (v1) back book and Global API for front book (v2) | Migrate — merchants onto v2 Decomm — v1 (later) | Global API
| PayApps/MDM/TMS |  | e-service PayApp for PAX & Ingenico Ingenico App - Ingenico managed UPA for Verifone PAX positive App for PAX Ingenico Nerpay - hWp TriPOS for Ingenico - hWp Yazara as part of Genius M Depriciated - Apriva mobile Pay (except iPhone) | Build - Genius S integration with TriPOS Build - Nucleus/PayApp 2.0 for hWP processing stack to replace NERPAY and be ready for Genius S, for standalone and semi-integrated Build - finish Nucleus/PayApp 2.0 development to cover all remaining gaps to replace UPA, Ingenico managed, e-service, PAX positive for hGP (e-service+Green house trhough PowerZAC) | Decom/Migration - UPA, Ingenico managed, e-service, PAX positive for hGP (e-service+Green house trhough PowerZAC)
| Developer Portal | Omnichannel | hGP Developer Portal hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migreate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | SDKs - connected to Access - connected to GP-API | Build - Connect Server-Side SDKs to Global API See also CP / Genius S & N below | SDKs - connected to Access - connected to GP-API | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | Extensions - connected to Access - connected to WPG - connected to GP-API | Build - Connect Target State Extensions to Global API | Extensions - connected to Access - connected to WPG - connected to GP-API | Build - Merge Extensions to single instance Migrate - Customers on non-Global API stacks to Global API via Extensions Decomm - Non-Global API Extensions |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
Unified Prop
| Hosted Solutions | eComm | hWP HPP | Build — conform HPP to global API standard Build — Components SDK for Cards, APMs, Wallets Align — Virtual Terminal approach (go foward for VT is via Payments Center Paymemts Links+ as interim) Decomm — Business Gateway | HPP (conformed) Payments Link+ (Stored) | (VT target approach TBD) | TBD |  | 4. Bank channels — BOI, Virgin Money/Nationwide, HSBC (Tuza, eComm, Genius Mobile, Dashboard hooks) | • Fragmented hGP/hWP sales tooling & portals — operational inefficiency and disjointed merchant journey
| CP / Genius S | Genius | TriPOS / EMBOSS | Build — Genius S payment: integrate with TriPOS SDK Build — Merge TriPOS SDK + GP SDK Build — Bridge to Nucleus (integrate GP SDK to Yazara) Align — Terminal fullfilment TBD | TriPOS with bridge to Nucleus | (no further change) | TriPOS / Nucleus Combined solution | • Genius resold under Worldpay UK Ltd • hGP back-book (Evo, Take Payments, GPUK) to be repapered to WP entities | 1. Genius S UK — decision confirmed; development on NAP target-state rails, Q1 '27 pilot | • BG migration — audit deadline extended to Jul '27; automated migration scripting blocked on infrastructure database capacity
| CP / Genius N | Genius | TriPOS / EMBOSS | Build — GP SDK support for new device (GP1) Build — GP SDK + Yazara MPOC for GP1 Build — Merge TriPOS SDK + GP SDK Build — Bridge to Nucleus (integrate GP SDK to Yazara) | TriPOS with bridge to Nucleus | (no further change) | TriPOS / Nucleus Combined solution | • Combined SDK requires PCI MPOC / INBOX certification (key injection, attestation), sequenced by region • Rationalise the 6 POS test and cert labs (incl. IDC) to cut certification time | 2. eCommerce expansion — WP eComm Essentials (targeting the POS back-book), Shopify Onsite plugin, payment links & invoicing | • NerPay Ingenico app sunset path (new localised ROI app unlocks next waves)
| CNP | eComm | WP eCom (Access); GP API (BOIPA) | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | v2 (front-book); v1/2 (back-book) | Migrate — merchants onto v2 Decomm — v1 (later) | Unified Global API |  | 3. VAS growth — Everyday Settlement (H2 '26, NAP-acquired merchants), DCC back-book opt-out enablement, MCA in-house (rev c.$35m '27–28), terminal leasing for hGP terminals | • ACI / Postilion BO exit by 2029 (corporate)
| Hosted | [7 empty] | 4. Bank channels — BOI, Virgin Money/Nationwide, HSBC (Tuza, eComm, Genius Mobile, Dashboard hooks) | • Fragmented hGP/hWP sales tooling & portals — operational inefficiency and disjointed merchant journey
2 · Boarding | Orchestration | All | OMS | Build — support party model Build — transition towards Boarding Gateway + Workstream Manager | Transition in flight | • Migrate - UK SMB BAck Book • Decom - OMS | HUB (Boarding Gateway Workstream Manager Product/Party Model Actor/PIL Kafka MuleSoft) |  | 5. WP360 — GA into the Irish market Q3 '26; omnichannel hospitality powered by WP eCommerce
| CPQ | All | Oracle CPQ | (continue supporting Oracle CPQ) Build - RCA in ISI (Jan '27 requirement) | Oracle CPQ RCA | Build - RCA in iNASA for UK/I | RCA
| Experience | All | Launchpad + Agent Hub + Tuza | Build — harmonize Launchpad + Agent Hub + Tuza | Ignition (harmonizing) | Build — integrate Tuza capabilities into Ignition Build - Update intgration for boarding TAM for iNASA Build - Ignition to consume RCA | Ignition | Boarding decision (Helix/UBA/Convergence) is a dependency
| Underwriting | All | FICO | Build — begin UCM Migrate — rewrite FICO rules in UCM | UCM in build / FICO live | Migrate — onto UCM Decomm — FICO | UCM | Awaiting budget approval
3 · Payment processing | Gateways | All | Emboss (Genius) WPT (*EOS) WPG / Access (eCom) GP eComm | Build — develop Global Gateway (GG) for UK&I (target rails for Genius S + eCommerce) Build — Querying from global gateway payment query service built out - likely enhancements for CP flow | Emboss (CP) + Access / WPG (eCom) | Migrate — onto GG Decomm — Emboss / legacy gateways | Global Gateway Maintain due to local requirements: - C2.0 - APF (as auth platform for Latam) - EDPS (as auth platform for Greek networks)
| APMs | eComm | — | N/A now (but live Klarna work ongoing?) - + Klarna Autoboarding | N/A | Next — build support for Klarna + other APMs | GPPaaS
| Switch | All | Supercheckout Postilion real-time GSAP EU | N/A now | Supercheckout | (no change) | Supercheckout
| Acquiring / Funding | All | NAP / SAS Postilion back office GMAS | Build — Genius S on NAP target-state rails (Q1 '27 pilot) | NAP / SAS | Migrate — off SAS Decomm — SAS | NAP / PowerZac
| Transaction monitoring | All | IBM Safer Payments / Brighterion / sanction screening / Activize | TBC | TBC
4 · Sales and servicing | CRM | All | iNASA (into Boarding Gateway) | Build — integrate Genius into iNASA Migrate - Migrate users from ISI to iNASA (possible small build need) | iNASA | Build - Update intgration for boarding TAM for iNASA | iNASA
| Servicing | All | iNASA; Siebel (NAP) | Build — commissions on hGP Salesforce Migrate — stop boarding hGP SF into hGP CRM → board into iNASA Migrate — complete in-flight capability migration | iNASA | (continue) | iNASA
5 · VAS | Routing | All | (to confirm) | Converge under combined Payment Optimization | — | — | Dynamic Routing 2.0
| Gifts | All | hWP Premier, hWP Valutec, hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Premier, Valutec, Engage | n/a | Engage, Valutec [no impact to UK&I] | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration
| Loyalty | All | (none in WP stack) | Build — integrate COMO into hWP stack | COMO (integrating) | — | COMO
| Payment tokens | All | Access tokens (security) | Build — route via credential API | Credential API | Build — unified credential vault | Unified credential vault
| Managed Optimization (incl. nw payment tokens) | All | Revenue Boost (eCom) | Build — invest in & build Revenue Boost 2.0 Validate — data reqs / elements to Ravelin | Revenue Boost 2.0 (build) | (extend to back-book) | Revenue Boost 2.0
| DCC (Genius) | All | Emboss DCC hWP (Genius) | Build — FX service + BIN lookup | Emboss DCC | Migrate — to target-state DCC | Target-state DCC (FX + BIN lookup) | • Required to sell Genius in UK and Ireland • Not available for pilot; targeted for GA in Q2
| 3DS | eComm | 3DS / WPG Flex (eCom) | Build — put hGP 3DS behind 3DS Flex | WPG Flex | (unify onto 3DS Flex) | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud | All | FraudSight (eCom) | (continue) | FraudSight | Build — converge under Payment Optimization | FraudSight
| FX | All | (to confirm) | Standardize comparable capability | — | — | hWP FX
| Risk / compliance | All | Viking Cloud (PCI compliance), Safer Payments (sold to SMBs) | Continue work already underway Align — tool to target capability & cost | Incumbent (do not stop) | (target TBD — not decided; do not time-bound) | TBD
| Cred management | All | (to confirm) | Route to unified credential vault | — | Build — unified credential vault | Unified credential vault
6 · Single-out | Portals | All | WP Dashboard | Build — WP Dashboard as MFE Build — surface MFE through MyAccount Build — converged portal on MyAccount; Genius back office | WP Dashboard (MFE) via MyAccount | (continue; terminal fulfilment TBD) | MyAccount 2.0
| Reporting | All | WP Dashboard | Define — how to normalize, expose & integrate internal + external reporting (large dependency) | Definitions in progress | (converge) | hGP SMB / Partner reporting platform SFG (for file delivery)
| Billing | All | NAP B&F ZSFK | Build — add support for Genius products (integrated with auto boarding) Build — Applying Tax across the new Products Build — surface statements / pricing to partners Build — include new products into invoices/statements Build — GL accounting for back-office activities Build — partner-branded statements (where applicable) Build — Support third party gateway billing Build — Work required for Instalments (yet to be assessed) | NAP B&F(config) | (continue) | NAP Billing
| Disputes | All | WDP → iQ, WP Dashboard, WP SSO | Build — integrate to new portal approach | WDP (current integration) | (continue) | WDP (to be renamed) | • Consolidate access points (iQ, Dashboard, myWorldpay SSO) to a single merchant credential
| Payouts | All | WPAP (none on hGP) | N/A now | hWP WPAP |  | hWP WPAP (target state is a P2X platform that utilises existing WPAP assets) | • SMB requires a simplified Payout product model for autom boarding
| Funding |  |  | explore - Funding requiremetns for JVs and strategic partners |  |  | NAP Funding | Funding requirements for JVs and strategic partners
| Residuals | All | hWP EPPE solution | Build - Additional contracts for partners and integration to billing for the new products to calculate rev share (if partner model is applicable) | hWP EPI solution |  | hWP EPI solution
7 · Data | MDM (Master Data) | All | n/a | Migrate — transition + align ownership into Data org Build — product catalog, pricing & party model |  | (continue) | Reltio (MDM) | • Party model not yet built for SMB hierarchies (it exists for enterprise) • UK pKYC follows separate MDM flows; align with Rajesh and Himanshu
| Real-time data | All | (to confirm) | Build — foundation from ingestion with resilience Follow-up — eventing in auth platform Validate — data reqs for Revenue Boost 2.0 |  | (continue) | Resilient real-time ingestion | • Define the data-availability SLA (sub-second debated) for query and reporting • Source from gateway query events rather than auth-platform eventing • Follow up on eventing in the auth platform
| Reporting | All | (to confirm) | Build — semantic layers for data platform |  | (continue) | Semantic layer
| Others | Genius | (to confirm) | Payment request service to target state data repository; eventing already in place for payment requests service

## UK&I Back-book - Approach
Tab title (save and calculate to sync)
UK&I Back-book Priority portfolios to exit |  | UK&I Back-book Trade-offs / key decisions
Evo / e-service | hGP SMB book that runs on the e-service platform (ACI-based, ~60% volume is CP); Key exit priority as moving to the target rails lets us exit ACI and supports the Project Carbon data-centre closure | E-commerce integration | These merchants are already integrated to GP API. The choice is to: (i) bridge GP API to the target Access gateway so they keep their integration, or (ii) require them to reintegrate onto Access directly (recommended) Either path depends first on publishing the new Global API standard. Worldpay eCommerce backbook already processing on Access so move to Global Gateway processing should be seamless
GMAS Europe | Migrating merchants to the target rails reduces dependency on FIS and enables closing the TSA | CP integration point | When swapping terminals, the choice is to: (i) route it through the target stack (terminal → Nucleus → host) or to (ii) keep a legacy direct-to-host connection Terminal heartbeats allows for the change to be pushed remotely, without a site visit
Greenhouse | Migration will allow Allows all UK&I SMB to converge to one stack | Migration sequencing and BIN / ICA structure | The choice is to (i) migrate small and mid-size merchants first onto a new BIN / ICA and leave large enterprises (which hold their own BINs) to a later wave, or (ii) to move the whole book at once
Take Payments | Still runs on its own CRM and dialer, which are not connected to other systems; Payment application (Take Payments Plus) is planned to switch to Genius

## NA>>
Corporate priorities | Consolidated Dependencies
1 · Single in | CNP / Global API Finalize API 2.0 standards across GPE API, Access, and TAPI so SMB follows the common API model rather than a separate SMB-specific design. Resolve Global Gateway timing and whether SMB NA uses a staged WPG-backed route before the cleaner target path is ready. Align with Boarding / CRM on iNASA sales compensation, pricing, and hierarchy prep before Direct merchants can fully board onto Heritage Worldpay rails. Account for channel rail differences: ISO still has meaningful GSAP / GMAS volume, while Indirect is primarily Express / MMS. CP / Payment apps Align Payment Apps / Payment Processing on the Genius → TriPOS → Express path so omni-channel front-book merchants use consistent backend rails. Confirm TriPOS / Express readiness before shifting Genius front-book volume. Align Nucleus timing with payment-app modernization so legacy app investment is not extended unnecessarily. Segment merchant populations by CP, CNP, omni, and Genius usage before sequencing partner or portfolio migrations.
2 · Boarding | Complete iNASA sales compensation, pricing, and hierarchy prep before Direct SMB merchants can board cleanly onto Heritage Worldpay rails. Align UCM scope, budget, and LOE across Launchpad + iNASA before retiring FICO-dependent workflows. Confirm UBA readiness for Wholesale / partner boarding into Sierra / TMAS. Align with Data / MDM on product catalog, pricing catalog, merchant hierarchy, and configuration inputs. Sequence Boarding with Single-in / Payment Apps so merchants boarded through iNASA, Launchpad, or UBA land on the correct API 2.0 / Express / TriPOS target paths.
3 · Payment processing | Confirm Global Gateway timing and which shared services can be carved out of Portico / TransIT first. Align Express interim moves with acquiring-platform readiness across MMS, Sierra, TMAS, GSAP, and GMAS. Segment SMB NA populations by channel — Direct, Wholesale, Indirect, ISO — and current rails before sequencing gateway migrations. Align Boarding with downstream acquiring rails so Launchpad / UBA boards merchants into the right Sierra / TMAS / Express / MMS path. Coordinate with Single-in so API / gateway entry decisions do not create duplicate routes into Express, Portico, TransIT, or Global Gateway.
4 · Sales and servicing | Complete the iNASA OMS, USI, and sales-comp gap closure before Direct net-new merchant enablement can scale. Define the iNASA servicing capability gaps by end of month: what iNASA already supports for banks / ISOs vs. what Base, Central Station, OnTrack, and MAP were expected to cover. Decide whether servicing must connect to Sierra / TMAS during the transition, or whether merchants should migrate to Heritage Worldpay rails first. Align with Boarding on Launchpad / UBA → Sierra / TMAS because servicing must follow the same partner / merchant transition path. Include sales and servicing scope in the FICO → UCM budget / LOE rework, since Launchpad and iNASA modifications create downstream servicing implications.
5 · VAS | Tie disputes sequencing to Payment Processing migrations: merchants get the target disputes experience once their payments process on the underlying target platform. Confirm whether DIMS → Worldpay Disputes Platform needs direct migration work, or whether it can follow naturally as processing moves to Core / Raft / new host. Align dynamic payouts with the payouts workstream; do not treat it as solved inside SMB VAS unless ownership and timing are confirmed. Align ACH / e-check, FX, multi-currency, and DCC with Core / acquiring work before removing those capabilities from VAP-related patterns. Account for channel differences: Indirect largely follows Express / MMS, while ISO still has meaningful GSAP / GMAS plus Sierra / TMAS exposure, so VAS sequencing should not assume one migration pattern.
6 · Single-out | Complete EPI / EPPE parity for Base, Central Station, and MEA residuals before decommissioning those outputs. Resolve reverse rev-share requirements for Indirect, including funding, billing, invoicing, and data feeds into EPI. Align with Boarding on Launchpad / UBA and Wholesale partner migration, since partner boarding and partner payments need to move together. Align with Sales & Servicing on partner portal and servicing needs across Direct, Wholesale, Indirect, and ISO. Confirm whether CBOS / eConnections / TransLink stay as interim portal experiences, plug into a target layer, or require replacement.

## NA Direct
Tab title (save and calculate to sync)
|  |  |  | Focus for discussion |  | Not focus for discussion
Boulder | Rock | Proposition / Portfolio | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities
1 · Single in | Global API | Omnichannel | GPAPI (for frontbook), backbook still on Portico/TransIT | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | GPAPI current versions (v1) back book and Global API for front book (v2) | Migrate — merchants onto v2 Decomm — v1 (later) | Global API
| PayApps |  | HGP/hWP OEM/3rd party, UPA | Build — Close feature gaps for Nucleus to NA Migrate — migrate UPA to Nucleus Migrate — OEM/3rd party to Nucleus | UPA, OEM/3rd party apps |  |  | • FOR DISCUSSION - How to accelerate path on UPA (Timline for freeze on UPA feature build)
| MDM/TMS |  | OEM, in-house | Build — TAM deplpyment-as-a-service (DaaS) platform (Scalefusion) Migrate — OEM/3rd party to DaaS | OEM, in-house TMS platforms
| Developer Portal | Omnichannel | hGP Developer Portal hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migreate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | SDKs - connected to Express - connected to GP-API | Build - Connect Server-Side SDKs to Global API See also CP / Genius S & N below | SDKs - connected to Express - connected to GP-API | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | Extensions - connected to Express - connected to GP-API | Build - Connect Target State Extensions to Global API | Extensions - connected to Express - connected to GP-API | Build - Merge Extensions to single instance Migrate - Customers on non-Global API stacks to Global API via Extensions Decomm - Non-Global API Extensions |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
Unified Prop
Hosted Solutions
| CP / Genius S |  | Terminal management (Gecco) Portico Admin Svc. Datacap (for payment terminal connectivity) hWP - Jigsaw (terminal mgmt.) | Build — Underway for building for Genius S (leverage same work for direct ) ASSESS - Jigsaw vs. Gecco |  |  | TriPOS / Nucleus Combined solution | • Sales commission is a key dependency • Current split is 66% Heartland, 33% TSYS, 1% NWS | • Genius S (core goals) - Accelerate Core North America Growth, Improve Merchant Experience (onboarding key), Expand Selectively in Strategic Markets (UK&I, Erste JV support, BOP (Mobile Only)) | • Separation project (TMAS / GMAS) to CORE, first priority GMAS then TMAS
| CP / Genius R/N |  |  | Build - GPSDK + TriPOS support for GP1 Per path support needs to be prioritized UPA stability plan to be executed while reducing tail of UPA in market (plan to migrate off UPA) BUILD - Converged path for Nucleus + TriPOS |  |  | TriPOS / Nucleus Combined solution | • GPSDK + TriPOS path should be enabled for non-Genius customers as well to get them onto the right rails (discuss on 21st Wshop - define pattern) | • Genius S (Execution Priorities): Launch Genius S into Worldpay FI Channel (Q3), MyAccount Genius Portal SSO, Merchant Onboarding & E2E Experience, resolve bugs with GP SDK | • GNAP to GSAP NA (ACI Consolidation project)
| CNP |  | GPAPI (for frontbook), backbook still on Portico, Access | BUILD - Protocols for GG BUILD - API 2.0 to Express Build — Build API 2.0 (continue supporting the Access API for a defined period) Build - Global Gateway US instance of Access (24+ months) | API 2.0 to Express | Thin/decom - Converge to global gateway | Unified Global API | • TAPI to converge to the new API standard; this is the driver, as TAPI to Express is needed for integrated • Define target solution path for personas (e.g. existing ecomm cx, omnichannel customers, Genius only customers) - for workshop on 21st | • Genius N Value Drop 1.1 (Jan '27) - US (hGP rails: Merchantware, GSAP/Sierra, GMAS) - enables existing Genius N first-party payment front-book via Merchantware, existing Stadia & Enterprise QSR (7Brew, CKE, etc) | Prioritize TMAS migration
| DevEx |  | GP Developer portal, hWP - Docs.Worldpay | BUILD - Consistent exp. Across heritage stacks (tied to design w/ Max B.) |  |  |  | • Follow up with Sean M. to replicate the design playbook
| Hosted |  | Portico VT, Payplan CNP - Major shopping card plugins, Drop in UI (front book) | Build — conform HPP to global API standard Build — enable hWP HPP on GPAPI Design — Components SDK on GAPI Align — PBL engine |  |  | TBD |  | dependencies: GP API + GPSDK boarding, TAPI, SDK integration?
2 · Boarding | Orchestration |  | Instant Boarding WebTops Onboard Merchant Enrollment Advantage (MEA) MMS Discover Enrollment System (DES) Genesis Client Manager SEAT Flex (EVO boarding) UBA integration | Augment iNASA to comply with tgt state boarding ASSESS - First movers (EVO, TSYS) and for Hearland as second wave what has to be in place |  |  | HUB (Boarding Gateway Workstream Manager Product/Party Model Actor/PIL Kafka MuleSoft) | • hWP sponsor bank is Citizens • Focused session - what does add location mean for existing customers (e.g., are there 2 locations for reconciliation and single out?) + Define transitionary period of time for which that experience needs to exist • We need new commission structure (first step) | • Genius R+S (h-GP US), Value Drop 1.0 (Oct '26) - (hGP rails: TransIT/Portico, Sierra/Exchange, TMAS/Passport)
| CPQ |  | Salesforce CPQ and ATLAS Oracle CPQ (hWP) | Build - RCA for hPOS + Atlas in iNASA Build - RCA for CAN in ISI (Jan '27 requirement) | Oracle CPQ (hWP) RCA | Build - RCA for CAN in iNASA Build - RCA for l-WP NA in iNASA | RCA |  | • Genius N+R (h-WP US), Value Drop 2 (Timing: TBD), Device: Moby 5500 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision
| Experience |  | Horizon (self-serve) Argo (dealer UI) Kirby Heartland Partner Portal Launchpad (hWP) | Build — Begin convergence of Kirby/Horizon to Ignition | Horizon / Kirby Launchpad (hWP) | Migrate - Heartland Partner Portal to Ignition (dependency on completion of iNASA migration for hPOS) | Ignition |  | • Genius N+R (h-WP US), Value Drop 3 (Timing: TBD), Device: GP1 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision, certification
| Underwriting |  | UCM | Migrate off FICO (Atlas and hPOS are the predominant CRMs for which we need to solve to allow dealers to come in through hWP rails) | UCM |  | UCM |  | • Genius N+R+S (hGP & h-WP Canada), Value Drop 5 (Timing: TBD), Single-In target state, Device GP-1, enables GP1 Handled, GC26, & Kiosk for Genius N, R, S in Canada, dependencies processing rails unknown, Pin on Glass with SCR, Offline PIN
3 · Payment processing | Gateways |  | Portico, Sterling, SNAP, TransIT, TXP (being decommed) CNP - Portico (predominant), GP eComm (minority) | Supporting payments API for h2h integrations through supercheckout ASSESS - feature assessments for net new dealers (e.g. P2P) BUILD Global Gateway->Raft/Core BUILD Hooks into boarding Complete Omnitoken support/GP Vault | Portico / Express? | Interim frontbook to Express; target decom migration and thinning to Global Gateway | Global Gateway | • Follow up with Matt L. to confirm the definition of direct • Confirm how many merchants are on SNAP Sterling • To be deployed in public cloud in the US • Accelerate work to create more seamless migration pathways • Work toward the standards as they are published, and continue in parallel • Portico, transit next state activities TBD | • CRM Go-Forward needed for sales acceleration, pipeline
| APMs | [5 empty] | TBD |  | • Seamelss onboarding
| Switch |  |  | Remapping legacy protocols ensuring they don’t hang directly to host and come through GG |  |  | Supercheckout |  | • Portal to elevate customer experiences
| Acquiring / Funding |  | Exchange, Exchange light, NWS | Build — complete CORE capability gaps required for TMAS migration Build - Transaction-level scheme fee calculations (supporting Surcharge model) |  |  | CORE / RAFT | • Confirm the residual merchants on GSAP and GMAS for SMB in the US and on NGTrans
| Settlement |  | Passport, TMAS | Ability to support payouts for sales commission ASSESS - feature parity on hWP platform |  |  |  | • Confirm how many merchants are on TMAS • Different BIN sponsors across hWP (Citizens, Fifth Third) and hGP (Wells Fargo, Deutsche, PNC, and others); account for new sales coming through for existing customers • Passport has a same-day batch close that must be preserved
| Transaction monitoring |  |  | TBC |  |  |  |  | Deliver VAS solutions
4 · Sales and servicing | CRM |  | Atlas (hGP), OMS, SF USI, SF hPOS | BUILD - hPOS CRM (for back-book) to enable frontbook direct US in iNASA BUILD - Begin iNASA gap closure / convergence to support OMS, USI use cases BUILD - Integration from iNASA to new UBA or new boarding TAM for hPOS | iNASA ISI | BUILD - l-GP CAN for iNASA BUILD - l-WP boarding integration to new boarding TAM | iNASA | • Follow up on how vertical markets are boarded, for example school solutions | • VAS Terminal (Fee-Assist) - Swipe Simple
| Servicing |  | Servicing site, SF USI, hWP Pulse | ASSESS - iNASA to identify gaps - retention, servicing tools, telephony Move to Genesys |  |  | iNASA |  | • VAS Lending - E2E MCA Digital Experience (Pilot, followed by GA)
5 · VAS | Routing |  | RTR (hGP), PRIME/Dynamic Routing (hWP) | EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning | RTR (hGP), PRIME/Dynamic Routing (hWP) |  | Dynamic Routing 2.0 |  | • VAS Como Integrated experience
| Gifts |  | hWP Premier, hWP Valutec, hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Premier, Valutec, Engage | Migrate - Premier to Engage | Engage, Valutec | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration | • Deliver FraudSight via Portico, TransIT
| Loyalty |  | (none in hWP stack) | Build — integrate COMO |  |  | COMO |  | • GP Developer Portal Tools: RevenueBoost, FraudSight, BigCommerce
| Payment tokens | [5 empty] | Unified credential vault | • Support token migration as part of migration planning First mover decision | • VAS Lending & Genius S Integration
| Managed Optimization (incl. nw payment tokens) |  | Revenue Boost | Build — Revenue Boost 2.0; standardize to single-in standards |  |  | Revenue Boost 2.0 |  | • GP Enable Receipt reprint capability in Semi-Integrated & Hooks for Gift & Loyalty
| DCC |  |  | ASSESS - DCC integration to Genius |  |  | Target-state DCC (FX + BIN lookup)
| 3DS |  | 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | FraudSight (via Portico, TransIT) | Build — deliver FraudSight via Portico, TransIT BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  | VAP using Scheme settlement rates | TBD requirements for multi-currency pricing/settlement on Core to support VAP thinning |  |  | hWP FX
| Risk / compliance | [5 empty] | TBD
| Cred management |  | Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API | Access tokens | Unified credential vault
6 · Single-out | Portals |  | MyAccount | Build — MyAccount Genius Portal SSO Build — unified identity (GSI + Azure B2C) BUILD - Genius BO iQ integration |  |  | MyAccount 2.0 | • Follow up on communications
| Reporting |  | Infocentral | ASSESS - New merchant servicing support impeding reconsiliation (making txn fee available via iQ - currently only avlb for interchange) Converge infocentral and iQ as reporting focused capability ASSESS - internal and external reporting need convergence | SMB2.0 |  | hGP SMB / Partner reporting platform SFG (for file delivery)
| Billing |  | Core | Build (On Core billing) - Support hGP products in pricing and billing - Transaction level fee calcs for all daily fees - Daily Net Settlement (support surcharging) - Statement /Invoice changes Design and Build - NAP B&F: Kick off PoC for NA Billing |  |  | CORE+, NAP B&F
| Disputes |  | DiMS, WDP | Build — enhance WDP capabilities; complete in-flight DiMS initiatives |  |  | WDP (to be renamed) | • Bulk upload of disputes data, similar to the approach used for the hWP disputes to WDP move
| Payouts |  |  | BUILD - support payouts/wallets for sales comms |  |  | hWP WPAP
| Funding |  |  | BUILD - support payouts/wallets for sales comms |  |  | hWP WPAP
| Residuals | [5 empty] | hWP EPI solution
7 · Data | MDM (Master Data) |  |  | ASSESS - New merchant servicing support impeding reconsiliation |  |  | Reltio (MDM)
| Real-time data | [5 empty] | Resilient real-time ingestion
| Reporting | [5 empty] | Semantic layer
Others
Note on C16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: See Developer Portal above.

## NA Wholesale
Tab title (save and calculate to sync)
|  |  |  | Focus for discussion |  | Not focus for discussion
Boulder | Rock | Proposition / Portfolio | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities
1 · Single in | Global API | Omnichannel | GPAPI (for frontbook), backbook still on Portico/TransIT | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | GPAPI current versions (v1) back book and Global API for front book (v2) | Migrate — merchants onto v2 Decomm — v1 (later) | Global API
| PayApps |  | HGP/hWP OEM/3rd party, UPA | Build — Close feature gaps for Nucleus to NA Migrate — migrate UPA to Nucleus Migrate — OEM/3rd party to Nucleus | UPA, OEM/3rd party apps
| MDM/TMS |  | OEM, in-house | Build — TAM deplpyment-as-a-service (DaaS) platform (Scalefusion) Migrate — OEM/3rd party to DaaS | OEM, in-house TMS platforms
| Developer Portal | Omnichannel | hGP Developer Portal hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migreate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | SDKs - connected to TransIT - connected to GP-API | Build - Connect Server-Side SDKs to Global API See also CP / Genius S & N below | SDKs - connected to TransIT - connected to GP-API | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | Extensions - connected to TransIT - connected to GP-API | Build - Connect Target State Extensions to Global API | Extensions - connected to TransIT - connected to GP-API | Build - Merge Extensions to single instance Migrate - Customers on non-Global API stacks to Global API via Extensions Decomm - Non-Global API Extensions |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
Unified Prop
| Hosted Solutions |  |  | Build — conform HPP to global API standard Build — enable hWP HPP on GPAPI Design — Components SDK on GAPI Align — PBL engine
| CP / Genius S |  |  | Build — Underway for building for Genius S |  |  | TriPOS / Nucleus Combined solution |  | • Genius S (core goals) - Accelerate Core North America Growth, Improve Merchant Experience (onboarding key), Expand Selectively in Strategic Markets (UK&I, Erste JV support, BOP (Mobile Only)) | • Separation project (TMAS / GMAS) to CORE, first priority GMAS then TMAS
| CP / Genius N | [5 empty] | TriPOS / Nucleus Combined solution |  | • Genius S (Execution Priorities): Launch Genius S into Worldpay FI Channel (Q3), MyAccount Genius Portal SSO, Merchant Onboarding & E2E Experience, resolve bugs with GP SDK | • GNAP to GSAP NA (ACI Consolidation project)
| CNP |  | TransIT | BUILD - Protocols for GG BUILD - API 2.0 to Express | API 2.0 to Express | Decomm - Converge to global gateway | Unified Global API |  | • Genius N Value Drop 1.1 (Jan '27) - US (hGP rails: Merchantware, GSAP/Sierra, GMAS) - enables existing Genius N first-party payment front-book via Merchantware, existing Stadia & Enterprise QSR (7Brew, CKE, etc)
| Hosted | [5 empty] | TBD |  | dependencies: GP API + GPSDK boarding, TAPI, SDK integration?
2 · Boarding | Orchestration |  | OnTrak Express/MMS MEA MAP Launchpad Orchestration (hWP) |  |  |  | Boarding gateway Workstream Manager Kafka MuleSoft | MAP orchestrates for Central Station OnTrak orchestrates for ELAPP/ Base | • Genius R+S (h-GP US), Value Drop 1.0 (Oct '26) - (hGP rails: TransIT/Portico, Sierra/Exchange, TMAS/Passport)
| CPQ |  | ELAPP Base Central Station MEA Oracle CPQ (hWP) | (Continue Oracle CPQ for Launchpad hWP) | Oracle CPQ (hWP) | Build - RCA for l-WP partners Build - RCA for l-GP partners | RCA | Pricing tool built into ELAPP, Base, Central Station, MEA | • Genius N+R (h-WP US), Value Drop 2 (Timing: TBD), Device: Moby 5500 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision
| Experience |  | ELAPP Base MAP (flat file only) Central Station MEA MerchantFlo Launchpad (hWP) | Migrate - Migration underway from ELAPP to Base Build - Genius for ISO Launchpad (hWP) Build - Feature parity into Launchpad for Base, MAP, Central Station, MEA, MerchantFlo | Base MAP (flat file only) Central Station MEA MerchantFlo Launchpad (hWP) | Build - Launchpad + Horizon harmonization (Ignition) Build - Ignition to consume RCA Build - Igniton consume Boarding Gateway/TAM boarding orchestration Migrate - Base, MAP, Central Station, MEA, MerchantFlo | Ignition | Does not replace OnTrak (servicing) Assumes Boarding Gateway connects to Sierra/TMAS - or - Sierra/TMAS demised - How long does it take for a new integration on Launchpad (e.g., to Sierra/TMAS) and how does that compare to effort needed to close feature gap to target | • Genius N+R (h-WP US), Value Drop 3 (Timing: TBD), Device: GP1 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision, certification
| Underwriting |  | UCM MAP Central Station FICO (hWP) | BUILD - FICO to UCM integration for Genius | UCM (all net new) | Build - Launchpad to integrate to UCM | UCM | Put MAP and Central Station on Launchpad first, then connect to UCM there (not earlier) | • Genius N+R+S (hGP & h-WP Canada), Value Drop 5 (Timing: TBD), Single-In target state, Device GP-1, enables GP1 Handled, GC26, & Kiosk for Genius N, R, S in Canada, dependencies processing rails unknown, Pin on Glass with SCR, Offline PIN
3 · Payment processing | Gateways |  | TransIT | Supporting payments API for h2h integrations through supercheckout ASSESS - feature assessments for net new dealers (e.g. P2P) BUILD Global Gateway->Raft/Core BUILD Hooks into boarding Complete Omnitoken support/GP Vault | TransIT |  | Global Gateway | TBD - how to move transit overtime (similar q to direct) | • CRM Go-Forward needed for sales acceleration, pipeline
| APMs | [5 empty] | TBD |  | • Seamelss onboarding
| Switch | [5 empty] | Supercheckout |  | • Portal to elevate customer experiences
| Acquiring / Funding |  | Sierra/TMAS | Build — complete CORE / RAFT capability gaps for L-TSYS migration |  |  | CORE / RAFT
| Transaction monitoring | [7 empty] | Deliver VAS solutions
4 · Sales and servicing | CRM |  | OnTrak MAP Central Station iNASA (hWP) | Build — CRM go-forward for partner managment for partners Build — integrate Genius into iNASA | iNASA + some of those to the left, need to determin plan | Cont. Build — CRM go-forward for Merchant source of truth + Partnership managment | iNASA | Is the plan to move all of these over to Salesforce? | • VAS Terminal (Fee-Assist) - Swipe Simple
| Servicing |  | OnTrak MAP Central Station iNASA (hWP) | ASSESS - Central station, OnTrack, MAP svc to converge with tgt state svc |  |  | iNASA | Is the plan to move all of these over to Salesforce? - Base can cover svc by Mid '27 (but this work is currently paused) - Should we continue getting svc to BASE vs. building directly to tgt state svc. - Need persp. By July end (exam question - what are the things you need to move over to iNASA) | • VAS Lending - E2E MCA Digital Experience (Pilot, followed by GA)
5 · VAS | Routing |  | RTR (hGP), PRIME/Dynamic Routing (hWP) | EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning | RTR (hGP), PRIME/Dynamic Routing (hWP) |  | Dynamic Routing 2.0 |  | • VAS Como Integrated experience
| Gifts | hWP Premier, hWP Valutec, hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Premier, Valutec, Engage | Migrate - Premier to Engage | Engage, Valutec | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration |  | • Deliver FraudSight via Portico, TransIT
| Loyalty |  | (none in hWP stack) | Build — integrate COMO |  |  | COMO |  | • GP Developer Portal Tools: RevenueBoost, FraudSight, BigCommerce
| Payment tokens |  | See Credential Management | See Credential Management | See Credential Management |  | Unified credential vault |  | • VAS Lending & Genius S Integration
| Managed Optimization (incl. nw payment tokens) |  | Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 Build — Revenue Boost 2.0; standardize to single-in standards | Revenue Boost Microservice |  | Revenue Boost 2.0 |  | • GP Enable Receipt reprint capability in Semi-Integrated & Hooks for Gift & Loyalty
| DCC | [5 empty] | Target-state DCC (FX + BIN lookup)
| 3DS |  | 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  | VAP using Scheme settlement rates | TBD requirements for multi-currency pricing/settlement on Core to support VAP thinning |  |  | hWP FX
| Risk / compliance | [5 empty] | TBD
| Cred management |  | Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API | Access tokens | Unified credential vault
6 · Single-out | Portals |  | Translink Central Station Web Portal myAccount (for MAP) iQ (hWP) | Build — MyAccount Genius Portal SSO Build — unified identity (GSI + Azure B2C) |  |  | MyAccount 2.0
| Reporting |  | Translink Central Station Web Portal myAccount (for MAP) iQ (hWP) |  |  |  | hGP SMB / Partner reporting platform SFG (for file delivery)
| Billing |  | TMAS |  |  |  | CORE+
| Disputes |  | DiMS, WDP, Merlin | Build — enhance WDP capabilities; complete in-flight DiMS initiatives (including Merlin migration to DiMs) ASSESS - Can dev be stopped on non starget platform based on move to new rails (reduce throwaway work) ASSESS - plan for CB Help |  |  | Global Disputes Platform (based on WDP) | - CB Help vs GDS feature gaps - GDS can never process non-acquired traffic - Ravelin and CB Help have overlapping features (open question)
| Payouts |  |  | BUILD - support payouts/wallets |  |  | hWP WPAP
| Funding |  | TMAS | BUILD - support payouts/wallets |  |  | hWP WPAP
| Residuals |  | Base Central Station residuals MEA residuals (?) EPPE (hWP) | BUILD - Close gaps on EPPE vs. BASE, MEA, Central Station (review and align rev share reqs) |  |  | hWP EPI solution | Has analysis of Base Residuals vs hWP residuals solution been done? - Raji has workshops scheduled Exam question - whats the path to get from express to base to EPPE / iNASA / Launchpad
7 · Data | MDM (Master Data) | [5 empty] | Reltio (MDM)
| Real-time data | [5 empty] | Resilient real-time ingestion
| Reporting | [5 empty] | Semantic layer
Others

## NA Indirect
Tab title (save and calculate to sync)
|  | First Movers (cross portfolio) |  | Focus for discussion |  | Not focus for discussion
What are we doing, whats the sequence, detailed (now migrations + new builds)
Boulder | Rock | Proposition / Portfolio | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities
1 · Single in | Global API | Omnichannel | GPAPI (for frontbook), backbook still on Portico/TransIT | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | GPAPI current versions (v1) back book and Global API for front book (v2) | Migrate — merchants onto v2 Decomm — v1 (later) | Global API
| PayApps |  | HGP/hWP OEM/3rd party, UPA | Build — Close feature gaps for Nucleus to NA Migrate — migrate UPA to Nucleus Migrate — OEM/3rd party to Nucleus | UPA, OEM/3rd party apps
| MDM/TMS |  | OEM, in-house | Build — TAM deplpyment-as-a-service (DaaS) platform (Scalefusion) Migrate — OEM/3rd party to DaaS | OEM, in-house TMS platforms
| Developer Portal | Omnichannel | [5 empty] | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | [5 empty] | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | [5 empty] | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
Unified Prop
| Hosted Solutions |  |  | Build — conform HPP to global API standard Build — enable hWP HPP on GPAPI Design — Components SDK on GAPI Align — PBL engine
| CP / Genius S | [5 empty] | TriPOS / Nucleus Combined solution |  | • Genius S (core goals) - Accelerate Core North America Growth, Improve Merchant Experience (onboarding key), Expand Selectively in Strategic Markets (UK&I, Erste JV support, BOP (Mobile Only)) | • Separation project (TMAS / GMAS) to CORE, first priority GMAS then TMAS
| CP / Genius N | [5 empty] | TriPOS / Nucleus Combined solution |  | • Genius S (Execution Priorities): Launch Genius S into Worldpay FI Channel (Q3), MyAccount Genius Portal SSO, Merchant Onboarding & E2E Experience, resolve bugs with GP SDK | • GNAP to GSAP NA (ACI Consolidation project)
| CNP | [5 empty] | Unified Global API |  | • Genius N Value Drop 1.1 (Jan '27) - US (hGP rails: Merchantware, GSAP/Sierra, GMAS) - enables existing Genius N first-party payment front-book via Merchantware, existing Stadia & Enterprise QSR (7Brew, CKE, etc)
| Hosted | [5 empty] | TBD |  | dependencies: GP API + GPSDK boarding, TAPI, SDK integration?
2 · Boarding | Orchestration |  | Express (uses MMS) |  | Express (uses MMS) |  | Boarding gateway Workstream Manager Kafka MuleSoft | What is the long term plan for Express? We should also look at consolidating MMS into Express. | • Genius R+S (h-GP US), Value Drop 1.0 (Oct '26) - (hGP rails: TransIT/Portico, Sierra/Exchange, TMAS/Passport)
| CPQ |  | Portfolio Pricing Manager (PPM) Jarvis |  | Portfolio Pricing Manager (PPM) Jarvis | Build - RCA for Indirect partners | RCA |  | • Genius N+R (h-WP US), Value Drop 2 (Timing: TBD), Device: Moby 5500 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision
| Experience |  | Express MMS Jarvis Launchpad (hWP) | Build - Genius for ISO Launchpad (hWP) Build - Feature parity into Launchpad for Express, MMS | Express MMS Jarvis Launchpad (hWP) | Build - Launchpad + Horizon = Ignition harmonization Build - Igniton consume Boarding Gateway/TAM boarding orchestration Migrate - Express, MMS | Ignition | Express and MMS are listed separately due to 2 Uis | • Genius N+R (h-WP US), Value Drop 3 (Timing: TBD), Device: GP1 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision, certification
| Underwriting |  | UCM can be licensed to partner Jarvis |  |  |  | NA (partners own their own UW) |  | • Genius N+R+S (hGP & h-WP Canada), Value Drop 5 (Timing: TBD), Single-In target state, Device GP-1, enables GP1 Handled, GC26, & Kiosk for Genius N, R, S in Canada, dependencies processing rails unknown, Pin on Glass with SCR, Offline PIN
3 · Payment processing | Gateways |  |  | Supporting payments API for h2h integrations through supercheckout ASSESS - feature assessments for net new dealers (e.g. P2P) BUILD Global Gateway->Raft/Core BUILD Hooks into boarding Complete Omnitoken support/GP Vault |  |  | Global Gateway | Whats the plan for 2+ year horizons | • CRM Go-Forward needed for sales acceleration, pipeline
| APMs | [5 empty] | TBD |  | • Seamelss onboarding
| Switch | [5 empty] | Supercheckout |  | • Portal to elevate customer experiences
| Acquiring / Funding |  | L-TSYS | Build — complete CORE / RAFT capability gaps for L-TSYS migration |  |  | CORE / RAFT | Decide on merchant migration First mover activity - removing d2h integrations
| Transaction monitoring | [7 empty] | Deliver VAS solutions
4 · Sales and servicing | CRM |  | CBOS (Comprehensive Back Office Solution) Jarvis | Build — CRM go-forward for partner managment for partners Build — integrate Genius into iNASA | iNASA | Cont. Build — CRM go-forward for Merchant source of truth + Partnership managment | iNASA | Tenative if this will be year 1 for l-GP Partners, based on other sequencing | • VAS Terminal (Fee-Assist) - Swipe Simple
| Servicing |  | CBOS (Comprehensive Back Office Solution) Jarvis |  |  |  | iNASA |  | • VAS Lending - E2E MCA Digital Experience (Pilot, followed by GA)
5 · VAS | Routing |  | RTR (hGP), PRIME/Dynamic Routing (hWP) | EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning | RTR (hGP), PRIME/Dynamic Routing (hWP) |  | Dynamic Routing 2.0 |  | • VAS Como Integrated experience
| Gifts |  | hWP Premier, hWP Valutec, hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Premier, Valutec, Engage | Migrate - Premier to Engage | Engage, Valutec | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration | • Deliver FraudSight via Portico, TransIT
| Loyalty |  | (none in hWP stack) | Build — integrate COMO |  |  | COMO |  | • GP Developer Portal Tools: RevenueBoost, FraudSight, BigCommerce
| Payment tokens |  | See Credential Management | See Credential Management | See Credential Management |  | Unified credential vault |  | • VAS Lending & Genius S Integration
| Managed Optimization (incl. nw payment tokens) |  | Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 Build — Revenue Boost 2.0; standardize to single-in standards | Revenue Boost Microservice |  | Revenue Boost 2.0 |  | • GP Enable Receipt reprint capability in Semi-Integrated & Hooks for Gift & Loyalty
| DCC | [5 empty] | Target-state DCC (FX + BIN lookup)
| 3DS |  | 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  | VAP using Scheme settlement rates | TBD requirements for multi-currency pricing/settlement on Core to support VAP thinning |  |  | hWP FX
| Risk / compliance |  | CBOS Risk 3.0 can be licensed to partner Jarvis |  |  |  | TBD
| Cred management |  | Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API | Access tokens | Unified credential vault
6 · Single-out | Portals |  | CBOS (Comprehensive Back Office Solution) eConnections TransLink Jarvis | Build — MyAccount Genius Portal SSO Build — unified identity (GSI + Azure B2C) | CBOS, eConnections |  | MyAccount 2.0
| Reporting |  | CBOS (Comprehensive Back Office Solution) Jarvis |  |  |  | hGP SMB / Partner reporting platform SFG (for file delivery)
| Billing | [5 empty] | CORE+
| Disputes |  | DiMS, WDP | Build — enhance WDP capabilities; complete in-flight DiMS initiatives |  |  | WDP (to be renamed)
| Payouts |  |  | BUILD - support payouts/wallets |  |  | hWP WPAP
| Funding |  |  | BUILD - support payouts/wallets |  |  | hWP WPAP
| Residuals |  | PPM/Relationship Profitability can be licensed to partner |  |  |  | hWP EPI solution
7 · Data | MDM (Master Data) | [5 empty] | Reltio (MDM)
| Real-time data | [5 empty] | Resilient real-time ingestion
| Reporting | [5 empty] | Semantic layer
| Others | [6 empty] | Data from boarding systems already in hGP datalake
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm if required.
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm if required.
Note on C11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm if required.

## NA ISO
Tab title (save and calculate to sync)
|  |  |  | Focus for discussion |  | Not focus for discussion
Boulder | Rock | Proposition / Portfolio | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities
1 · Single in | Global API | Omnichannel | GPAPI (for frontbook), backbook still on Portico/TransIT | Build — Build OAuth Authentication for Global API Build — publish global API standards; adhere gateways Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | GPAPI current versions (v1) back book and Global API for front book (v2) | Migrate — merchants onto v2 Decomm — v1 (later) | Global API
| PayApps |  | HGP/hWP OEM/3rd party, UPA | Build — Close feature gaps for Nucleus to NA Migrate — migrate UPA to Nucleus Migrate — OEM/3rd party to Nucleus | UPA, OEM/3rd party apps
| MDM/TMS |  | OEM, in-house | Build — TAM deplpyment-as-a-service (DaaS) platform (Scalefusion) Migrate — OEM/3rd party to DaaS | OEM, in-house TMS platforms
| Developer Portal | Omnichannel | hGP Developer Portal hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migreate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | SDKs - connected to TransIT - connected to GP-API | Build - Connect Server-Side SDKs to Global API See also CP / Genius S & N below | SDKs - connected to TransIT - connected to GP-API | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | Extensions - connected to TransIT - connected to GP-API | Build - Connect Target State Extensions to Global API | Extensions - connected to TransIT - connected to GP-API | Build - Merge Extensions to single instance Migrate - Customers on non-Global API stacks to Global API via Extensions Decomm - Non-Global API Extensions |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
Unified Prop
| Hosted Solutions |  |  | Build — conform HPP to global API standard Build — enable hWP HPP on GPAPI Design — Components SDK on GAPI Align — PBL engine
| CP / Genius S | [5 empty] | TriPOS / Nucleus Combined solution |  | • Genius S (core goals) - Accelerate Core North America Growth, Improve Merchant Experience (onboarding key), Expand Selectively in Strategic Markets (UK&I, Erste JV support, BOP (Mobile Only)) | • Separation project (TMAS / GMAS) to CORE, first priority GMAS then TMAS
| CP / Genius N |  | Merchantware, GSAP / Sierra, GMAS (hGP) | Build — Genius N first-party front-book via Merchantware (Value Drop 1.1, Jan '27) |  |  | TriPOS / Nucleus Combined solution |  | • Genius S (Execution Priorities): Launch Genius S into Worldpay FI Channel (Q3), MyAccount Genius Portal SSO, Merchant Onboarding & E2E Experience, resolve bugs with GP SDK | • GNAP to GSAP NA (ACI Consolidation project)
| CNP | [5 empty] | Unified Global API |  | • Genius N Value Drop 1.1 (Jan '27) - US (hGP rails: Merchantware, GSAP/Sierra, GMAS) - enables existing Genius N first-party payment front-book via Merchantware, existing Stadia & Enterprise QSR (7Brew, CKE, etc)
| Hosted | [5 empty] | TBD |  | dependencies: GP API + GPSDK boarding, TAPI, SDK integration?
2 · Boarding | Orchestration | [7 empty] | • Genius R+S (h-GP US), Value Drop 1.0 (Oct '26) - (hGP rails: TransIT/Portico, Sierra/Exchange, TMAS/Passport)
| CPQ | [7 empty] | • Genius N+R (h-WP US), Value Drop 2 (Timing: TBD), Device: Moby 5500 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision
| Experience | [7 empty] | • Genius N+R (h-WP US), Value Drop 3 (Timing: TBD), Device: GP1 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision, certification
| Underwriting |  | UCM/FICO | Migrate - FICO data to UCM Decom - FICO | FICO/UCM |  |  | Dependent on budget approval to move forward. We have submitted a budget of $2.6M for 2.5 years work to complete gap build out, data migration & decom of FICO | • Genius N+R+S (hGP & h-WP Canada), Value Drop 5 (Timing: TBD), Single-In target state, Device GP-1, enables GP1 Handled, GC26, & Kiosk for Genius N, R, S in Canada, dependencies processing rails unknown, Pin on Glass with SCR, Offline PIN
3 · Payment processing | Gateways |  | Merchantware, TransIT | Build — develop Global Gateway for North America | Express | Decomm to Global Gateway | Global Gateway |  | • CRM Go-Forward needed for sales acceleration, pipeline
| APMs | [5 empty] | TBD |  | • Seamelss onboarding
| Switch | [5 empty] | Supercheckout |  | • Portal to elevate customer experiences
| Acquiring / Funding |  | GMAS, GSAP / Sierra, Merchantware | Build — complete CORE capability gaps for GMAS migration Build — GNAP → GSAP NA enablement (ACI consolidation) |  |  | CORE / RAFT
| Transaction monitoring | [7 empty] | Deliver VAS solutions
4 · Sales and servicing | CRM | [5 empty] | iNASA, ISI |  | • VAS Terminal (Fee-Assist) - Swipe Simple
| Servicing |  | MAP, Central Station (hGP) |  |  |  | iNASA |  | • VAS Lending - E2E MCA Digital Experience (Pilot, followed by GA)
5 · VAS | Routing |  | RTR (hGP), PRIME/Dynamic Routing (hWP) | EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning | RTR (hGP), PRIME/Dynamic Routing (hWP) |  | Dynamic Routing 2.0 |  | • VAS Como Integrated experience
| Gifts |  | hWP Premier, hWP Valutec, hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Premier, Valutec, Engage | Migrate - Premier to Engage | Engage, Valutec | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration | • Deliver FraudSight via Portico, TransIT
| Loyalty |  | (none in hWP stack) | Build — integrate COMO |  |  | COMO |  | • GP Developer Portal Tools: RevenueBoost, FraudSight, BigCommerce
| Payment tokens |  | See Credential Management | See Credential Management | See Credential Management |  | Unified credential vault |  | • VAS Lending & Genius S Integration
| Managed Optimization (incl. nw payment tokens) |  | Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 Build — Revenue Boost 2.0; standardize to single-in standards | Revenue Boost Microservice |  | Revenue Boost 2.0 |  | • GP Enable Receipt reprint capability in Semi-Integrated & Hooks for Gift & Loyalty
| DCC | [5 empty] | Target-state DCC (FX + BIN lookup)
| 3DS |  | 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  | VAP using Scheme settlement rates | TBD requirements for multi-currency pricing/settlement on Core to support VAP thinning |  |  | hWP FX
| Risk / compliance | [5 empty] | TBD
| Cred management |  | Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API | Access tokens | Unified credential vault
6 · Single-out | Portals |  | MyAccount + hWP | Build — MyAccount Genius Portal SSO Build — unified identity (GSI + Azure B2C) |  |  | MyAccount 2.0
| Reporting | [5 empty] | hGP SMB / Partner reporting platform SFG (for file delivery)
| Billing | Fee Assist |  |  |  |  | CORE+
| Disputes |  | DiMS, WDP | Build — enhance WDP capabilities; complete in-flight DiMS initiatives |  |  | WDP (to be renamed)
| Payouts |  |  | BUILD - support payouts/wallets |  |  | hWP WPAP
| Funding |  |  | BUILD - support payouts/wallets |  |  | hWP WPAP
| Residuals | [5 empty] | hWP EPI solution
7 · Data | MDM (Master Data) | [5 empty] | Reltio (MDM)
| Real-time data | [5 empty] | Resilient real-time ingestion
| Reporting | [5 empty] | Semantic layer
Others

## RoW>>
Corporate priorities | Consolidated Dependencies
1 · Single in | CNP / Global API Finalize API 2.0 standards for GPAPI and align them with the GPECom → Global Gateway convergence path. Confirm GPECom feature parity by market before moving off MPGS / CyberSource, especially for local APMs, installments, recurring payments, and localized checkout needs. Secure NAP acquiring licenses / market coverage for AP priority markets, starting with Hong Kong, then Philippines, Macau, and Malaysia. Align with onboarding so AP can move from manual onboarding to automated flows before scaling CNP migration. Confirm where GPECom uses underlying third-party services today and which services need to become reusable microservices behind the API. CP / Payment apps Complete Genius S localization for AP markets, including BOIPA / Philippines and Hong Kong / Macau. Confirm Nucleus + TMS readiness before moving merchants off local payment-app and device-management stacks. Integrate MBS with TMS for payment-app and remote terminal management. Align CP migration with iNASA / boarding amendments, pricing configuration, and merchant hierarchy setup. Preserve country-specific requirements — e.g., JV rules in the Philippines, fiscalization in Greece / CEE, and local routing rules in Europe — before scaling the Nucleus path.
2 · Boarding | Complete Salesforce International → MBS / OmniTracker integration for AP self-serve, with Salesforce as the experience layer and MBS as the activation / orchestration layer. Resolve AP product, product-pricing, and merchant-hierarchy design before scaling onboarding or NAP migration. Extend Salesforce beyond lead management for Greece / Poland, including full sales pipeline, product, and pricing data needed for end-to-end onboarding.
3 · Payment processing | Secure NAP acquiring licenses / market coverage before moving AP markets at scale, starting with Hong Kong, then Philippines, Macau, and Malaysia. Resolve IPP on NAP, especially for Hong Kong where IPP represents roughly 30%+ of revenue and cannot be assumed in the Heritage Worldpay stack. Align with CyberSource / Visa globally, including the Rob Ward / UK CyberSource-to-target-rails pattern, so AP does not solve CyberSource exit in isolation. Decide DCC target path: AP currently uses Planet; moving DCC into the EU solution may require backward compatibility to Planet if support needs to continue longer. Account for Europe routing / bilat rules and on-us JV routing, especially in Poland / Europe, so target processing preserves cost-effective routing advantages.
4 · Sales and servicing | Confirm the RoW Salesforce operating model across Poland, Greece, AP, and other markets before migrating market CRMs. Align CRM changes with Boarding, since Salesforce International → MBS / OmniTracker is the key path for AP self-serve and sales-assisted onboarding. Ensure product and pricing data are available in Salesforce for Greece / Poland before end-to-end sales and onboarding can work. Define the servicing target before moving off CBD / ECBD / Hermes / Arc Mercury, including telephony and notifications. Align with portal / Single-out on where merchants go for reporting, disputes, reconciliation, and merchant portal / MyAccount during and after migration.
5 · VAS | Confirm Genius S / Nucleus / GPECom readiness before expanding AP VAS; VAS sequencing depends on the payment app and gateway foundations. Resolve Planet global agreement and backward-compatibility scope before moving DCC onto the go-forward stack. Align AP installment / IPP design with NAP, especially for Hong Kong, where IPP is a major revenue dependency. Confirm ownership and timing for APM / Blik-style services behind GPECom / GPADS, since APM capabilities may be one of the quickest reusable VAS wins. Coordinate Poland VAS work with the broader commerce solution strategy — fiscal app, POS app, terminal app, and service pipe — so VAS does not become a standalone add-on.
6 · Single-out | Backend migration to NAP gates full reporting convergence; portal closure should follow backend movement, not precede it. Worldpay Dashboard → My Account Plus / unified shell in UK&I should mature before scaling the same pattern across the rest of Europe. AP Genius S commercialization must define where merchants go for reconciliation, reporting, and disputes after launch. Greece / CEE portal migration depends on mapping eService portal, GPECom / RealControl, Marketplace, and My Account access by merchant type. Billing and reporting design must align with backend platform moves so RoW does not create a temporary reporting layer that gets replaced again.

## RoW (excl. UK&I)
RoW (excl. UK&I)
|  |  |  | Focus for discussion |  | Not focus for discussion |  |  | Pending to discuss Commerce GP Germany (Ami Mehta), CSOP JV in Czech Republic, Hungary (Vaclav Kerka) and Spain - Comercia (Luis Palomero)
Boulder | Rock | Proposition / Portfolio | Current Platforms | Build / Migrate / Decomm (Now) | Interim Platforms (~H2 '27) | Build / Migrate / Decomm (Next) | Target Platforms (~2029) | Notes / Dependencies / Follow-ups | Business priorities | Corporate priorities
1 · Single in | Global API |  | GPAPI, CYbs, MPGS, GPWebPay, EDPS | Build — publish global API standards; adhere gateways Build — Build OAuth Authentication for Global API Build — version APIs to v2.0 + publish (continue v1) Build — connect SDKs to new API std → update plugins | Global API (GPAPI Codebase) - GPeCom | Migrate — merchants onto v2 Decomm "GPAPI" — v1 (later) | Global API |  | Project Frank - Bring Croatia to GP stack
| PayApps/MDM/TMS |  | Nucleus Ingenico GPE Printec SK for Verifone P2C ERSTE JV e-service PayApp (Poland) app pos Novelpay PL EDPS - Greece Mellon - Greece Comercia PayApp PAX AP Verifone AP Spectra AP Castless AP Quest Oceania PayTen & Printec Croatia 7Pay (SoftPOS) Croatia Rubean for CEMA & Malta CCV Germany Genius S mobile (softPOS) in Phillipines - 10/31 (not live yet) -> Fast follow with other countries GP PAY (3rd party in ERSTE) | Build - finish Nucleus/PayApp 2.0 development to cover remaining gaps to replace P2C for PAX and Printec Verifone for ERSTE JV and Ingenico for transport -> Build - Payment app (Nucleus + TMS) for Genius S underway in AP Build - Nucleus/PayApp 2.0 development to replace e-service PayApp for Genius S launch in PL and for e-service replacement for standalone and semi-integrated Build - Nucleus/PayApp 2.0 for Hong-Kong and Macau to be launched in Q1/27 Build - Nucleus/PayApp 2.0 for replacement of EDPS PayApp Build - Nucleus/PayApp 2.0 for Croatia to replace PayTen & Printec solution Build - GP mobile/Yazara to replace 7Pay in Croatia Migrate - Nucleus shim for triPOS (AP) Migrate - Look at convergence between eService and Nucleus, including TMS consolidation (Poland) Migrate - Convergence between GP PAY and Nucleus (ERSTE). 3 markets with gaps (SK, AT, RO) | Build/Migrate - Nucleus/PayApp 2.0 development to replace e-service PayApp for Genius S launch in PL and for e-service replacement for standalone and semi-integrated Build - Nucleus/PayApp 2.0 for all countries Build/Migrate - Nucleus/PayApp 2.0 for replacement of EDPS PayApp Migrate/Decomm - Nucleus/PayApp 2.0 for Croatia to replace PayTen & Printec solution MIgrate/Decomm - GP mobile/Yazara to replace 7Pay in Croatia |  |  |  | Use Nucleus as one and only payment APP - ERSTE JV
| Developer Portal | Omnichannel | hGP Developer Portal hWP Developer Portal | Build - Net new experience (nGP) for front book Migrate - Content from hWP to nGP to support New and Interim Migrate - Customer SSO from hWP (FIS) to GP Azure B2C | hGP Developer Portal (with some migrated hWP content) | Migrate - Customers from hWP & hGP to nGP Decomm - hWP Developer Portal, hGP Developer Portal |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| SDKs | Omnichannel | SDKs - connected to TransIT - connected to GP-API | Build - Connect Server-Side SDKs to Global API See also CP / Genius S & N below | SDKs - connected to TransIT - connected to GP-API | Migrate - Customers on non-Global API stacks to Global API via SDKs Decomm - Non-Global API SDKs |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
| 3rd Party Software Extensions | eComm | Extensions - connected to TransIT - connected to GP-API | Build - Connect Target State Extensions to Global API | Extensions - connected to TransIT - connected to GP-API | Build - Merge Extensions to single instance Migrate - Customers on non-Global API stacks to Global API via Extensions Decomm - Non-Global API Extensions |  | Dependency on what solutions needs to be supported in market; Global API, GP-API, Access, WPG, TriPOS etc.
Unified Prop
| Hosted Solutions |  |  | [Build] conform HPP to global API standard [Build] feature parity on HPP Premium Express to Decomm Legacy HPP and migrate back book [Build] Components SDK session support on Express [Build / Migrate /Decomm] Merge TUI / OEHP functionality and migrate TUI merchants [Align] PBL engine |  |  |  | Follow up - Assess with Rob on Cybersource relation interdependency with hosted experience
| CP / Genius S |  |  | Migrate - Assess if updating vs. swaping terminals |  | Swap existint terminals over time for back-book. Understand pathway of direct integrations (e.g., 3rd party gateways, GSAP). Ensure all integrate with global gateaway switch |  | Genius is the pre-requisite to build VAS on the use case bases | • Genius S (core goals) - Accelerate Core North America Growth, Improve Merchant Experience (onboarding key), Expand Selectively in Strategic Markets (UK&I, Erste JV support, BOP (Mobile Only)) - Genius Mobile (Greece) - September/October will migrate to Genius Mobile. Pending to decide how we will fiscalize in Greece. | • Separation project (TMAS / GMAS) to CORE, first priority GMAS then TMAS
| CP / Genius N | [7 empty] | • Genius S (Execution Priorities): Launch Genius S into Worldpay FI Channel (Q3), MyAccount Genius Portal SSO, Merchant Onboarding & E2E Experience, resolve bugs with GP SDK -> Serve HKG and Phillipines | • GNAP to GSAP NA (ACI Consolidation project)
| CNP |  | GPAPI, CYbs, MPGS, GPWebPay (ERSTE), EDPS | Continue launch in Asia, Croatia, Germany Build boarding support for Access/WPG/Redsys Spain while awaiting GG support TBC on GPAPI launch in Spain for smaller SMBs as well Build - GPWebPAY features to pair GPeCom. Cost challenge for invoicing/billing out features (GPWebPay is cheaper) |  |  | Global API | GPAPI as is will be supported for some time, so launching with it in next 6-9 months is ok Most of volume is CP, 80% volume is in person in ERSTE Follow-up: Richard J, Mark H, Rob W on ACI consolidation plan. How do we solve APM piece and Ecom proposition together? | • Genius N Value Drop 1.1 (Jan '27) - US (hGP rails: Merchantware, GSAP/Sierra, GMAS) - enables existing Genius N first-party payment front-book via Merchantware, existing Stadia & Enterprise QSR (7Brew, CKE, etc) - ECOM is a priority for ERSTE / GAPS today are: Large merchants/Enterprises (move to Adyen), - GPeCom - MPGS (Mastercard) and GPeCom -> There are gaps with mandatory APMs (Greece)
| Hosted | [7 empty] | dependencies: GP API + GPSDK boarding, TAPI, SDK integration?
2 · Boarding | Orchestration |  | MBS - Activation and orchestration; MOSS AP ECBD (Greece) | Migrate - Assess path out of MOSS AP (Review and determine the go-forward product, pricing and merchant hierarchy structure) [Migrate] Determine boarding amendments within iNASA (pricing/merchant hierarchy configurations) to prep for migrations- AP Build - ECBD (eService boarding process) connected to MBS and MBS connect to GPeCom to enable boarding automation (Greece). Sugar CRM into ROW Salesforce enables this |  |  |  | Time to activation Gap between ECBG and MPS (manual add them if we want to board) | • Genius R+S (h-GP US), Value Drop 1.0 (Oct '26) - (hGP rails: TransIT/Portico, Sierra/Exchange, TMAS/Passport)
| CPQ |  | Veloce | Build -RCA for ROW Salesforce | RCA |  | RCA |  | • Genius N+R (h-WP US), Value Drop 2 (Timing: TBD), Device: Moby 5500 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision
| Experience | [6 empty] | [APAC - HKG; PH] Automated expereince (12-14 days -> reduce to 2-3 days) requirement: direct channel; 1 software transaction within 20 minutes (from softPOS perspective). Get micro clients onto softPOS requirement - for: sales channel - straight through processing that's automated (get from 14 days to 2-3 days) | • Genius N+R (h-WP US), Value Drop 3 (Timing: TBD), Device: GP1 - hWP rails (Express, RAFT, Core) - requires GPSDK + TriPOS, unlocks WP backbook & Frontbook sales, CRM alignment required, onboarding decision, certification
| Underwriting |  | UCM | Migrate - FICO to UCM |  |  |  |  | • Genius N+R+S (hGP & h-WP Canada), Value Drop 5 (Timing: TBD), Single-In target state, Device GP-1, enables GP1 Handled, GC26, & Kiosk for Genius N, R, S in Canada, dependencies processing rails unknown, Pin on Glass with SCR, Offline PIN
3 · Payment processing | Gateways |  | GPeCom, CYbs, MPGS (Greece), GPWebPay, EDPS (Greece), SuperCheckout | GPeCom build to support GPAPI launch in AP GPWebPay build to support Croatia Build - MPGS feature parity with GPeCom to enable ecommerce (Greece) | GPeCom | Converge to Global Gateway Migrate - Thin out EDPS and how to migrate to Nucleus. Lot of custom features, challenging for fiscalization (Greece) | Global Gateway | One of biggest constraints is 3rd party gateways in APAC Concentration risk Follow-up - Lucy to discuss with JR. Pending to decide how to serve direct SMB sales (uncouple from integrated). How are we going to support back-book SMB direct sales | • CRM Go-Forward needed for sales acceleration, pipeline
| APMs |  | GPaaS | Continue single out support on NAP for APMs Build - BLIK APM capabilities |  |  |  | [Poland] Follow-up with James Fry - APM is a quick win - we have already contract with BLIK provider and integration with gateway | • Seamelss onboarding - Brik products (migrate in Greece)
| Switch |  | GSAP/GMAS | Supercheckout support for PIN, P2PE, MDM and protocol support for SPDH, P2H and GPISO | Supercheckout | Powerzac (to support e.g. protocol conversion, VAS, etc) GG connected to Powerzac | Powerzac |  | • Portal to elevate customer experiences
| Acquiring / Funding |  | GSAP/GMAS GSAP AP/GMAS AP eService Postillion/ZSFK GPE B24/MMS (ERSTE) TMAS Comercia | Build - Need to build IPP capabilities on hWP core acquiring stack (APAC) NAP support for AP markets LCPs, BINs, Banks, BPI etc Start NAP in Cloud (GPE) and PZaC integration PZac support for GPE scope and start on SAS Migrate - Assess migration of merchants into NAP platform for top 5 priority markets Build - Stand up capabilities of PowerZac as auth host and NAP to enable transition from non-target platforms in ERSTE JVs |  | GMAS and GPE B24 focus first TNAS unlikely to be a priority given GG focus on N America and need for full stack data residency | NAP Comercia | Make sure top 5 (HKG, Phi, Makao, alasya) are built into NAP. Phillipines is a JV market, serving Enterprise requirements.
| Transaction monitoring | [7 empty] | Deliver VAS solutions
4 · Sales and servicing | CRM |  | ROW Salesforce, including AP eziDebit eWay Sugar (Poland) | Continue as is Migrate - Move Sugar CRM into ROW Salesforce (including Greece) | ROW Salesforce eziDebit eWay | Build - ROW Salesforce to support AUS book of business | ROW Salesforce | Any extension needs to be included, e.g., bring Genius into Market + other requirements (e.g., language) | • VAS Terminal (Fee-Assist) - Swipe Simple
| Servicing |  | ECBD, Hermes, Arch Mercury | Build - Assess overall servicing experience and build the plan (Poland) |  |  |  |  | • VAS Lending - E2E MCA Digital Experience (Pilot, followed by GA)
5 · VAS | Routing |  | N/A - None today | EXPLORE - RTR Microservice interoperability with PRIME/Dynamic Routing ML Models for routing BUILD - Acquiring-agnostic Routing Microservice with ML model for routing decisioning |  |  | Dynamic Routing 2.0 | Debit Routing right now is exclusive to NA. Future state is to enable this to interoperate across int’l b-schemes like EFTPOS, JCB, etc (further reason in the need to decouple as a micro service. | • VAS Como Integrated experience
| Gifts |  | hWP Premier, hWP Valutec, hGP Engage | Build / Enable Engage UI for Valutec Build RAFT / CORE Integration for Engage leveraging existing Valutec integration | Premier, Valutec, Engage | Migrate - Premier to Engage | Engage, Valutec [no impact to RoW] | RAFT / CORE intergration on Engage RAFT/CORE engineering capacity to support Engage integration | • Deliver FraudSight via Portico, TransIT
| Loyalty |  | COMO - not yet integrated in ERSTE. Connected only to P2C terminals | BUILD - COMO integration to target (NUCLEUS) |  |  | COMO |  | • GP Developer Portal Tools: RevenueBoost, FraudSight, BigCommerce - Greece wants to start implementation with COMO
| Payment tokens |  | See Credential Management | See Credential Management | See Credential Management | See Credential Management | Unified credential vault | • BAU; accelerate the unified credential vault architecture | • VAS Lending & Genius S Integration
| Managed Optimization (incl. nw payment tokens) |  | Revenue Boost Microservice (WPG, RAFT, VAP, NAP, Access) | EXPLORE - Design and arch. for RB 2.0 | Revenue Boost Microservice |  | Revenue Boost 2.0 |  | • GP Enable Receipt reprint capability in Semi-Integrated & Hooks for Gift & Loyalty
| DCC |  | Planet (APAC) DCC Poland/Greece (Leveraging GPE DCC for PL via Supercheckout today) | BUILD - isolate DCC svc. From WPG Build - EXPLORE - DCC svc. From WPT to Genius |  |  | Target-state DCC (FX + BIN lookup) - Localized DCC | Need to ensure localized DCC meets Planet requirements
| 3DS |  | 3DS Flex Service (Cardinal & Ravelin MPI) | BUILD (Integrate) hGP MPI to hWP 3DS Flex Microservice | 3DS Flex Service (Cardinal & Ravelin MPI) |  | hWP 3DS flex ser-vice (w/ Ravelin)
| Fraud |  | FraudSwitch Microservice (WPG, RAFT, VAP, Express, Access) | BUILD (Integrate) - hGP Gateways to hWP FraudSwitch Microservice (Portico, Edge, TransIT, MWare) | FraudSwitch Microservice |  | FraudSight
| FX |  |  | EXPLORE - Fx pricing prop for hGP customers (GMAS EU, GMAS AP) - per note across 2 traches |  |  | hWP FX
| Risk / compliance | [5 empty] | TBD
| Cred management |  | Credential API (Revenue Boost, Jaywan, EFTPOS, aaS [Meta]) | BUILD (Integrate) - hGP Token Provisioning services to Credential API (NTRS, TaaS) EXPLORE - hGP & hWP Token Vault consolidation (Unified Credential Vault) | Credential API |  | Unified credential vault
6 · Single-out | Portals |  | GPE (ERSTE) eService Portals (Greece) | Migrate - Consider localization of portal Migrate - Help centers (row) Build - MyAccoutn shell and WP dashboard |  |  |  | ROW - outside of UK&I. Dependency on back-end target-state. Sequence until WP dashboard converges into MyAccount ++ framework
| Reporting | [6 empty] | Followe up - Gap analysis to ensure readiness in ERSTE
| Billing |  |  | Build — add support for existing hGP products pricing (integrated with auto boarding) Build — Applying Tax across the hGP Products Build — surface statements / pricing to partners Build — Support billing for in scope JVs Build — include new products into invoices/statements Build — GL accounting for back-office activities Build — partner-branded statements (where applicable) Build — Work required for Instalments (yet to be assessed)
Disputes
| Payouts |  |  | BUILD - support payouts/wallets |  |  | hWP WPAP
| Funding |  |  | BUILD - support payouts/wallets |  |  | hWP WPAP
Residuals
7 · Data | MDM (Master Data)
Real-time data
Reporting
Others