## How to read
TAM 2.0 sequencing pre-work — SMB
June workshop pack: Europe · APAC · Oceania
How to read this workbook:
• This is an SMB-specific view, organised by the three geos — Europe (UK&I, Poland, Greece, Spain, CEE — Erste JV · green tabs), APAC (blue tab) and Oceania (grey tab — left blank pending priorities). Rows are the stack workstreams; square brackets give channel context; columns are the Now / Next / Later horizons.
• Each geo tab opens with the inputs: business priorities and corporate priorities, with the dates by which they must be met.
• The Milestones row (▼) places major proposition-related milestones over the horizon in which they land.
• Each workstream row shows the current-state stack, the target-state stack, and the planned actions across Now (H2 '26 – H1 '27), Next (H2 '27 – H1 '29) and Later (H2 '29+).
• Actions are tagged: [BUILD] target-state build · [MIGRATE] migration or thin-out · [STOP] stop-sell / stop-integration · [EXIT] decommission.
• Square brackets denote channel context where relevant, e.g. [Bank], [ISV], [Payrix].
• Content is scoped to TAM 2.0 — platform-rationalisation actions, not the full BAU roadmap. Where an action enables a stated business priority, the cell says so.
• Data centre consolidation is tracked under the Global Infrastructure & Security workstream.
• Blue text is a working hypothesis for validation. A blank cell is a request for input — not an indication that nothing is planned.
Aggregate priorities (cross-segment, 2026–27) — general context across all segments, included for completeness:
• Standardization and platform unification (POM + TAM).
• Onboarding and activation speed — the core growth bottleneck.
• VAS monetization — lending, payments optimization, settlement.
• Execution discipline — customer commitments and large rollouts.
• Migration off legacy and reduction of fragmentation.
SMB segment priorities:
• 2026 — Fix the core experience and onboarding. Accelerate Genius growth and address localization for international expansion (partner-led self-enrollment + lead funnel). Scale VAS and monetization (bundles: Lending, Fee Assist, Disputes / Fraud / Payments). Reduce attrition (portal + onboarding).
• 2027 — Global platform standardization across partner, merchant and developer. Fully digital SMB lifecycle (self-serve onboarding and servicing; portal-driven SMB). VAS scaling.
Genius S priorities:
• Rest of 2026 — Fix onboarding and scalability. Improve merchant experience. Launch Wholesale onboarding (h-TSYS).
• 2027 — Automate onboarding for US/CA. Expand Genius S as a core SMB growth engine. Increase multi-product attach rate (VAS + software).
Genius Restaurants priorities:
• Under review.

## UK&I
TAM 2.0 sequencing — SMB · UK&I
INPUTS
Business priorities | 1. Genius S UK — decision confirmed; development on NAP target-state rails, Q1 '27 pilot 2. eCommerce expansion — WP eComm Essentials (targeting the POS back-book), Shopify Onsite plugin, payment links & invoicing 3. VAS growth — Everyday Settlement (H2 '26, NAP-acquired merchants), DCC back-book opt-out enablement, MCA in-house (rev c.$35m '27–28), terminal leasing for hGP terminals 4. Bank channels — BOI, Virgin Money/Nationwide, HSBC (Tuza, eComm, Genius Mobile, Dashboard hooks) 5. WP360 — GA into the Irish market Q3 '26; omnichannel hospitality powered by WP eCommerce
Corporate priorities | • BG migration — audit deadline extended to Jul '27; automated migration scripting blocked on infrastructure database capacity • NerPay Ingenico app sunset path (new localised ROI app unlocks next waves) • ACI / Postilion BO exit by 2029 (corporate) • Fragmented hGP/hWP sales tooling & portals — operational inefficiency and disjointed merchant journey
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Genius S UK pilot live Q1 '27 (NAP rails) ▼ WP360 GA Ireland Q3 '26 ▼ Everyday Settlement launch H2 '26 | ▼ BG migration audit deadline Jul '27 ▼ MCA in-house revenue c.$35m '27–28 | ▼ ACI / Postilion BO exit 2029
Single-in | APIs • GP ecom API (legacy) • Access APIs (legacy) Payment apps • UPA • eService app • NerPay Ingenico app (sunset path) • Yazara softPOS (standalone) | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [BUILD] Develop Global API to the GP-API standard — the single UK&I SMB front door, enabling the eCommerce expansion priority • [BUILD] Genius S payment app Phase 1 (GP SDK → triPOS on the hWP stack) — enabling the Genius S UK launch • [STOP] Stop new integrations to GP ecom and Access legacy APIs | • [BUILD] Genius S Phase 2 — Nucleus headless (PayApp 2.0 convergence) • [MIGRATE] Move UPA / eService app traffic to PayApp 2.0 • [MIGRATE] Move back-book API traffic to Global API • [STOP] Stop core-acquiring integrations to legacy payment apps | • [EXIT] Decommission GP ecom and Access APIs • [EXIT] Decommission eService / UPA / Yazara standalone apps once migration completes
Boarding | Boarding tools • hGP referral boarding tools • Tuza (bank) • Legacy BG boarding estate | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM | • [BUILD] Adhere to the boarding API and hWP party model • [BUILD] Single boarding instance for UK&I — supporting Genius S and bank-channel launches • [STOP] Stop-sell hGP referral boarding tools [ISV] | • [BUILD] Ignition capabilities live (Horizon/Kirby + Launchpad converge) • [BUILD] Replace Tuza with a Horizon-based solution [Bank] — enabling the bank-channel priority (BOI, Virgin Money/Nationwide, HSBC) • [MIGRATE] BG back-book migration ahead of the Jul '27 audit deadline | • [MIGRATE] Migrate the boarding back-book to Ignition • [EXIT] Decommission legacy boarding
Sales & Servicing | CRM & servicing • Fragmented hGP/hWP CRM, servicing tools & portals | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction | • [BUILD] Use iNASA at launch while target-state platforms are developed (CRM 2/3 decision pending)
Payment Processing | Gateways • WPG • Inovo • Sterling Back-office • ACI / Postilion BO | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [BUILD] Genius S development on NAP target-state rails (Q1 '27 pilot) • [BUILD] Develop Global Gateway for UK&I — target rails for Genius S and eCommerce growth • [STOP] Stop new integrations to non-target gateways (WPG et al.) | • [MIGRATE] Integrate POS and API flows to Global Gateway, then migrate the back-book • [MIGRATE] Thin out WPG | • [EXIT] Decommission Inovo and Sterling • [EXIT] ACI / Postilion BO exit (2029 — corporate)
VAS | VAS estate • Mixed legacy VAS integrations on legacy gateways | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP | • [BUILD] Deploy Como — loyalty target platform, supporting the VAS growth priority | • [BUILD] VAS orchestration layer (Revenue Boost single API) • [MIGRATE] Integrate VAS to Global Gateway and migrate the front-book | • [MIGRATE] Migrate the VAS back-book • [EXIT] Decommission legacy VAS integrations
Unified Data and AI | Data estate • Fragmented legacy data stores & reporting feeds | Data platforms • Snowflake + Iceberg Master data • MDM | • [BUILD] MDM adherence • [BUILD] Genius AI + Fraudsight proof of concept | • [BUILD] Data platforms and orchestration on Snowflake + Iceberg • [MIGRATE] Move reporting and data feeds to target platforms | • [EXIT] Decommission legacy data stores
Global Infrastructure & Security (incl. data centres) | Infra • Mixed hGP/hWP design systems • Database capacity constraint blocking BG migration tooling | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure) | • [BUILD] WP design-system foundation + Vega visual layer (Genius S UI adherence) • [BUILD] Provision infrastructure / database capacity to unlock automated BG migration tooling
Single-out | Portals • Dashboard • Legacy portals Disputes • Legacy disputes | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending) | • [BUILD] MyAccount 2.0 — portal target-state build, consolidating fragmented hGP/hWP portals | • [MIGRATE] Integrate, then migrate Dashboard and legacy portals to MyAccount++ • [BUILD] Disputes adherence to WDP | • [EXIT] Decommission legacy portals

## Poland
TAM 2.0 sequencing — SMB · Poland
INPUTS
Business priorities | 1. eCommerce — Click2Pay by June for Cashless Programme eligibility (85% of PL eCom sales) plus Visa/MC incentives; GP eCom enhancements (DCC, BLIK LVL0/OneClick, eRaty) 2. Nestpay decommission and migration to GP eCom 3. SMB POS — COMO loyalty integrated with the POS payment app; Xpay all-in-one 4. Cash2card with the eService Pay app (€750k incentive)
Corporate priorities | • PDLC / ownership gaps on eService core platforms (no PM allocation) • Technology capacity — multi-year delays (e.g. pre-auth on host) • GP eCom delivery delays and reprioritisation flip plans
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Click2Pay by Jun '26 (Cashless Programme) ▼ P2C → Nucleus cutover Sep '26 | ▼ Genius S expansion pilot #2 (post-UK)
Single-in | Payment apps • eService payment app (P2C) • PAX AP / ECC estate | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [BUILD] Nucleus replaces the eService payment app — P2C cutover Sep '26 | • [MIGRATE] Migrate the PAX AP / ECC estate to Nucleus | • [EXIT] Decommission the eService legacy payment app once migration completes
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | eCom gateways • Nestpay (legacy) • GP eCom (post-EPG) | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [STOP] Nestpay — stop-sell and stop new integrations (decommission confirmed as a regional priority) | • [BUILD] Genius S expansion pilot #2 on NAP rails (post-UK) • [MIGRATE] Migrate Nestpay merchants to GP eCom — consolidating Polish eCommerce on the target platform | • [EXIT] Decommission Nestpay
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Greece
TAM 2.0 sequencing — SMB · Greece
INPUTS
Business priorities | 1. Close out the Mirage migration (NBG bank systems → eService/Postilion) — completes end of June 2. GP eCom — finalise the plan and sales strategy 3. Fiscalization-led all-in-one market (SoftPOS, PCI POS, pre-auth on NBG Pay tom, 2nd-screen POS on PAX) 4. Genius Mobile — smooth transition from the white-label NBG Pay tom; complete Genius prioritisation analysis for the Greek market
Corporate priorities | • MPGS → GP eCom feature gap — features planned over an 18-month timeline, leaving the platform non-competitive until closed • Greek fiscalization rules (including pre-auth alignment) • Postilion dependency (ACI exit 2029 — corporate)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Mirage migration completes end-Jun '26 | ▼ MPGS feature-gap plan closes (18 months) | ▼ ACI / Postilion BO exit 2029
Single-in | Payment apps • EDPS payment app • NBG Pay tom (white-label) | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [BUILD] Nucleus (+ Genius S) replaces the EDPS payment app — enabling the fiscalization-led all-in-one priority and the Genius Mobile transition | • [MIGRATE] Migrate the EDPS app estate to Nucleus | • [EXIT] Decommission the EDPS payment app
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | eCom gateways • MPGS (exit) Acquiring estate • eService / Postilion | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [STOP] MPGS — stop new integrations (feature-gap plan in flight) | • [MIGRATE] Migrate MPGS merchants to GP eCom — restoring eCommerce competitiveness in market | • [EXIT] Complete the MPGS exit (timing to be confirmed) • [EXIT] ACI / Postilion BO exit (2029 — corporate)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Spain
TAM 2.0 sequencing — SMB · Spain
INPUTS
Business priorities | 1. Bizum scale-out to ~500k terminals (full deployment by 29 June; enterprise activations underway) 2. Multi-acquiring C2.0 — LIDL won, ALDI strategic; 157-opportunity pipeline; multi-merchant per terminal 3. BNPL with CaixaBank — full rollout this quarter; Tink Pay-by-Bank go-live 4. Close the Worldpay/Comercia commercial and product model gap to stop share loss 5. TPV&GO launch (June) — terminals as light EPOS; restaurant, stock and loyalty modules by year-end
Corporate priorities | • No omnichannel product (eCom + face-to-face via a single API) in Spain • Legacy and new stack coexistence — impacting speed and scalability • Carve-out: Model 170, reconciliation files • GP eCom processing/development cost alignment; mid-term GP API & eCom scope
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Bizum full deployment 29 Jun '26 ▼ TPV&GO launch Jun '26 | ▼ GP API live as the Spain eCommerce gateway '27
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API |  | • [BUILD] GP API as the eCommerce gateway for Spain ('27) — closing the omnichannel gap with a single API for eCom and face-to-face
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Acquiring / eCom • UniversalPay (run-down) • miTPV (Comercia) • EPG / Addon2 eComm • TPV&GO | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [MIGRATE] Continue the UniversalPay run-down |  | • [EXIT] Deprecate miTPV (Comercia) • [EXIT] Complete the UniversalPay exit
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## CEE — Erste JV
TAM 2.0 sequencing — SMB · CEE — Erste JV
INPUTS
Business priorities | 1. VAS growth (+70% YoY; 16% of JV revenue) — DCC on SoftPOS (GP TOM) in 4 countries, loyalty, instalments; POS Rating pilot in Romania 2. Genius parity for Central Europe (with the Genius S team); rebranding to Genius in CZ (terminal and app) 3. Croatia expansion — Croatian National Bank regulatory friction; key meeting in June 4. EEA Accessibility Act rollout on payment devices in 4 countries 5. eCommerce — Transaction Risk Analysis launch in 4 countries to improve back-book conversion
Corporate priorities | • eCommerce capacity on GP Webpay versus competitor pace • Croatian National Bank interference with Croatia plans • Genius product gap versus competition in Central Europe — reset plan created by Erste-JV leadership and underway
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Croatia CNB key meeting Jun '26 ▼ EEA Accessibility Act rollout | ▼ CZ Genius rebrand (timing to be confirmed)
Single-in | Payment apps • eService / EDPS / Erste JV apps • GP TOM SoftPOS | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API |  | • [MIGRATE] Move the front-book (eService / EDPS / Erste JV) onto Nucleus [Bank] • [BUILD] Genius parity for Central Europe — enabling the CZ rebrand and the JV reset plan | • [MIGRATE] Migrate the back-book to Nucleus (timing to be confirmed)
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Acquiring • JV acquiring AT/CZ/SK/RO/CRO eCom • GP Webpay | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## APAC
TAM 2.0 sequencing — SMB · APAC
INPUTS
Business priorities | 1. Genius Mobile Pay for PH (BPI JV; executive-endorsed) — build Q3, deploy early Q4 2. eCommerce — localisation and launch of GP eCom to replace CyberSource / MPGS as the in-house platform 3. Asia boarding — localise the boarding solution to move from >14-day wet-signature onboarding to 1–3 days digital 4. IPP solution design — accelerate the productised IPP solution (~35% of Asia P&L) and embed it in transformation plans
Corporate priorities | • TNAS post-launch stabilisation (~100 production incidents outstanding) • Compliance backlog dating to 2017/18 (~$2.5M p.a. penalties) • Historic under-investment; manual foundations • CYBS Secure Acceptance end of life Jul '27
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Genius Mobile Pay PH — build Q3 '26, deploy Q4 '26 | ▼ CYBS Secure Acceptance EOL Jul '27 ▼ GP-API omnichannel CP launches Q2 '27 – Q1 '28
Single-in | eCom gateways • CYBS • MPGS • CIL 3rd-party QR | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [BUILD] GP eCom + GP API build — replacing CyberSource / MPGS with the in-house target platform | • [BUILD] GP-API omnichannel card-present launches Q2 '27 – Q1 '28 • [MIGRATE] Migrate the CYBS / MPGS estate to GP eCom • [EXIT] CYBS Secure Acceptance end of life Jul '27 | • [EXIT] Complete the MPGS exit (timing to be confirmed)
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM | • [BUILD] Localise the target boarding solution across Asia — enabling the move from >14-day wet-signature to 1–3 day digital onboarding
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Acquiring • TNAS eCom • Legacy eCom gateways | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) |  | • [BUILD] EU Nucleus localisation for HK/SG/PH/MY — the card-present foundation for Genius Mobile Pay • [BUILD] Replace the third-party CIL QR gateway (Octopus, PayMe) with target rails
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Oceania
TAM 2.0 sequencing — SMB · Oceania
INPUTS
Business priorities | (populate ahead of June workshop)
Corporate priorities | (populate ahead of June workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Platforms (confirm SMB vs Integrated ownership) • eWay • Ezidebit • Integrapay | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)