## Notes — READ ME
TAM 2.0 sequencing pre-work — Enterprise (geo × segment view; June workshop pack: Europe · APAC · Oceania)
READ ME FIRST — what this file is (per 12-Jun working session): 1) Unlike the Genius-UK PPT exercise, this is a GEO × SEGMENT view — the unit of sequencing is geo + segment (broken by persona only where it makes sense), NOT proposition. 2) Business priorities and corporate priorities/constraints are INPUTS to sequencing — captured up front with the timeline by which they must be met; propositions (Genius S, WP360, Revenue Boost, eCom…) appear there and as ▲ milestone annotations on the timeline, never as an axis. 3) Each geo tab captures the CURRENT-STATE stack and the TARGET-STATE stack before the timeline. 4) With those inputs, the Now / Next / Later columns sequence the three kinds of work per workstream: new feature build [BUILD], migration [MIGRATE] (+[STOP] constrain/stop-sell), and decom [EXIT].
Terminology alignment (12-Jun): SALES MOTION = direct / partner-led / self-serve · PERSONA = partner/customer type within a segment (e.g. Referral, Agent, ISO/Wholesale, Payfac, PFaaS) · CHANNEL = digital / in-person / omnichannel · PROPOSITION = what the merchant buys (Genius S, WP360, Revenue Boost) — an input & milestone, not an axis · PLATFORM = the stack (current vs target). Persona treatment: SMB = no persona split · Integrated = split by persona · Enterprise = TBD (region × vertical candidate — open decision).
Tags: [BUILD] target-state build / adherence · [MIGRATE] front-book switch, back-book migration, thin-out · [STOP] stop-sell / stop-integration / constrain (feeds Debt Book tranches) · [EXIT] decommission milestone. Motion tags [Direct]/[Bank]/[ISV] only where an implication is motion-specific. Horizons: Now = H2 '26 – H1 '27 · Next = H2 '27 – H1 '29 · Later = H2 '29+. Blue text = hypothesis — validate. Blank = input needed, not 'nothing planned'. (validate w/ SPOC) = no confirmed TAM linkage.
Open questions for the group: 1) Which countries do we consider per region (avoid the long tail) — Europe list to confirm; APAC / Oceania scope to confirm. 2) Enterprise: do we split by persona / vertical (region × top 1–4 verticals) — decide before populating. 3) North America intentionally omitted from this June pack — sequenced for the Jul 20–21 in-person (US/Canada straw-man content preserved in SMB v0.3). 4) Non-UK&I tabs carry pre-fill from the v0.2/v0.3 straw man for efficiency — validate or clear with each geo lead.
Enterprise note: persona / vertical split TBD — candidate structure is region × top 1–4 priority verticals (airlines, gambling, QSR/FSR/Stadia…); decide before populating. Seeded items to validate: WP Total end-of-life — triPOS option currently points at MBoss (not the long-term answer); GMAS EU enterprise back-book → NAP migration as expansion unlock.

## Europe
TAM 2.0 sequencing — Enterprise · Europe (inputs first → current vs target stack → Now/Next/Later by workstream; see Notes tab)
INPUT — Business priorities (segment lead; incl. timing to be met) | (populate ahead of June workshop)
INPUT — Corporate priorities / constraints (hard dates, contractual, regulatory) | (populate ahead of June workshop)
INPUT — Proposition & corporate milestones (▲ annotate on timeline — propositions are inputs, not axes) | (populate ahead of June workshop)
Workstream (boulder) | Current-state stack (today) | Target-state stack (decisions to date — validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Single-in |  | Global API → API 2.0 / Global API ecosystem on Global Gateway · Payment Apps & SDKs → PayApp 2.0 (Nucleus + triPOS hybrid; Yazara softPOS; Scalefusion + Sightstream TMS) · Developer experience → common portal + MCP server · Hosted solutions / plug-ins → target plug-in set on GP-API
Boarding |  | Experience → Ignition (Horizon/Kirby + Launchpad converge) · Ingress → Boarding gateway · Orchestration → Workstream manager · Fulfillment → Actor & PIL · Integration & messaging → Kafka + Mulesoft · Ops data → hWP party model · CPQ → RCA · Credit & underwriting → UCM
Sales & Servicing |  | CRM → 2/3 analysis in progress (OPEN TAM DECISION) · Servicing tools · Risk monitoring (merchant & transaction)
Payment Processing |  | Gateway → Global Gateway · Switch → PowerZac · Auth → RAFT (NA) + PowerZac (ROW) · Clearing → CORE (NA) + NAP (ROW) · APMs → GPPaaS (ROW)
VAS |  | Routing → Routing 2.0 · Gifts → Valutec · Network tokens → hWP tokens · Loyalty → Como · Fraud → Fraudsight · Managed optimization → Revenue Boost · FX / DCC / credential mgmt → hWP · 3DS / exemptions → hWP 3DS flex
Unified Data and AI |  | Data platforms → Snowflake + Iceberg · Master data → MDM
Global Infrastructure |  | Design systems → WP DS foundation + Vega visual layer · Cloud · Observability
Single-out |  | Portal → MyAccount++ · Disputes → WDP · PFaaS → Converged PFaaS · Reporting → analysis in progress (OPEN)

## APAC
TAM 2.0 sequencing — Enterprise · APAC (inputs first → current vs target stack → Now/Next/Later by workstream; see Notes tab)
INPUT — Business priorities (segment lead; incl. timing to be met) | (populate ahead of June workshop)
INPUT — Corporate priorities / constraints (hard dates, contractual, regulatory) | (populate ahead of June workshop)
INPUT — Proposition & corporate milestones (▲ annotate on timeline — propositions are inputs, not axes) | (populate ahead of June workshop)
Workstream (boulder) | Current-state stack (today) | Target-state stack (decisions to date — validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Single-in |  | Global API → API 2.0 / Global API ecosystem on Global Gateway · Payment Apps & SDKs → PayApp 2.0 (Nucleus + triPOS hybrid; Yazara softPOS; Scalefusion + Sightstream TMS) · Developer experience → common portal + MCP server · Hosted solutions / plug-ins → target plug-in set on GP-API
Boarding |  | Experience → Ignition (Horizon/Kirby + Launchpad converge) · Ingress → Boarding gateway · Orchestration → Workstream manager · Fulfillment → Actor & PIL · Integration & messaging → Kafka + Mulesoft · Ops data → hWP party model · CPQ → RCA · Credit & underwriting → UCM
Sales & Servicing |  | CRM → 2/3 analysis in progress (OPEN TAM DECISION) · Servicing tools · Risk monitoring (merchant & transaction)
Payment Processing |  | Gateway → Global Gateway · Switch → PowerZac · Auth → RAFT (NA) + PowerZac (ROW) · Clearing → CORE (NA) + NAP (ROW) · APMs → GPPaaS (ROW)
VAS |  | Routing → Routing 2.0 · Gifts → Valutec · Network tokens → hWP tokens · Loyalty → Como · Fraud → Fraudsight · Managed optimization → Revenue Boost · FX / DCC / credential mgmt → hWP · 3DS / exemptions → hWP 3DS flex
Unified Data and AI |  | Data platforms → Snowflake + Iceberg · Master data → MDM
Global Infrastructure |  | Design systems → WP DS foundation + Vega visual layer · Cloud · Observability
Single-out |  | Portal → MyAccount++ · Disputes → WDP · PFaaS → Converged PFaaS · Reporting → analysis in progress (OPEN)

## Oceania
TAM 2.0 sequencing — Enterprise · Oceania (inputs first → current vs target stack → Now/Next/Later by workstream; see Notes tab)
INPUT — Business priorities (segment lead; incl. timing to be met) | (populate ahead of June workshop)
INPUT — Corporate priorities / constraints (hard dates, contractual, regulatory) | (populate ahead of June workshop)
INPUT — Proposition & corporate milestones (▲ annotate on timeline — propositions are inputs, not axes) | (populate ahead of June workshop)
Workstream (boulder) | Current-state stack (today) | Target-state stack (decisions to date — validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Single-in |  | Global API → API 2.0 / Global API ecosystem on Global Gateway · Payment Apps & SDKs → PayApp 2.0 (Nucleus + triPOS hybrid; Yazara softPOS; Scalefusion + Sightstream TMS) · Developer experience → common portal + MCP server · Hosted solutions / plug-ins → target plug-in set on GP-API
Boarding |  | Experience → Ignition (Horizon/Kirby + Launchpad converge) · Ingress → Boarding gateway · Orchestration → Workstream manager · Fulfillment → Actor & PIL · Integration & messaging → Kafka + Mulesoft · Ops data → hWP party model · CPQ → RCA · Credit & underwriting → UCM
Sales & Servicing |  | CRM → 2/3 analysis in progress (OPEN TAM DECISION) · Servicing tools · Risk monitoring (merchant & transaction)
Payment Processing |  | Gateway → Global Gateway · Switch → PowerZac · Auth → RAFT (NA) + PowerZac (ROW) · Clearing → CORE (NA) + NAP (ROW) · APMs → GPPaaS (ROW)
VAS |  | Routing → Routing 2.0 · Gifts → Valutec · Network tokens → hWP tokens · Loyalty → Como · Fraud → Fraudsight · Managed optimization → Revenue Boost · FX / DCC / credential mgmt → hWP · 3DS / exemptions → hWP 3DS flex
Unified Data and AI |  | Data platforms → Snowflake + Iceberg · Master data → MDM
Global Infrastructure |  | Design systems → WP DS foundation + Vega visual layer · Cloud · Observability
Single-out |  | Portal → MyAccount++ · Disputes → WDP · PFaaS → Converged PFaaS · Reporting → analysis in progress (OPEN)