## SMB
TAM 2.0 — Sequencing pre-work: propositions × workstream matrix ¦ Segment: SMB (v0.3 STRAW MAN — columns restructured to proposition view per 5-Jun direction; TAM implications only, for reaction)
How to read (v0.3 — restructured to the column spec from the 29-May workshop & follow-up calls): COLUMNS = propositions per geo — priority AND legacy/run-off — under geo & region banners (“essentially the columns in a table where the rows are… the applications in the stack”). ROWS = workstreams (boulders). HORIZONS now live inside each cell as line prefixes (≈ the year-1/3/5 altitude): Now = H2 '26 – H1 '27 · Next = H2 '27 – H1 '29 · Later = H2 '29+. Tags unchanged: [BUILD] target-state build / adherence · [MIGRATE] front-book switch, back-book migration, traffic move, thin-out · [STOP] stop-sell / stop-integration / constrain (frees capacity) · [EXIT] decommission milestone. Narrative lens for the Jun-30 ELT readout: lines tied to a numbered business priority = TAM-as-ENABLER; pure rationalisation lines = TAM-as-HERO; [STOP] lines feed the stop-list (capacity release). Legacy run-off columns feed the Debt Book tranche analysis (T1 = no-regret exit 0–6 mo · T2 = ≤18 mo · T3 = 24 mo+); tranche tags in the motion row are HYPOTHESES — validate w/ SPOC. Cells merged across a whole geo = geo-wide content, not yet proposition-specific. Blank = we need your input, not 'nothing planned'. (validate w/ SPOC) = no confirmed TAM linkage. Replicate per segment with segment-specific column logic: Enterprise = region × priority vertical (1–4 per region); Integrated & Platforms = platform/portfolio first (Payrix · ProPay · Assist · hWP vs hGP integrated), region second. Blue text = hypothesis to validate. Corporate anchors: Genius S live on hWP/NAP rails (UK pilot Q1 '27) · GMAS EU / FIS migration waves 2028 · ACI / Postilion BO exit 2029 · UPA demise T1 9/'27 · T2 3/'28 · T3 9/'28.
|  | EUROPE | [10 empty] | NORTH AMERICA |  |  |  |  | APAC
|  | UK&I |  |  |  | Poland |  | Greece |  | Spain |  | CEE — Erste JV | US |  |  | Canada |  | Asia
Workstream (boulder) | Big rock → target-state platform (blue-text hypothesis — validate) | Genius S (Direct — incoming) | Direct core TP+ · WP360 · WP eComm (+Essentials) | Partner — Bank & JV BOIPA · BOI/PTSB · Tuza → Horizon | Legacy estate (run-off) GP ecom/Access APIs · WPG · Inovo/Sterling · legacy payment apps | Partner — Bank & JV (PKO BP / eService) POS estate · Xpay · Merchant Portal | Direct eCom GP eCom (post-EPG) · Nestpay (legacy — exit) | Partner — Bank & JV (NBG Pay) NBG Pay tom (white-label) · eService/Postilion estate | Direct GP tom · GP eCom (incoming) · MPGS (legacy — exit) | Partner — Bank & JV (CaixaBank / Comercia) Comercia 2.0 POS · TPV&GO · EPG/Addon2 · MyCommerce (to-be) | Direct GP API eComm (incoming '27) · UniversalPay (run-off) | Partner — Bank & JV (Erste) JV acquiring AT/CZ/SK/RO/CRO · GP TOM SoftPOS · GP Webpay · Genius (CZ rebrand) | Direct Genius hPOS (Retail/Restaurant) · SwipeSimple · GP-API | Partner — Bank/FI Genius for SMB Merchant Bank (WP rails) · FI self-enrollment (Citizens, M&T) | Partner — ISV/ISO & legacy iQ + Launchpad · TrustCommerce · NPC (decom) · UPA/Cayan (run-off) | Direct UPA on GP-API/Portico · IP (Cayan) launch (incoming) | Partner — indirect/ISV Enablement parity (Interac, French) | Direct TNAS acquiring · IPP · GP eCom + GP API (incoming) · CYBS/MPGS (run-off) | Partner — Bank & JV (BPI, PH) Genius Mobile Pay / SoftPOS
|  | Direct — GP P&L · front-book target (incoming) | Direct — GP P&L · front-book | Partner — Bank & JV — JV/shared P&L (BOIPA) + FI referral · front-book | Legacy — run-off · Debt Book hypothesis: Inovo/Sterling T1–T2 · WPG thin-out then T3 · ACI exit dated 2029 (validate) | Partner — Bank & JV — eService / PKO BP P&L · front-book | Direct — GP P&L · front-book (GP eCom) + run-off (Nestpay — Debt Book T1 hypothesis) | Partner — Bank & JV — NBG Pay P&L · front-book | Direct — GP P&L · incoming (GP eCom) + run-off (MPGS — T2 hypothesis; feature-gap gate) | Partner — Bank & JV — Comercia (CaixaBank) P&L · front-book | Direct — GP P&L · incoming ('27) + run-off (UniversalPay — scheduled run-down) | Partner — Bank & JV — Erste JV P&L · front-book | Direct — GP P&L · front-book | Partner — Bank/FI — GP P&L w/ FI distribution · front-book (on sale H2 '26) | Partner — ISV/ISO — GP P&L · front-book (iQ/Launchpad) + run-off (NPC decom in flight · UPA demise dated T1–T3 · Cayan post-harvest) | Direct — GP P&L · front-book | Partner — ISV/indirect — GP P&L · enablement | Direct — GP P&L · front-book (TNAS/IPP) + incoming (GP eCom/GP API) + run-off (CYBS EOL 7/'27 · MPGS) | Partner — Bank & JV — BPI JV P&L · front-book (incoming)
Business priorities | Per geo-segment — from segment leads (validate); numbered per geo to support the enabler lens | 1. Genius S UK — decision confirmed; dev on NAP target-state rails, Q1 '27 pilot | 2. eCommerce expansion — WP eComm Essentials, Shopify Onsite, plugin activation 3. VAS growth — Everyday/Instant Settlement, DCC back-book, MCA in-house (rev c.$35m '27–28) | 4. Bank channels — BOI, Virgin Money/Nationwide, HSBC (Tuza, eComm, Genius Mobile, Dashboard hooks) | (run-off — no growth priorities; capacity-release / Debt Book candidate) | 3. SMB POS — COMO loyalty + Xpay all-in-one 4. Cash2card w/ eService Pay app (€750k incentive) | 1. eCom: Click2Pay by June — Cashless Programme eligibility (85% of PL eCom sales) + Visa/MC incentives 2. GP eCom enhancements — DCC, BLIK LVL0/OneClick, eRaty | 1. Close out Mirage migration (NBG bank systems → eService/Postilion) — completes end-June 3. Fiscalization-led all-in-one market (SoftPOS, PCI POS) 4. Genius Mobile — transition from white-label NBG Pay tom | 2. GP eCom — finalise plan & sales strategy | 1. Bizum scale-out → ~500k terminals (full deploy by 29 Jun; enterprise activations) 2. Multi-acquiring C2.0 — LIDL won, ALDI strategic; 157-opp pipeline 3. BNPL w/ CaixaBank — full rollout this quarter 4. Close WP/Comercia commercial & product model gap (share loss) | (GP API eComm entry '27 — omnichannel gap is the binding constraint; UniversalPay run-off) | 1. VAS growth (+70% YoY; 16% of JV revenue) — DCC on SoftPOS, loyalty, instalments 2. Genius parity for Central Europe (w/ Genius S team); CZ rebrand 3. Croatia expansion (CNB regulatory friction — key meeting June) 4. EEA Accessibility Act rollout (4 countries) | 1. Genius rooftop growth +20% (re-baseline w/ Gilbert) 3. VAS bundles for SMB by Q4; attrition 28.8% → 23% 4. GP-API as single integration front door (launched US SMB & Mid-Corp) | 2. Genius for SMB Merchant Bank on WP rails — on sale H2 '26 | (channel enablement parity through transition; NPC / UPA run-off) | 2. UPA rollout on GP API & Portico (Direct CA) | 1. Indirect enablement parity — PIN Debit/Interac + French | 2. GP eCom localisation — replace CyberSource/MPGS in-house 3. Boarding: >14-day wet-signature → 1–3 day digital onboarding 4. Productise IPP (~35% of Asia P&L) | 1. Genius Mobile Pay PH (BPI JV; exec-endorsed) — build Q3, deploy early Q4
Corporate constraints | Hard dates / contractual / regulatory (validate) — geo-wide | • BG migration: audit deadline Jul '27; automated tooling blocked on infra DB capacity • NerPay Ingenico app sunset path • ACI / Postilion BO exit by 2029 (corporate) • Fragmented hGP/hWP sales tooling & portals |  |  |  | • PDLC / ownership gaps on eService core platforms (no PM allocation) • Tech capacity — multi-year delays (e.g. pre-auth on host) • GP eCom delivery delays & reprioritisation flip plans |  | • MPGS → GP eCom feature gap (18-mo plan; platform non-competitive until closed) • Greek fiscalization rules (incl. pre-auth alignment) • Postilion dependency (ACI exit 2029 — corporate) |  | • No omnichannel product (eCom + F2F single API) in Spain • Legacy + new stack coexistence — speed & scalability • Carve-out: Model 170, reconciliation files • GP eCom processing/dev cost alignment; mid-term GP API & eCom scope |  | • E-com capacity on GP Webpay vs competitor pace • Croatian National Bank interference (CRO plans) • Genius product gap vs competition in Central Europe | • TAM contingency on Genius Retail (WP) • Dual hWP/hGP partner tooling through transition • ISO NPC decom — readiness done; migration & decom to complete • UPA demise tranche dates (T1 9/'27 · T2 3/'28 · T3 9/'28) |  |  | • Parity gaps vs US stack (Interac, language) • GNAP exit underway → GSAP/Portico (corporate — illustrative) • UPA demise T2 incl. Canada (3/'28) |  | • TNAS post-launch stabilisation (~100 open incidents) • Compliance backlog to 2017/18 (~$2.5M p.a. penalties) • Historic under-investment; manual foundations • CYBS Secure Acceptance EOL Jul '27
Single-in | Global API → API 2.0 / Global API ecosystem on Global Gateway · Payment Apps & SDKs → PayApp 2.0 (Nucleus + triPOS hybrid; Yazara softPOS; Scalefusion + Sightstream TMS) · Developer experience → common portal + MCP server · Hosted solutions / plug-ins → target plug-in set on GP-API | Now · [BUILD] Genius S payment app Ph.1 — GP SDK → triPOS on hWP stack Next · [BUILD] Genius S Ph.2 — Nucleus headless (PayApp 2.0 convergence) | Now · [BUILD] Global API — develop & adhere to GP-API standard (UK&I SMB front door) Next · [MIGRATE] Back-book API traffic → Global API |  | Now · [STOP] Stop new integrations to GP ecom / Access legacy APIs Next · [MIGRATE] UPA / eService app traffic → PayApp 2.0 Next · [STOP] Stop core-acquiring integrations to legacy payment apps Later · [EXIT] Decom GP ecom & Access APIs Later · [EXIT] Decom eService / UPA / Yazara standalone apps (post-migration) | Now · [BUILD] Nucleus replaces eService payment app — P2C → Nucleus (Sep '26) Next · [MIGRATE] PAX AP / ECC estate → Nucleus Later · [EXIT] eService legacy payment app decom (post-migration) |  | Now · [BUILD] Nucleus (+ Genius S) replaces EDPS payment app — build & localise Next · [MIGRATE] EDPS app estate → Nucleus Later · [EXIT] EDPS payment app decom |  |  | Next · [BUILD] GP API as eComm gateway for Spain ('27) | Next · [MIGRATE] Front-book — eService / EDPS / Erste JV onto Nucleus [Bank] Next · [BUILD] Genius parity for Central Europe Later · [MIGRATE] Back-book → Nucleus (validate w/ SPOC) | Now · [BUILD] GP-API adherence — single integration front door (US SMB live) Now · [BUILD] Harvest Cayan components into PayApp 2.0 (Nucleus + triPOS hybrid) |  | Next · [EXIT] UPA demise T1 — Bermuda / L-GPN (9/'27) Next · [EXIT] UPA demise T2 — L-HPY / L-TSYS / Canada (3/'28) Next · [EXIT] UPA demise T3 — semi-integrated / P2PE (9/'28) Later · [EXIT] Cayan platform deprecation (post-harvest) | Now · [BUILD] IP (Cayan) Canada launch on PayApp 2.0 path-to-TAM Next · [EXIT] UPA demise T2 incl. Canada (3/'28) |  | Now · [BUILD] GP eCom + GP API build (TAM #24713) Next · [BUILD] GP-API omnichannel CP launches Q2 '27 – Q1 '28 (#122516) Next · [MIGRATE] CYBS / MPGS estate → GP eCom Next · [EXIT] CYBS Secure Acceptance EOL Jul '27 Later · [EXIT] MPGS exit complete (validate w/ SPOC)
Boarding | Experience → Ignition (Horizon/Kirby + Launchpad converge) · Ingress → Boarding gateway · Orchestration → Workstream manager · Fulfillment → Actor & PIL · Integration & messaging → Kafka + Mulesoft · Ops data → hWP party model · CPQ → RCA · Credit & underwriting → UCM |  | Now · [BUILD] Adhere — boarding API + hWP party model Now · [BUILD] Single boarding instance for UK&I Next · [BUILD] Ignition capabilities live (Horizon/Kirby + Launchpad converge) | Next · [BUILD] Tuza → Horizon-based replacement | Now · [STOP] Stop-sell hGP referral boarding tools [ISV] Next · [MIGRATE] BG back-book migration (audit deadline Jul '27) Later · [MIGRATE] Boarding back-book → Ignition Later · [EXIT] Legacy boarding decom
Sales & Servicing | CRM → 2/3 analysis in progress (OPEN TAM DECISION) · Servicing tools · Risk monitoring (merchant & transaction) | Now · [BUILD] CRM 2/3 analysis — OPEN TAM DECISION (geo-wide; validate w/ SPOC) | [12 empty] | Now · [EXIT] ISO NPC decom — complete migration & decom (762 ISOs migrated) [ISV]
Payment Processing | Gateway → Global Gateway · Switch → PowerZac · Auth → RAFT (NA) + PowerZac (ROW) · Clearing → CORE (NA) + NAP (ROW) · APMs → GPPaaS (ROW) | Now · [BUILD] Genius S dev on NAP target-state rails (pilot Q1 '27) | Now · [BUILD] Global Gateway — develop for UK&I Next · [MIGRATE] Integrate POS & API flows to Global Gateway; migrate back-book |  | Now · [STOP] Stop new integrations to non-target gateways (WPG et al.) Next · [MIGRATE] Thin out WPG Later · [EXIT] Decom Inovo / Sterling Later · [EXIT] ACI / Postilion BO exit (2029 — corporate) | Next · [BUILD] Genius S expansion pilot #2 on NAP rails (post-UK) | Now · [STOP] Nestpay — stop-sell / stop new integrations Next · [MIGRATE] Nestpay merchants → GP eCom Later · [EXIT] Nestpay decommission |  | Now · [STOP] MPGS — stop new integrations (feature-gap plan in flight) Next · [MIGRATE] MPGS → GP eCom merchant migration Later · [EXIT] MPGS exit Later · [EXIT] ACI / Postilion BO exit (2029 — corporate) | Later · [EXIT] miTPV (Comercia) deprecation | Now · [MIGRATE] UniversalPay migration (run-down continues) Later · [EXIT] UniversalPay exit complete |  | Next · [BUILD] Auth → RAFT / Clearing → CORE adherence (validate w/ SPOC) | Now · [BUILD] Genius for SMB Merchant Bank on WP processing rails [Bank] |  | Next · [MIGRATE] GNAP exit → GSAP / Portico (corporate) |  | Next · [BUILD] Replace 3rd-party CIL QR gateway (Octopus, PayMe → target rails) | Next · [BUILD] EU Nucleus localisation — HK/SG/PH/MY (CP foundation for Genius Mobile Pay)
VAS | Routing → Routing 2.0 · Gifts → Valutec · Network tokens → hWP tokens · Loyalty → Como · Fraud → Fraudsight · Managed optimization → Revenue Boost · FX / DCC / credential mgmt → hWP · 3DS / exemptions → hWP 3DS flex | Now · [BUILD] Deploy Como (loyalty target platform) Next · [BUILD] VAS orchestration layer Next · [MIGRATE] Integrate VAS to Global Gateway; migrate front-book Later · [MIGRATE] VAS back-book Later · [EXIT] Legacy VAS decom (geo-wide; constrain VAS distribution to target gateways only — no new legacy integrations)
Unified Data and AI | Data platforms → Snowflake + Iceberg · Master data → MDM | Now · [BUILD] MDM adherence Now · [BUILD] Genius AI + Fraudsight POC Next · [BUILD] Data platforms & orchestration → Snowflake + Iceberg Next · [MIGRATE] Migrate reporting / data feeds to target platforms Later · [EXIT] Legacy data stores decom (geo-wide)
Global Infrastructure | Design systems → WP DS foundation + Vega visual layer · Cloud · Observability | Now · [BUILD] WP design-system foundation + Vega visual layer (Genius S UI adherence) Now · [BUILD] Infra / DB capacity to unblock BG migration tooling (geo-wide)
Single-out | Portal → MyAccount++ · Disputes → WDP · PFaaS → Converged PFaaS · Reporting → analysis in progress (OPEN) | Now · [BUILD] MyAccount 2.0 — portal target-state build Next · [MIGRATE] Integrate, then migrate Dashboard / legacy portals → MyAccount++ Next · [BUILD] Disputes → WDP adherence Later · [EXIT] Legacy portal decom (geo-wide)