## How to read
TAM 2.0 sequencing pre-work — Enterprise
Workshop pack: Europe · APAC · Oceania (June) · North America (Jul 20–21)
How to read this workbook:
• Each geo tab opens with the inputs: business priorities and corporate priorities, with the dates by which they must be met.
• The Milestones row (▼) places major proposition-related milestones over the horizon in which they land.
• Each workstream row shows the current-state stack, the target-state stack, and the planned actions across Now (H2 '26 – H1 '27), Next (H2 '27 – H1 '29) and Later (H2 '29+).
• Actions are tagged: [BUILD] target-state build · [MIGRATE] migration or thin-out · [STOP] stop-sell / stop-integration · [EXIT] decommission.
• Square brackets denote channel context where relevant, e.g. [Bank], [ISV], [Payrix].
• Content is scoped to TAM 2.0 — platform-rationalisation actions, not the full BAU roadmap. Where an action enables a stated business priority, the cell says so.
• Data centre consolidation is tracked under the Global Infrastructure & Security workstream.
• Blue text is a working hypothesis for validation. A blank cell is a request for input — not an indication that nothing is planned.
Aggregate priorities (segment-wide, 2026–27):
• Standardization and platform unification (POM + TAM).
• Onboarding and activation speed — the core growth bottleneck.
• VAS monetization — lending, payments optimization, settlement.
• Execution discipline — customer commitments and large rollouts.
• Migration off legacy and reduction of fragmentation.
Enterprise segment priorities:
• 2026 — Expand global payment capabilities (APMs, card acceptance, hosted payouts and in-app solutions). Enable complex enterprise use cases (marketplace and platform capabilities: split payments, cross-border collection, embedded payouts and treasury flows). Launch next-gen commerce (agentic commerce foundations; tokenized payments and AI integrations). Optimize partner and cost structure (third-party dependencies, partner agreements, commercial models).
• 2027 — Platform for global enterprise commerce (global payments, marketplaces, embedded finance). Scale next-gen commerce (card networks, AI ecosystems). Marketplace dominance at scale (split payments, cross-border collection, embedded payouts and treasury flows). Complete global APM coverage.

## North America
TAM 2.0 sequencing — Enterprise · North America
Pre-seeded for the Jul 20–21 North America sequencing session.
INPUTS
Business priorities | 1. Pay-by-Bank US — GPPaaS completes PI2, Core (RAFT and EF) in PI3, end-to-end testing late Q3 / early Q4; Aeropay progressing on the non-guaranteed model 2. Agentic commerce — launch 1–2 merchants on ACP/UCP; OpenAI ACP code-complete and Visa Agentic Token in certification (protocol, token and trust layers) 3. Interac in-app — eCom enablement for Google and Apple Pay ($19M+ Canadian pipeline) 4. Franchisee automation — boarding API, Salesforce and Maxwell automation for Canadian merchants ($19M+ pipeline) 5. Payouts expansion — PayPal and USDC wallets; UATP US domestic; whale-deal conversion to de-risk the payouts cross-sell gap
Corporate priorities | • Aeropay contract unsigned; revised non-guaranteed pricing introduces material risk to the US Pay-by-Bank business case for Platforms • Klarna Network US pushed ~1 PI (≥Q1 '27) in favour of Pay-by-Bank — agreed trade-off • Revenue Boost proposition completeness — boarding and reporting limitations driving poor merchant experience • eDCC for US/CAN hospitality — did not make the PI2 cutline; sizing under way
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Agentic commerce — first 1–2 merchants live on ACP/UCP ▼ Pay-by-Bank US end-to-end testing late Q3 / early Q4 '26 | ▼ Klarna Network US ≥Q1 '27 (post trade-off)
Single-in | Front doors • Access Worldpay • TAPI (persists, corporate) • GP eCom API / GP-API (hGP) Card present • FreedomPay (reseller) • triPOS | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [STOP] Constrain new enterprise API builds to Access / the front-end API — segment-wide policy ahead of API 2.0 • [BUILD] Agentic commerce foundations — complete OpenAI ACP and Visa Agentic Token certification; launch 1–2 merchants on ACP/UCP — enabling the next-gen commerce priority | • [MIGRATE] Converge Access onto the API 2.0 / Global API standard (federated build to spec)
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM | • [BUILD] Unified franchisee platform and automation — boarding API, Salesforce and Maxwell automation for Canadian merchants, replacing custom-built setups | • [BUILD] Auto-boarding end to end across gateway systems down to APM partners — supporting payfac and marketplace setups at scale
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Acquiring & switches • VAP — NA only • Core • RAFT | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [BUILD] Pay-by-Bank US — GPPaaS, Core (RAFT/EF) and end-to-end testing; low-code integration model removing APM adoption friction • [BUILD] Interac in-app enablement (ETP, ~1 PI) — unlocking top Canadian opportunities | • [BUILD] Klarna Network US (re-sequenced ≥Q1 '27 after the Pay-by-Bank trade-off) • [BUILD] Payouts expansion — PayPal and USDC wallets; UATP US domestic
VAS | Optimization • Revenue Boost • FraudSight / Ravelin • Separate authentication & routing services (sold separately today) | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP | • [BUILD] Revenue Boost completeness — integrated debit routing and intelligent token decisioning • [BUILD] FraudSight premier UI enablement; Ravelin integration to both hWP and hGP gateways — one fraud answer either side of the estate | • [BUILD] Bring optimization and authentication services under the single intelligent decision layer — sold as a suite, not separate products • [BUILD] eDCC for US/CAN hospitality (sizing in progress)
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Europe
TAM 2.0 sequencing — Enterprise · Europe
INPUTS
Business priorities | 1. Wero — start build in PI3 (GPP, Plutus and WPAP trains) to protect iDEAL revenue (~$1.7m p.a.) and top-tier merchants (Disney, Apple, Etsy, Bet365) ahead of iDEAL decommissioning Q4 '27; merchants need 8–12 months to integrate 2. Marketplaces — APM enablement for split payments across ~60% of EU countries (Germany, Poland, Netherlands, Nordics, Italy, Belgium ≈ 50% of EU eCom GMV); $9.3M lost to date, $14M+ active pipeline 3. Jaywan enablement — mandated in the UAE; Q3 go-live dependent on credential management and MPLS connectivity 4. Vipps/MobilePay for the Nordics — required for the ~$1m Miinto deal 5. Reach — global Merchant-of-Record enablement (Tier-1 interest incl. META) 6. Omnichannel — Genius into enterprise QSR/FSR/Stadia for UK & Europe; WP Total replacement 7. GMAS EU enterprise back-book — migration to NAP as the expansion unlock
Corporate priorities | • iDEAL decommissioning Q4 '27 — hard external date; Wero capacity not available across APM trains in PI3/PI4 without trade-offs (Payermax and Pix delayed to fund it) • WP Total end-of-life — the triPOS option currently points at MBoss, which is not the long-term answer; replacement must carry real-time reporting or customers will leave • Jaywan — lack of clarity from the credential management team on timelines (escalated) • GMAS EU / FIS separation — migration waves 2028 (corporate) • FX — eDCC widening and live FX (<10-minute onboarding) extend the MCP+ moat for the airline-heavy book
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Jaywan go-live Q3 '26 (UAE mandate) ▼ Wero build starts PI3 ▼ Klarna Network GA RoW | ▼ iDEAL decommissioning Q4 '27 (Wero integrated 8–12 months prior) ▼ WP Total replacement defined and in market ▼ GMAS EU / FIS migration waves 2028
Single-in | Front doors • Access Worldpay • WPG Card present • WP Total (end-of-life path) • FreedomPay (reseller) • Genius (referral today) | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [STOP] Constrain new enterprise API builds to Access / the front-end API — segment-wide policy ahead of API 2.0 • [BUILD] Reach — global Merchant-of-Record enablement via Access and WPG (Tier-1 interest incl. META) | • [MIGRATE] Converge Access onto the API 2.0 / Global API standard (federated build to spec) • [BUILD] Genius into the enterprise omnichannel offer (QSR/FSR/Stadia, UK & Europe) on the target SDK path — full end-to-end replacing the referral model
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM | • [BUILD] Marketplace seller onboarding (KYC/KYB) — fold into the pan-TAM KYB/KYC approach and partner selection
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Acquiring • GMAS Europe (hGP enterprise back-book) • NAP (target) APM estate • iDEAL (decommissioning Q4 '27) • Legacy MOR models (Klarna) • APM trains: GPP · Plutus · WPAP | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [BUILD] Wero — start build PI3 across GPP/Plutus/WPAP — protecting iDEAL-dependent revenue and top-tier merchants • [BUILD] Jaywan enablement (3 teams; credential management dependency) — mandated in the UAE • [BUILD] Vipps/MobilePay for the Nordics — enabling the Miinto deal and Nordic TAM • [BUILD] Marketplace APM enablement for split payments (WPG + MPM) — enabling the marketplace addressability priority (14% → 40%) • [BUILD] Hosted Payouts marketplace solution — fully hosted payouts distribution, reducing integration friction | • [EXIT] iDEAL decommissioning Q4 '27 (post-Wero migration) • [MIGRATE] Klarna RoW merchants off legacy MOR architecture onto WPG/Access • [MIGRATE] GMAS EU enterprise back-book → NAP (FIS waves 2028) — new locations and products then route via converged rails • [MIGRATE] WP Total exit — define the proprietary triPOS-based replacement (MBoss pointing is tactical at best) | • [EXIT] Complete the GMAS EU exit • [EXIT] Decommission WP Total
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP | • [BUILD] FX — eDCC widening and live FX (<10-minute onboarding), extending the MCP+ moat • [BUILD] FraudSight premier — UI enablement and the gambling SAM campaign
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out | Payouts • Payout portal (hosted payouts incoming) | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending) | • [BUILD] Hosted payouts directly in the portal (1 team, 1 PI) — removes merchant dev-prioritisation dependency (UKVI, Disney, Next, Qatar Airways; ~$1M plus product pull-through) | • [BUILD] Payout rules and reconciliation reporting — closing the proposition gap that limits marketplace scalability

## APAC
TAM 2.0 sequencing — Enterprise · APAC
INPUTS
Business priorities | 1. Japan — JCB proxy aggregator launch (B2B + PayFac acceptance of Japan's second-largest network without a direct relationship); JCB network tokenization next (auth-rate uplift, reduced proxy fees) 2. Alipay+ scale-out — single connection unlocking 17 dominant APMs; live with Garuda, Lensemode, NEXT 3. Taiwan — data-localisation path required; the CyberSource connection is end-of-life next year and Tier-1s (Apple) want to move 4. Payermax for SEA — preferred local payment methods where APMs dominate share of wallet (delayed by the Wero trade-off)
Corporate priorities | • Taiwan data localisation — current stack is not cloud-ready in-market; fundamental TAM work required before a CyberSource replacement can be offered • Payermax delivery pushed from Q4 '26 to ≥Q1 '27 (capacity moved to Wero); $8.3M p.a. acquiring ACV at risk plus $1.8M pipeline • JCB tokenization spans CMP, RB, PET, WPG and NAP — multi-train coordination
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Japan JCB proxy aggregator launch Q3 '26 ▼ Alipay+ live (17 APMs) | ▼ CyberSource Taiwan connection end-of-life '27 ▼ Payermax delivery ≥Q1 '27 (post-trade-off)
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [STOP] Constrain new enterprise API builds to Access / the front-end API — segment-wide policy ahead of API 2.0 | • [BUILD] Card-present solution and certification for APAC enterprise — required before hGP CP back-books (omnichannel, hotels) can move to target rails
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Acceptance • CyberSource connection — Taiwan (end-of-life '27) • Gateway-acquirer card-present only in parts of Asia APMs • Alipay+ (live) • Local APM gaps (SEA) | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [BUILD] Japan JCB proxy aggregator — acceptance without a direct relationship, expanding the addressable footprint • [BUILD] Scale Alipay+ — 17 APMs through one connection, enabling the geo-presence priority | • [BUILD] Taiwan data-localisation path — cloud-ready stack to replace the end-of-life CyberSource connection and retain Tier-1s (Apple) • [BUILD] JCB network tokenization across CMP/RB/PET/WPG/NAP — auth-rate uplift and reduced Japan proxy fees • [BUILD] Payermax for SEA (re-sequenced ≥Q1 '27 after the Wero trade-off)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Oceania
TAM 2.0 sequencing — Enterprise · Oceania
INPUTS
Business priorities | (populate ahead of the workshop)
Corporate priorities | (populate ahead of the workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)