## How to read
TAM 2.0 sequencing pre-work — Integrated & Platforms
Workshop pack: Europe · APAC · Oceania (June) · North America (Jul 20–21)
How to read this workbook:
• Each geo tab opens with the inputs: business priorities and corporate priorities, with the dates by which they must be met.
• The Milestones row (▼) places major proposition-related milestones over the horizon in which they land.
• Each workstream row shows the current-state stack, the target-state stack, and the planned actions across Now (H2 '26 – H1 '27), Next (H2 '27 – H1 '29) and Later (H2 '29+).
• Actions are tagged: [BUILD] target-state build · [MIGRATE] migration or thin-out · [STOP] stop-sell / stop-integration · [EXIT] decommission.
• Square brackets denote channel context where relevant, e.g. [Bank], [ISV], [Payrix].
• Content is scoped to TAM 2.0 — platform-rationalisation actions, not the full BAU roadmap. Where an action enables a stated business priority, the cell says so.
• Data centre consolidation is tracked under the Global Infrastructure & Security workstream.
• Blue text is a working hypothesis for validation. A blank cell is a request for input — not an indication that nothing is planned.
Aggregate priorities (segment-wide, 2026–27):
• Standardization and platform unification (POM + TAM).
• Onboarding and activation speed — the core growth bottleneck.
• VAS monetization — lending, payments optimization, settlement.
• Execution discipline — customer commitments and large rollouts.
• Migration off legacy and reduction of fragmentation.
Integrated segment priorities:
• 2026 — Stabilize core growth engines (Payrix; close roadmap gaps across hGP and hWP). Accelerate merchant activation and partner growth in the US and UK. Payrix with in-person payments. Embedded Finance. Assist / Integrated. Monetize VAS (payouts, lending/EFE, fraud, tokenization) and increase multi-product attach rate. Solve ACH. CRM consolidation and fragmentation.
• 2027 — Converge onboarding, payments and reporting (reduce duplicate stacks). Embedded finance and VAS as primary growth drivers (lending, RTP, fraud, tokenization). Global partner expansion. Fully integrate the merchant lifecycle (onboard → activate → monetize).

## North America
TAM 2.0 sequencing — Integrated · North America
Pre-seeded for the Jul 20–21 North America sequencing session.
INPUTS
Business priorities | 1. Stabilize Payrix — Cornerstone (platform integrity, reporting, reconciliation) and in-person payments; restore partner confidence and merchant activation 2. Close roadmap gaps across the two IP books (hGP $1.3B / hWP $750M) to create growth and minimize attrition 3. Embedded Finance — EFE–GP integration brings Capital to hGP Integrated ISVs; faster funding (RTP / P2A); iQ SMB widget distribution 4. Monetize VAS via pilot motions — Fee Assist (surcharge), Disputes Defender, network payment tokens, account updater — particularly in PayFac 5. Solve ACH pan-segment — the binding constraint on VAP retirement (VAP serves North America only) 6. CRM consolidation (hGP) and Launchpad low-code self-enrolment
Corporate priorities | • ACH dependency — VAP cannot be retired while Payfacs and Payrix depend on its ACH; Express/CheckCommerce is US-only with disconnected reporting; hGP relies on third parties (DCS) • Aeropay PBB no longer commercially viable for Platforms — a pan-segment ACH solution with purpose-fit features is needed • GPI SF.com → hCorp SF.com consolidation — complex cutover with surcharging and auto-boarding dependencies (Jul 13) • PayFac optimization suite delays — managed Account Updater slipped to Q3/Q4, smart retries to early '27 (multi-train dependencies) • POSPortal → Jeffersonville move blocking Android device activation
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ SF.com cutover Jul 13 '26 (surcharging + auto-boarding) ▼ Assist 2B date Jul 10 '26 ▼ Payrix in-person payments GA (~2 PIs) | ▼ PayFac optimization suite GA — managed AU Q3/Q4 '26, smart retries early '27 ▼ VAP ACH decision unlocks VAP-to-Core migrations
Single-in | Integration front doors • Payrix API • Assist • ProPay • hWP integrated stack • hGP integrated stack (iQ + Launchpad) | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API | • [BUILD] Payrix in-person payments experience [Payrix] — card-present acceptance and terminal management for ISVs (4 teams, ~2 PIs) • [BUILD] Assist card-present implementation [Assist] — embeddable React component on triPOS Cloud, letting ISVs embed full CP capability • [BUILD] Launch modern Android OS devices across merchant form factors [IP] | • [BUILD] Align both IP books to the API 2.0 / Global API federated standard — converging hGP and hWP integration front doors • [MIGRATE] Begin converging duplicate integration stacks — enabling the 2027 priority to fully integrate the merchant lifecycle | • [EXIT] Decommission duplicate integration front doors once partner migration completes
Boarding | Boarding • Launchpad (hGP) • Payrix boarding • GPI SF.com (consolidating into hCorp SF.com) | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM | • [MIGRATE] GPI SF.com → hCorp SF.com consolidation — cutover Jul 13 with surcharging and auto-boarding enablement [IP] • [BUILD] Launchpad seamless self-enrolment — low-code embed of the enrolment process, enabling the partner-led growth priority | • [BUILD] Parallel onboarding and faster funding [EFE] • [BUILD] Converge boarding onto Ignition / the hWP party model as the target experience lands | • [EXIT] Decommission legacy partner boarding paths
Sales & Servicing | CRM • Fragmented hGP CRM estate (consolidation in flight) | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction | • [BUILD] Progress hGP CRM consolidation in line with the pending CRM 2/3 decision
Payment Processing | Platforms • VAP — NA only (retirement gated on ACH) • Express / CheckCommerce (US-only ACH) • Core • Third-party ACH (DCS) on hGP | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [BUILD] Resolve the pan-segment ACH gap — decide between retaining VAP as an ACH-only platform behind Core/Express, or mirroring VAP with Fifth Third as ODFI behind Core (~$1.4M scope); VAP serves NA only and this gates its retirement • [STOP] Aeropay Pay-by-Bank for Platforms — deprioritised (no longer commercially viable) | • [MIGRATE] VAP → Core migrations once the ACH path lands • [BUILD] Real-time payments / dynamic payouts for instant sub-merchant funding [PayFac] • [BUILD] Push to Account — single global payouts solution [PayFac] | • [EXIT] Retire VAP (gated on the ACH decision and migrations)
VAS | Embedded finance & VAS • EFE (hWP) • Fee Assist / surcharge • Payrix VAS set (fraud, tokens, payouts) | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP | • [BUILD] EFE–GP integration — Capital available to hGP Integrated ISVs, establishing the framework for future geo expansion [EFE] • [BUILD] Payrix VAS expansion — second lending provider (YouLend), Disputes Defender, network payment token, real-time payouts, account updater [Payrix] • [BUILD] Fee Assist (surcharge) for sub-merchants [PayFac] | • [BUILD] PayFac full optimization suite to GA — managed account updater (Q3/Q4) with Pazien reporting; smart retries (early '27) [PayFac] • [BUILD] Distribute EFE through non-ISV channels (iQ SMB widget) — expanding the embedded-finance SAM
Unified Data and AI | Reporting • Payrix reporting & reconciliation (Cornerstone remediation) • Pazien | Data platforms • Snowflake + Iceberg Master data • MDM | • [BUILD] Payrix Cornerstone — reconciliation reporting, chargeback/payout stabilization and platform revenue integrity (4 teams, ~3 PIs) [Payrix] | • [BUILD] Enhanced reporting intelligence layer — uniform data codification for reporting and reconciliation, aligned with Pazien direction • [BUILD] Automated merchant migration tooling — processor-to-processor moves for software platforms
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure) | • [MIGRATE] POSPortal → Jeffersonville distribution centre — resolve key-exchange issues blocking Android device activation
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending) |  | • [MIGRATE] Converge onboarding, payments and reporting experiences — reducing duplicate stacks per the 2027 priority

## UK&I
TAM 2.0 sequencing — Integrated · UK&I
INPUTS
Business priorities | 1. Accelerate merchant activation and partner growth in the UK (2026 segment priority) 2. UK expansion — currently behind plan given early pilot challenges [Intl] 3. Define the target path off the Integrapay dependency for UK Integrated
Corporate priorities | • UK Integrated currently leverages Integrapay — interim platform, not target state • Multi-SUN capability for direct debit required in market [Intl] • POS pilot challenges slowing UK expansion
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ UK POS pilot stabilisation
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM |  | • [BUILD] Align UK partner boarding to Ignition / the hWP party model as it lands
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Platforms • Integrapay (interim for UK Integrated) | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [MIGRATE] Define the target path off Integrapay for UK Integrated — sooner rather than later; align with the Global Gateway timeline to avoid a two-hop migration | • [BUILD] Multi-SUN direct debit capability — enabling the UK expansion priority [Intl]
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Europe — other
TAM 2.0 sequencing — Integrated · Europe — other
INPUTS
Business priorities | (populate ahead of the workshop)
Corporate priorities | (populate ahead of the workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## APAC
TAM 2.0 sequencing — Integrated · APAC
INPUTS
Business priorities | (populate ahead of the workshop)
Corporate priorities | (populate ahead of the workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Oceania
TAM 2.0 sequencing — Integrated · Oceania
INPUTS
Business priorities | 1. Consolidate Ezidebit promptly — onto Integrapay or TAM 2.0 target-state rails 2. Confirm SMB vs Integrated ownership of the Oceania platform estate (eWay · Ezidebit · Integrapay)
Corporate priorities | • Ezidebit consolidation decision open — interim (Integrapay) vs direct-to-target path • Global Gateway readiness in-region determines whether a one-hop migration is feasible (avoid paying for two migrations)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼ |  |  | ▼ Ezidebit consolidation decision
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing | Platforms (confirm ownership) • eWay • Ezidebit • Integrapay | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [MIGRATE] Consolidate Ezidebit — onto Integrapay or TAM 2.0 target-state rails (decision required; interim hop vs wait-for-target trade-off) • [STOP] Constrain new builds on eWay and Ezidebit to critical maintenance | • [MIGRATE] eWay — Debt Book tranche-2 candidate; migration path and timing to be confirmed against Global Gateway readiness | • [EXIT] Decommission consolidated legacy platforms
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)