## Notes — READ ME
TAM 2.0 sequencing pre-work — Integrated & Platforms
June workshop pack: Europe · APAC · Oceania
Notes:
1. Unlike the PPT exercise we did for Genius, this is a geo × segment view.
2. It takes business priorities and corporate priorities as inputs.
3. It captures the current-state and target-state stack.
4. It tracks BUILD, MIGRATE and DECOM decisions on a Now / Next / Later timeline.
How to read each geo tab:
• The INPUTS box holds business priorities and corporate constraints, with the dates they must be met. Segment-level priorities (below) sit above the geo-level priorities captured on each tab.
• The Milestones row (▼) places proposition and corporate milestones over the horizon in which they land.
• The table has one row per workstream: current-state stack, target-state stack, then Now / Next / Later actions.
• All timeline activities are TAM-scoped; BAU roadmap items are excluded. Where an activity directly enables a stated business priority, the cell says so: "[BUILD] … — enabling <priority>".
• Tags: [BUILD] = target-state build or adherence · [MIGRATE] = front-book switch, back-book migration or thin-out · [STOP] = stop-sell / stop-integration (frees capacity) · [EXIT] = decommission milestone.
• Channel / persona context is tagged inline in square brackets where relevant, e.g. [Bank], [ISV], [Wholesale].
• Data centre consolidation is tracked under the Global Infrastructure & Security workstream.
• Horizons: Now = H2 '26 – H1 '27 · Next = H2 '27 – H1 '29 · Later = H2 '29+.
• Blue text is a hypothesis to validate. A blank cell means we need your input — not that nothing is planned.
Terminology:
• Sales motion = direct, partner-led, or self-serve.
• Persona = the partner or customer type within a segment (e.g. Referral, Agent, ISO/Wholesale, Payfac, PFaaS).
• Channel = digital, in-person, or omnichannel.
• Proposition = what the merchant buys (e.g. Genius S, WP360, Revenue Boost). Propositions are inputs and milestones, not an axis of this view.
• Platform = the stack itself, current vs target.
• Persona treatment: SMB is not split by persona; Integrated tags personas inline in brackets; Enterprise is to be decided.
Open questions:
1. Which countries do we consider per region? We want to avoid the long tail.
2. Enterprise: do we split by persona / vertical (region × top 1–4 verticals)? Decide before populating.
3. Reconcile platform retirement timelines with the data centre consolidation plan — preliminary view requested from infrastructure (an application kept for three years cannot sit in a data centre exiting in one).
4. North America is intentionally omitted from this June pack — it is sequenced for the Jul 20–21 in-person.
5. Tabs other than UK&I carry pre-fill from the June QPRs and the earlier straw man — validate or clear with each geo lead.
Aggregate priorities (segment-wide, 2026–27):
• Standardization and platform unification (POM + TAM).
• Onboarding and activation speed — the core growth bottleneck.
• VAS monetization — lending, payments optimization, settlement.
• Execution discipline — customer commitments and large rollouts.
• Migration off legacy and reduction of fragmentation.
Integrated segment priorities:
• 2026 — Stabilize core growth engines (Payrix; close roadmap gaps across hGP and hWP). Accelerate merchant activation and partner growth in the US and UK. Payrix with in-person payments. Embedded Finance. Assist / Integrated. Monetize VAS (payouts, lending/EFE, fraud, tokenization) and increase multi-product attach rate. Solve ACH. CRM consolidation and fragmentation.
• 2027 — Converge onboarding, payments and reporting (reduce duplicate stacks). Embedded finance and VAS as primary growth drivers (lending, RTP, fraud, tokenization). Global partner expansion. Fully integrate the merchant lifecycle (onboard → activate → monetize).
Integrated notes:
• Personas are tagged inline in square brackets (e.g. [Wholesale], [Referral], [Payfac], [PFaaS]) rather than split into separate rows.
• Confirm with segment leads whether any persona warrants its own breakout — the answer is expected to be largely the same across personas (diminishing returns).
• Lens: platform / portfolio first, region second (per Ian Hillis).
• Seeded item to validate: the UK currently leverages Integrapay — to be solved sooner rather than later (J. Osborn).
• Seeded item to validate: consolidate Ezidebit promptly — onto Integrapay or TAM 2.0 target-state rails in Australia (Matt, via J. Osborn).

## UK&I
TAM 2.0 sequencing — Integrated · UK&I
INPUTS
Business priorities | (populate ahead of June workshop)
Corporate priorities / constraints | (populate ahead of June workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [MIGRATE] Integrated currently leverages Integrapay for the UK — solution required sooner rather than later (to be confirmed)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Europe — other
TAM 2.0 sequencing — Integrated · Europe — other
INPUTS
Business priorities | (populate ahead of June workshop)
Corporate priorities / constraints | (populate ahead of June workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## APAC
TAM 2.0 sequencing — Integrated · APAC
INPUTS
Business priorities | (populate ahead of June workshop)
Corporate priorities / constraints | (populate ahead of June workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)

## Oceania
TAM 2.0 sequencing — Integrated · Oceania
INPUTS
Business priorities | (populate ahead of June workshop)
Corporate priorities / constraints | (populate ahead of June workshop)
SEQUENCING
Workstream | Current-state stack | Target-state stack (validate) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Milestones ▼
Single-in |  | Global API • API 2.0 / Global API on Global Gateway — federated build to the published spec (linting & validation services) Payment apps & SDKs • PayApp 2.0 (Nucleus + triPOS hybrid) • Yazara softPOS • Scalefusion + Sightstream TMS Developer experience • Common portal + MCP server Hosted solutions / plug-ins • Target plug-in set on GP-API
Boarding |  | Experience • Ignition (Horizon/Kirby + Launchpad converge) Ingress • Boarding gateway Orchestration • Workstream manager Fulfillment • Actor & PIL Integration & messaging • Kafka + Mulesoft Ops data • hWP party model CPQ • RCA Credit & underwriting • UCM
Sales & Servicing |  | CRM • iNASA at launch; target state under 2/3 analysis (decision pending) Servicing tools • (to be defined) Risk monitoring • Merchant & transaction
Payment Processing |  | Gateway • Global Gateway Switch • PowerZac Auth • RAFT (NA) • PowerZac (ROW) Clearing • CORE (NA) • NAP (ROW) APMs • GPPaaS (ROW) | • [MIGRATE] Consolidate Ezidebit — onto Integrapay or TAM 2.0 target-state rails (to be confirmed)
VAS |  | Routing • Routing optimization service — RTR microservice + Prime capabilities extracted from RAFT Managed optimization • Revenue Boost — single orchestration API across credentials, smart retry, fraud and 3DS microservices Fraud • Fraudsight (powered by Ravelin) 3DS / exemptions • hWP 3DS Flex Network tokens / credentials • hWP credential management Loyalty • Como Gifts • Valutec FX / DCC • hWP
Unified Data and AI |  | Data platforms • Snowflake + Iceberg Master data • MDM
Global Infrastructure & Security (incl. data centres) |  | Design systems • WP DS foundation + Vega visual layer Cloud • (to be defined) Observability • (to be defined) Data centres • Consolidation overlay — reconcile application retirement dates with data centre decommissioning timelines (preliminary view requested from infrastructure)
Single-out |  | Portal • MyAccount++ Disputes • WDP — north star (DMS interim for hGP; Merlin & VAP disputes migrate to WDP in years 1–3; DMS converges to WDP in years 2–5) PFaaS • Converged PFaaS Reporting • Target selection in progress (decision pending)