## SMB
TAM 2.0 — Sequencing pre-work: business priorities × capability matrix ¦ Segment: SMB (v0.2 STRAW MAN — TAM implications only, for reaction)
How to read: each cell = TAM implication only — target-state builds & adherence, migrations / thin-outs, stop-sell / stop-integrate, decommissions. BAU & commercial roadmap items intentionally excluded. Tags: [BUILD] target-state build / adherence to standards · [MIGRATE] front-book switch, back-book migration, traffic move, thin-out · [STOP] stop-sell / stop-integration / constrain (feeds Debt Book tranche logic) · [EXIT] decommission milestone. Motion tags [Direct]/[Bank]/[ISV] appear only where an implication is motion-specific. Horizons: Now = H2 '26 – H1 '27 · Next = H2 '27 – H1 '29 · Later = H2 '29+. Corporate anchors: Genius S live on hWP/NAP rails (UK pilot Q1 '27) · GMAS EU / FIS migration waves 2028 · ACI / Postilion BO exit 2029. LOB = customer motion with P&L ownership; eComm is treated as a proposition within motions — if a geo runs eComm as a standalone P&L, promote it (fact-check per geo). Blank = we need your input, not 'nothing planned'. Items marked (validate w/ SPOC) lack confirmed TAM linkage. Replicate this tab per segment (Integrated, Enterprise).
|  | EUROPE | [14 empty] | NORTH AMERICA | [5 empty] | APAC
Workstream (boulder) | Big rock → target-state platform (blue-text hypothesis — validate) | UK&I |  |  | Poland |  |  | Greece |  |  | Spain |  |  | CEE — Erste JV |  |  | US |  |  | Canada |  |  | Asia
|  | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+) | Now (H2 '26 – H1 '27) | Next (H2 '27 – H1 '29) | Later (H2 '29+)
Business priorities | Per geo-segment — from segment leads (validate) | 1. Genius S UK — decision confirmed; dev on NAP target-state rails, Q1 '27 pilot 2. eCommerce expansion — WP eComm Essentials, Shopify Onsite, plugin activation 3. VAS growth — Everyday/Instant Settlement, DCC back-book, MCA in-house (rev c.$35m '27–28) 4. Bank channels — BOI, Virgin Money/Nationwide, HSBC (Tuza, eComm, Genius Mobile, Dashboard hooks) |  |  | 1. eCom: Click2Pay by June — Cashless Programme eligibility (85% of PL eCom sales) + Visa/MC incentives 2. GP eCom enhancements — DCC, BLIK LVL0/OneClick, eRaty 3. SMB POS — COMO loyalty + Xpay all-in-one 4. Cash2card w/ eService Pay app (€750k incentive) |  |  | 1. Close out Mirage migration (NBG bank systems → eService/Postilion) — completes end-June 2. GP eCom — finalise plan & sales strategy 3. Fiscalization-led all-in-one market (SoftPOS, PCI POS) 4. Genius Mobile — transition from white-label NBG Pay tom |  |  | 1. Bizum scale-out → ~500k terminals (full deploy by 29 Jun; enterprise activations) 2. Multi-acquiring C2.0 — LIDL won, ALDI strategic; 157-opp pipeline 3. BNPL w/ CaixaBank — full rollout this quarter 4. Close WP/Comercia commercial & product model gap (share loss) |  |  | 1. VAS growth (+70% YoY; 16% of JV revenue) — DCC on SoftPOS, loyalty, instalments 2. Genius parity for Central Europe (w/ Genius S team); CZ rebrand 3. Croatia expansion (CNB regulatory friction — key meeting June) 4. EEA Accessibility Act rollout (4 countries) |  |  | 1. Genius rooftop growth +20% (re-baseline w/ Gilbert) 2. Genius for SMB Merchant Bank on WP rails — on sale H2 '26 3. VAS bundles for SMB by Q4; attrition 28.8% → 23% 4. GP-API as single integration front door (launched US SMB & Mid-Corp) |  |  | 1. Indirect enablement parity — PIN Debit/Interac + French 2. UPA rollout on GP API & Portico (Direct CA) |  |  | 1. Genius Mobile Pay PH (BPI JV; exec-endorsed) — build Q3, deploy early Q4 2. GP eCom localisation — replace CyberSource/MPGS in-house 3. Boarding: >14-day wet-signature → 1–3 day digital onboarding 4. Productise IPP (~35% of Asia P&L)
Corporate constraints | Hard dates / contractual / regulatory (validate) | • BG migration: audit deadline Jul '27; automated tooling blocked on infra DB capacity • NerPay Ingenico app sunset path • ACI / Postilion BO exit by 2029 (corporate) • Fragmented hGP/hWP sales tooling & portals |  |  | • PDLC / ownership gaps on eService core platforms (no PM allocation) • Tech capacity — multi-year delays (e.g. pre-auth on host) • GP eCom delivery delays & reprioritisation flip plans |  |  | • MPGS → GP eCom feature gap (18-mo plan; platform non-competitive until closed) • Greek fiscalization rules (incl. pre-auth alignment) • Postilion dependency (ACI exit 2029 — corporate) |  |  | • No omnichannel product (eCom + F2F single API) in Spain • Legacy + new stack coexistence — speed & scalability • Carve-out: Model 170, reconciliation files • GP eCom processing/dev cost alignment; mid-term GP API & eCom scope |  |  | • E-com capacity on GP Webpay vs competitor pace • Croatian National Bank interference (CRO plans) • Genius product gap vs competition in Central Europe |  |  | • TAM contingency on Genius Retail (WP) • Dual hWP/hGP partner tooling through transition • ISO NPC decom — readiness done; migration & decom to complete • UPA demise tranche dates (T1 9/'27 · T2 3/'28 · T3 9/'28) |  |  | • Parity gaps vs US stack (Interac, language) • GNAP exit underway → GSAP/Portico (corporate — illustrative) • UPA demise T2 incl. Canada (3/'28) |  |  | • TNAS post-launch stabilisation (~100 open incidents) • Compliance backlog to 2017/18 (~$2.5M p.a. penalties) • Historic under-investment; manual foundations • CYBS Secure Acceptance EOL Jul '27
LOB motions & propositions | Propositions grouped by P&L-owning motion (Direct · Partner—Bank & JV · Partner—ISV/ISO). eComm = proposition within motions; promote if standalone P&L (fact-check) | Direct: TP+ · WP eComm direct (+Essentials) · WP360 · Genius S (incoming) Partner — Bank & JV: BOIPA · BOI / PTSB · Tuza → Horizon-based replacement Partner — ISV/ISO/Franchise: hGP referral & ISV integrations (constrain to target gateways) |  |  | Partner — Bank & JV (PKO BP / eService): eService POS estate · Xpay all-in-one · Merchant Portal Direct eCom: GP eCom (post-EPG) · Nestpay (legacy — exit) |  |  | Partner — Bank & JV (NBG Pay): NBG Pay tom (white-label) · eService / Postilion estate Direct: GP tom · GP eCom (incoming) |  |  | Partner — Bank & JV (CaixaBank / Comercia): Comercia 2.0 POS · TPV&GO · EPG / Addon2 eComm · MyCommerce (to-be) Direct: UniversalPay (migrating out) |  |  | Partner — Bank & JV (Erste): JV acquiring AT/CZ/SK/RO/CRO · GP TOM SoftPOS · GP Webpay eCom · Genius (CZ rebrand) |  |  | Direct: Genius hPOS (Retail/Restaurant) · SwipeSimple · GP-API Partner — Bank/FI: Genius for SMB Merchant Bank on WP rails · FI self-enrollment (Citizens, M&T) Partner — ISV/ISO: iQ + Launchpad stack · TrustCommerce · NPC (decommissioning) |  |  | Direct: UPA devices on GP-API / Portico · IP (Cayan) launch (incoming) Partner — indirect/ISV: enablement parity (Interac, French) · Genius incoming via channels |  |  | Direct: TNAS acquiring · GP eCom + GP API (incoming) · IPP instalments Partner — Bank & JV (BPI, PH): Genius Mobile Pay / SoftPOS eCom (within motions): CYBS / MPGS (to replace) · CIL 3rd-party QR gateway (to replace)
Single-in | Global API → API 2.0 / Global API ecosystem on Global Gateway · Payment Apps & SDKs → PayApp 2.0 (Nucleus + triPOS hybrid; Yazara softPOS; Scalefusion + Sightstream TMS) · Developer experience → common portal + MCP server · Hosted solutions / plug-ins → target plug-in set on GP-API | • [BUILD] Global API — develop & adhere to GP-API standard (UK&I SMB front door) • [BUILD] Genius S payment app Ph.1 — GP SDK → triPOS on hWP stack • [STOP] Stop new integrations to GP ecom / Access legacy APIs | • [BUILD] Genius S Ph.2 — Nucleus headless (PayApp 2.0 convergence) • [MIGRATE] UPA / eService app traffic → PayApp 2.0 • [MIGRATE] Back-book API traffic → Global API • [STOP] Stop core-acquiring integrations to legacy payment apps | • [EXIT] Decom GP ecom & Access APIs • [EXIT] Decom eService / UPA / Yazara standalone apps (post-migration) | • [BUILD] Nucleus replaces eService payment app — P2C → Nucleus (Sep '26) | • [MIGRATE] PAX AP / ECC estate → Nucleus | • [EXIT] eService legacy payment app decom (post-migration) | • [BUILD] Nucleus (+ Genius S) replaces EDPS payment app — build & localise | • [MIGRATE] EDPS app estate → Nucleus | • [EXIT] EDPS payment app decom |  | • [BUILD] GP API as eComm gateway for Spain ('27) |  |  | • [MIGRATE] Front-book — eService / EDPS / Erste JV onto Nucleus [Bank] • [BUILD] Genius parity for Central Europe | • [MIGRATE] Back-book → Nucleus (validate w/ SPOC) | • [BUILD] GP-API adherence — single integration front door (US SMB live) • [BUILD] Harvest Cayan components into PayApp 2.0 (Nucleus + triPOS hybrid) | • [EXIT] UPA demise T1 — Bermuda / L-GPN (9/'27) • [EXIT] UPA demise T2 — L-HPY / L-TSYS / Canada (3/'28) • [EXIT] UPA demise T3 — semi-integrated / P2PE (9/'28) | • [EXIT] Cayan platform deprecation (post-harvest) | • [BUILD] IP (Cayan) Canada launch on PayApp 2.0 path-to-TAM | • [EXIT] UPA demise T2 incl. Canada (3/'28) |  | • [BUILD] GP eCom + GP API build (TAM #24713) | • [BUILD] GP-API omnichannel CP launches Q2 '27 – Q1 '28 (#122516) • [MIGRATE] CYBS / MPGS estate → GP eCom • [EXIT] CYBS Secure Acceptance EOL Jul '27 | • [EXIT] MPGS exit complete (validate w/ SPOC)
Boarding | Experience → Ignition (Horizon/Kirby + Launchpad converge) · Ingress → Boarding gateway · Orchestration → Workstream manager · Fulfillment → Actor & PIL · Integration & messaging → Kafka + Mulesoft · Ops data → hWP party model · CPQ → RCA · Credit & underwriting → UCM | • [BUILD] Adhere — boarding API + hWP party model • [BUILD] Single boarding instance for UK&I • [STOP] Stop-sell hGP referral boarding tools [ISV] | • [BUILD] Ignition capabilities live (Horizon/Kirby + Launchpad converge) • [BUILD] Tuza → Horizon-based replacement [Bank] • [MIGRATE] BG back-book migration (audit deadline Jul '27) | • [MIGRATE] Boarding back-book → Ignition • [EXIT] Legacy boarding decom
Sales & Servicing | CRM → 2/3 analysis in progress (OPEN TAM DECISION) · Servicing tools · Risk monitoring (merchant & transaction) | • [BUILD] CRM 2/3 analysis — OPEN TAM DECISION (validate w/ SPOC) | [14 empty] | • [EXIT] ISO NPC decom — complete migration & decom (762 ISOs migrated) [ISV]
Payment Processing | Gateway → Global Gateway · Switch → PowerZac · Auth → RAFT (NA) + PowerZac (ROW) · Clearing → CORE (NA) + NAP (ROW) · APMs → GPPaaS (ROW) | • [BUILD] Genius S dev on NAP target-state rails (pilot Q1 '27) • [BUILD] Global Gateway — develop for UK&I • [STOP] Stop new integrations to non-target gateways (WPG et al.) | • [MIGRATE] Integrate POS & API flows to Global Gateway; migrate back-book • [MIGRATE] Thin out WPG | • [EXIT] Decom Inovo / Sterling • [EXIT] ACI / Postilion BO exit (2029 — corporate) | • [STOP] Nestpay — stop-sell / stop new integrations | • [BUILD] Genius S expansion pilot #2 on NAP rails (post-UK) • [MIGRATE] Nestpay merchants → GP eCom | • [EXIT] Nestpay decommission | • [STOP] MPGS — stop new integrations (feature-gap plan in flight) | • [MIGRATE] MPGS → GP eCom merchant migration | • [EXIT] MPGS exit • [EXIT] ACI / Postilion BO exit (2029 — corporate) | • [MIGRATE] UniversalPay migration (run-down continues) |  | • [EXIT] miTPV (Comercia) deprecation • [EXIT] UniversalPay exit complete |  |  |  | • [BUILD] Genius for SMB Merchant Bank on WP processing rails [Bank] | • [BUILD] Auth → RAFT / Clearing → CORE adherence (validate w/ SPOC) |  |  | • [MIGRATE] GNAP exit → GSAP / Portico (corporate) |  |  | • [BUILD] EU Nucleus localisation — HK/SG/PH/MY (CP foundation) • [BUILD] Replace 3rd-party CIL QR gateway (Octopus, PayMe → target rails)
VAS | Routing → Routing 2.0 · Gifts → Valutec · Network tokens → hWP tokens · Loyalty → Como · Fraud → Fraudsight · Managed optimization → Revenue Boost · FX / DCC / credential mgmt → hWP · 3DS / exemptions → hWP 3DS flex | • [BUILD] Deploy Como (loyalty target platform) | • [BUILD] VAS orchestration layer • [MIGRATE] Integrate VAS to Global Gateway; migrate front-book | • [MIGRATE] VAS back-book • [EXIT] Legacy VAS decom
Unified Data and AI | Data platforms → Snowflake + Iceberg · Master data → MDM | • [BUILD] MDM adherence • [BUILD] Genius AI + Fraudsight POC | • [BUILD] Data platforms & orchestration → Snowflake + Iceberg • [MIGRATE] Migrate reporting / data feeds to target platforms | • [EXIT] Legacy data stores decom
Global Infrastructure | Design systems → WP DS foundation + Vega visual layer · Cloud · Observability | • [BUILD] WP design-system foundation + Vega visual layer (Genius S UI adherence) • [BUILD] Infra / DB capacity to unblock BG migration tooling
Single-out | Portal → MyAccount++ · Disputes → WDP · PFaaS → Converged PFaaS · Reporting → analysis in progress (OPEN) | • [BUILD] MyAccount 2.0 — portal target-state build | • [MIGRATE] Integrate, then migrate Dashboard / legacy portals → MyAccount++ • [BUILD] Disputes → WDP adherence | • [EXIT] Legacy portal decom