## SMB
TAM 2.0 — Sequencing pre-work: business priorities × capability matrix ¦ Segment: SMB (v0.1 STRAW MAN — illustrative, for reaction)
How to read: each cell = what the workstream must deliver for SMB in that geo & horizon. Tags mirror the TAM roadmap legend — [BUILD] define/build · [LIVE] first live / initial adoption · [SCALE] broader use / migration / scale · [EXIT] decommission milestone. Corporate milestones pinned: UK&I Genius live end-2026 · GMAS EU / FIS migration waves 2028 · ACI / Postilion BO exit 2029. Populated from the June '26 SMB QPR as a straw man — product & engineering leads: correct, complete, re-time. Blank = we need your input, not 'nothing planned'. QPR Now(Q2)/Next(Q3)/Later(Q4+) provisionally mapped into Now (H2 '26); 2027 items → Next; 2028+ → Later. Replicate this tab per segment (Integrated, Enterprise).
|  | EUROPE | [14 empty] | NORTH AMERICA | [5 empty] | APAC
Workstream (boulder) | Big rocks in scope (placemat ref.) | UK&I |  |  | Poland |  |  | Greece |  |  | Spain |  |  | CEE — Erste JV |  |  | US |  |  | Canada |  |  | Asia
|  | Now (H2 '26) | Next (FY27) | Later (FY28+) | Now (H2 '26) | Next (FY27) | Later (FY28+) | Now (H2 '26) | Next (FY27) | Later (FY28+) | Now (H2 '26) | Next (FY27) | Later (FY28+) | Now (H2 '26) | Next (FY27) | Later (FY28+) | Now (H2 '26) | Next (FY27) | Later (FY28+) | Now (H2 '26) | Next (FY27) | Later (FY28+) | Now (H2 '26) | Next (FY27) | Later (FY28+)
Business priorities | Per geo-segment — from segment leads (validate) | 1. Genius S UK — decision confirmed; dev on NAP target-state rails, Q1 '27 pilot 2. eCommerce expansion — WP eComm Essentials, Shopify Onsite, plugin activation 3. VAS growth — Everyday/Instant Settlement, DCC back-book, MCA in-house (rev c.$35m '27–28) 4. Bank channels — BOI, Virgin Money/Nationwide, HSBC (Tuza, eComm, Genius Mobile, Dashboard hooks) |  |  | 1. eCom: Click2Pay by June — Cashless Programme eligibility (85% of PL eCom sales) + Visa/MC incentives 2. GP eCom enhancements — DCC, BLIK LVL0/OneClick, eRaty 3. SMB POS — COMO loyalty + Xpay all-in-one 4. Cash2card w/ eService Pay app (€750k incentive) |  |  | 1. Close out Mirage migration (NBG bank systems → eService/Postilion) — completes end-June 2. GP eCom — finalise plan & sales strategy 3. Fiscalization-led all-in-one market (SoftPOS, PCI POS) 4. Genius Mobile — transition from white-label NBG Pay tom |  |  | 1. Bizum scale-out → ~500k terminals (full deploy by 29 Jun; enterprise activations) 2. Multi-acquiring C2.0 — LIDL won, ALDI strategic; 157-opp pipeline 3. BNPL w/ CaixaBank — full rollout this quarter 4. Close WP/Comercia commercial & product model gap (share loss) |  |  | 1. VAS growth (+70% YoY; 16% of JV revenue) — DCC on SoftPOS, loyalty, instalments 2. Genius parity for Central Europe (w/ Genius S team); CZ rebrand 3. Croatia expansion (CNB regulatory friction — key meeting June) 4. EEA Accessibility Act rollout (4 countries) |  |  | 1. Genius rooftop growth +20% (re-baseline w/ Gilbert) 2. Genius for SMB Merchant Bank on WP rails — on sale H2 '26 3. VAS bundles for SMB by Q4; attrition 28.8% → 23% 4. GP-API as single integration front door (launched US SMB & Mid-Corp) |  |  | 1. Indirect enablement parity — PIN Debit/Interac + French 2. UPA rollout on GP API & Portico (Direct CA) |  |  | 1. Genius Mobile Pay PH (BPI JV; exec-endorsed) — build Q3, deploy early Q4 2. GP eCom localisation — replace CyberSource/MPGS in-house 3. Boarding: >14-day wet-signature → 1–3 day digital onboarding 4. Productise IPP (~35% of Asia P&L)
Corporate constraints | Hard dates / contractual / regulatory (validate) | • BG migration: audit deadline Jul '27; automated tooling blocked on infra DB capacity • NerPay Ingenico app sunset path • ACI / Postilion BO exit by 2029 (corporate) • Fragmented hGP/hWP sales tooling & portals |  |  | • PDLC / ownership gaps on eService core platforms (no PM allocation) • Tech capacity — multi-year delays (e.g. pre-auth on host) • GP eCom delivery delays & reprioritisation flip plans |  |  | • MPGS → GP eCom feature gap (18-mo plan; platform non-competitive until closed) • Greek fiscalization rules (incl. pre-auth alignment) • Postilion dependency (ACI exit 2029 — corporate) |  |  | • No omnichannel product (eCom + F2F single API) in Spain • Legacy + new stack coexistence — speed & scalability • Carve-out: Model 170, reconciliation files • GP eCom processing/dev cost alignment; mid-term GP API & eCom scope |  |  | • E-com capacity on GP Webpay vs competitor pace • Croatian National Bank interference (CRO plans) • Genius product gap vs competition in Central Europe |  |  | • TAM contingency on Genius Retail (WP) • Dual hWP/hGP partner tooling through transition • ISO NPC decom — readiness done; migration & decom to complete |  |  | • Parity gaps vs US stack (Interac, language) • GNAP exit underway → GSAP/Portico (corporate — illustrative) |  |  | • TNAS post-launch stabilisation (~100 open incidents) • Compliance backlog to 2017/18 (~$2.5M p.a. penalties) • Historic under-investment; manual foundations • CYBS Secure Acceptance EOL Jul '27
Current propositions in market | Chris's ask — what exists today; feeds yr-1/3/5 migration view | Take Payments+ · Worldpay eCommerce (+Essentials) · WP360 (+ROI GA) · hGP standalone POS (new ROI app) · Payment Links+ · Dashboard · MCA via YouLend · Genius S (incoming) |  |  | eService POS estate · GP eCom (post-EPG migration) · Merchant Portal · Xpay all-in-one · Nestpay (legacy gateway — exit) |  |  | NBG Pay tom (white-label SoftPOS) · eService/Postilion estate · IRIS A2A POS · GP tom · voucher platform |  |  | Comercia 2.0 POS · EPG / Addon2 eComm · TPV&GO · MyCommerce (to-be) · UniversalPay (migrating out) |  |  | Erste JV acquiring (AT/CZ/SK/RO/CRO) · GP TOM SoftPOS · GP Webpay eCom · Genius (rebranding in CZ) |  |  | Genius hPOS (Retail/Restaurant) · SwipeSimple · C360 · iQ + Launchpad partner stack · TrustCommerce · Portico / Express rails · GP-API |  |  | Portico / GSAP estate · UPA devices · Genius (incoming via channels) |  |  | CyberSource / MPGS eCom (to replace) · BPI JV propositions · TNAS acquiring · CIL 3rd-party QR gateway (to replace) · IPP instalments
Single-in | Global API · Payment Apps & SDKs · Developer Experience · Hosted solutions (plug-ins, connections, hosted pages) · Unified proposition | • [LIVE] Shopify Onsite plugin — pilot → GA • [LIVE] Payment Links+ invoicing / recurring / VT support • [BUILD] Embedded wallets (Hyva for Magento) | • [BUILD] Seamless plugin activation via Dashboard login (no credential copy-paste) • [BUILD] Worldpay Essentials SaaS pricing ph.1 + enhanced reporting • [LIVE] WooCommerce embedded wallets; Ecwid plugin | • [BUILD] PrestaShop + further platforms • [BUILD] Network Tokens & Click-to-Pay (scheme incentives); Klarna • [SCALE] Adherence to Global API standard (TAM — illustrative) | • [BUILD] GP eCom bug-fixing post-EPG (incl. missing APM reporting in RealControl) • [BUILD] DCC + Click2Pay Direct API (Click2Pay = June must-have) | • [BUILD] BLIK LVL0 + BLIK 1-click Direct API • [BUILD] DCC, Click2Pay, PKO BP eRaty plugins | • [BUILD] BLIK LVL0 plugins | • [BUILD] GP eCom plan finalisation → define sales strategy | • [SCALE] MPGS → GP eCom merchant migration (additional features required) |  | • [LIVE] Tink Pay-by-Bank ph.1 (Facilitea go-live) • [BUILD] GooglePay in Addon2 (EPG) | • [BUILD] Tink ph.2 (improvements + Iberdrola); PayByLink rebrand | • [BUILD] GP API as new eComm gateway (2027); Tink ph.3 (BCenter) | • [LIVE] Shoptet integration (biggest CZ/SK webshop builder); QR payments for Apple Pay • [LIVE] Transaction Risk Analysis (TRA) — 4 countries, back-book conversion uplift | • [BUILD] Recurring payments for Apple Pay; e-mail notifications for unfinished payments; business-card surcharge (CZ/SK) | • [BUILD] DCC for wallets; recurring for Google Pay | • [LIVE] GP-API for US SMB & Mid-Corp (initial: Portico L-HPS) • [LIVE] BNPL via Apex — Affirm/Zip/Klarna/Sezzle; Magento & PrestaShop pay-in-4 • [BUILD] Windows SDK (Moby/BBPOS); Moby C/LESS certified (TransIT/Portico) | • [BUILD] Shopify plug-in (GP dev tools) | • [BUILD] BigCommerce plug-in; Revenue Boost + Fraudsight enablement via dev tools | • [LIVE] UPA on GP API Canada — Alipay/WeChat, Launcher app, Downloader | • [BUILD] UPA on Portico — Visa Installments standalone, semi-integrated enhancements, host auto-close | • [BUILD] UPA GP-API CA — receipt reprint (semi-integrated); gift & loyalty hooks | • [BUILD] GP eCom + GP API build (TAM #24713) • [LIVE] CYBS Unified Checkout — interim rollout • [BUILD] MPGS v100 upgrade; CUP SecurePay sunset path | • [LIVE] GP eCom + GP API launch & pilot | • [EXIT] Migrate CYBS/MPGS estate → GP eCom (EOL Jul '27)
Boarding | Boarding experience · Ingress · Orchestration · Fulfillment · Integration & Messaging · Operations data (catalog, pricing, party model) · CPQ / quote-pricing · Credit & underwriting | • [BUILD] BG migration — automated migration scripting (blocked: infra DB setup) | • [BUILD] Genius UK enabled on target-state boarding rails • [BUILD] Fast Launch — contract-signing → activation • [SCALE] BG merchant migrations at scale (audit: Jul '27) | • [SCALE] Digital self-serve onboarding as default (illustrative) | • [LIVE] Onboarding system integration w/ PKO BP for new sales | • [BUILD] Self-onboarding via Merchant Portal (Xsell) |  |  |  |  | • [BUILD] Digital signature (1/2) | • [BUILD] Digital signature (2/2); digital onboarding improvements |  | • [LIVE] Automated onboarding for Genius (AT, CZ) |  |  | • [LIVE] Seamless self-enrollment partner pre-fill (SMB FI & IP) — Citizens live (+66% CTR); M&T pilot |  | • [BUILD] US seamless self-enrollment — white-label digital enrollment GA |  |  |  | • [BUILD] Asia SMB boarding foundations — self-service journey + GP eCom (#143029) • [SCALE] Project Peony — migrate SCB merchants • [BUILD] Hybrid boarding (MOSS AP + MBS) for BPI SoftPOS | • [BUILD] Sales-led & CP boarding incl. IPP + APMs • [BUILD] Multi-location toolkit — Salesforce/MBS/UCM automation ×5 countries | • [LIVE] Self-serve SMB sign-up, fixed pricing ×5 countries (2 in Q1, 3 in Q2)
Sales & Servicing | CRM · Servicing tools · Sales automation · Risks (merchant & transaction risk monitoring) | • [BUILD] Sales tooling shortlist w/ LOB leader (competing hGP/hWP initiatives) • [LIVE] WP↔GP lead sharing; B365 onboarded for hWP MCA outbound • [BUILD] BOIPA dialler automation | • [BUILD] Terminal leasing enablement, hGP estate (planning/design) • [BUILD] Account renewal — self-service targeted offers in Dashboard |  |  |  | • [BUILD] New front-sales system — digital sales | [9 empty] | • [EXIT] ISO NPC decommissioning — 762 ISO partners migrated (end-May); strategic platforms ready (Launchpad, iNASA, iQ, ServiceCloud) • [BUILD] Partner Portal initial pilot; SMB Sales Assistant pilot | • [LIVE] Partner Portal GA; SMB Sales Assistant launch • [BUILD] New Partner iQ Portal — analytics, servicing, role-based access | • [BUILD] NMI IRIS <> iQ API reporting & chargeback integration
Payment Processing | Gateway · Switch · Authorization platform · Clearing back-end · Transaction monitoring · APMs | • [BUILD] Genius S dev start on NAP rails • [SCALE] WP360 GA into Irish market (Q3) • [LIVE] WP Standalone+ ROI app GA → unlocks NerPay sunset • [LIVE] TP+ A77 device for BOIPA | • [LIVE] Genius S pilot on NAP (Q1 '27) — integrated terminal on target-state processing rails | • [SCALE] Genius S scale in market; handheld devices • [EXIT] NerPay Ingenico app sunset • [EXIT] ACI / Postilion BO exit (2029 — corporate) | • [LIVE] Pre-auth on host (HoReCa UX); Fast Refund; Recurring on POS | • [BUILD] GPE protocol in eService; new PAX A8900 / IM25; fleet cards integration | • [BUILD] Cash2card w/ eService Pay app (€750k incentive) • [EXIT] Nestpay decommission → migrate to GP eCom | • [LIVE] IRISx A2A on 230k POS; GP tom >6k terminals • [BUILD] Pre-auth on NBG Pay tom + fiscalization alignment | • [BUILD] 2nd-screen POS on PAX (first in Greek market) • [SCALE] Genius Mobile transition from NBG Pay tom |  | • [LIVE] Multi-acquiring pilot (Jun); new closing cycles (12k terminals); Bizum rollout • [BUILD] VISANet processing improvements; offline ops improvements | • [BUILD] Multi-merchant per terminal (multi-FUC on one device) • [BUILD] Mastercard processing improvements; dynamic DCC | • [EXIT] UniversalPay migration (run-off) • [BUILD] ATM | • [LIVE] A2A QR payments on devices (SK); hospitality Oracle integration (CZ/SK/AT/RO) • [LIVE] Deposit-return use case (Visa Direct / MC Send) • [BUILD] EEA Accessibility Act on payment devices (4 countries) | • [BUILD] Fast Refund (Visa Direct / MC Send); Visa Fleet 2.0 (CZ/SK) | • [BUILD] Nexgo devices w/ Nucleus (CRO); hospitality Oracle (CRO) | • [BUILD] Genius Retail US — Merchant Bank on WP partner tooling & processing rails (sale H2 '26) • [BUILD] Genius Restaurant — TransIT UPA + V2 POS software • [LIVE] SoftPOS triPOS; QR via TransIT | • [LIVE] Genius Retail pilot → GA (WP hPOS — TAM-contingent) • [BUILD] CNP / Mobile POS / TTP certifications w/ WPY (full Genius SMB solution) | • [SCALE] Genius Retail GA; TrustCommerce reseller expansion | • [LIVE] Indirect: CP/EMV, Amex/JCB, Discover/UnionPay support | • [BUILD] PIN Debit/Interac + French translation (indirect) |  | • [BUILD] BPI SoftPOS PH — first Genius-branded SoftPOS (Wave-0 release) • [BUILD] TNAS governance + day-2 stabilisation; FPS (HK) | • [BUILD] EU Nucleus localisation — HK/SG/PH/MY (CP foundation for Genius suite) • [BUILD] TNAS ph.2; Oracle Simphony certification (pan-Asia Android) • [BUILD] Octopus, PayMe (HK) — replace 3rd-party CIL gateway | • [BUILD] PayNow / PH QR • [SCALE] PH RRHI portfolio migration; HK unattended POS
VAS | Routing · Gifts · Network payment tokens · DCC/eDCC · Credential mgmt · Fraud · Loyalty · Managed optimization · FX · 3DS / exemptions | • [LIVE] hWP DCC opt-out, front + back book; hGP DCC on TP+ (stadium & events) • [BUILD] MCA in-house — solution design & plan | • [LIVE] Everyday Settlement pilot → launch (NAP-acquired; hospitality MVP) — closes competitor gap, enables Elavon referral turn-off • [SCALE] Mass DCC opt-out, hWP standalone back-book • [BUILD] MCA in-house build (rev c.$35m '27–28) | • [LIVE] Instant Settlement (30-min, chargeable) • [SCALE] Everyday Settlement GA | • [LIVE] All-in-one w/ Xpay (virtual cash register + POS on Sunmi) • [LIVE] COMO integrated w/ eService payment app (SMB target) • [LIVE] Instalments in F2F | • [BUILD] New TIP flow on POS; Oracle Symfonia (TIP); Visa Intelligent Authorization | • [BUILD] Advertising on POS; currency exchange; new gift-card platform; eService Pay app | • [LIVE] Voucher Greece 2.0 — terminal replacement & service programme |  |  | • [LIVE] BNPL pilot (20 merchants) → full rollout w/ CaixaBank • [BUILD] TPV&GO relaunch (terminal as light EPOS, Jun) |  | • [BUILD] TPV&GO modules — restaurant tables, stock, loyalty (YE) • [BUILD] MiTPV experience redesign | • [LIVE] DCC on GP TOM (4 countries); BNPL Skip Pay (CZ/SK); GP Stars (RO); Payment Protection (AT/RO) • [BUILD] Genius rebrand in CZ — terminal + app | • [BUILD] COMO loyalty (SK); GP Security (CZ/SK); GP Stars (AT) | • [BUILD] DCC + instalments (CRO); COMO (RO); Visa Currency Cloud (CZ/SK); POS Rating pilot (RO) | • [LIVE] Fraudsight; Fee Assist self-service sign-up; monthly pricing model • [BUILD] Terminal leasing launch — US/UK/Canada • [BUILD] MCA (YouLend + iQ EFE) — pilot planning | • [BUILD] Disputes Defender (AI/ML chargeback mgmt); YouLend embedded; Account Updater; wider Como integrated experience | • [LIVE] E2E MCA digital experience pilot → GA • [BUILD] Genius POS lending integration (Retail) |  |  |  | • [LIVE] Lazada online BPI SIP; FreedomPay via GP API (CIL) • [BUILD] DCC migration — Planet legacy → in-house | • [BUILD] Productise IPP — scalable instalment services | • [BUILD] MCA across Asia, starting PH
Unified Data and AI | Data trust · AI enablement services · Data services · Data platforms · Data acquisition · Data risks | • [BUILD] Fix data access & consistency gaps (slowing decisions; limited comparability) | • [BUILD] AI translations; MCP server for GP-API (global builds reaching UK&I — illustrative) | [7 empty] | • [BUILD] Fabric — unified data lake + DWH | • [BUILD] Advanced data processing (dynamic DCC, conversion engine) • [BUILD] Agent Platform creation + use-case execution | • [BUILD] Data & AI office operating model |  |  |  | • [BUILD] Action Engine — AI agent orchestrator (foundation) • [LIVE] Conversational analytics agent; MCP server for GP-API; developer-experience agent • [LIVE] AI-powered translations (all regions) | • [LIVE] Action Engine via 2–3 platforms incl. GP MyAccount • [BUILD] Product discovery, loyalty/VAS upsell agents; NL onboarding; invoice scanning & RFP responder | • [BUILD] TARS (the GP OS); premium super-agents; automated disputes agent; decline recovery + dynamic routing
Global Infrastructure | Data centers · Cloud · Observability · Security · AI tools · Design systems | • [BUILD] Infra / database capacity to unblock BG migration automation
Single-out | Portal · Reporting · Billing · Settlement · Disputes · Payouts · PFaaS products | • [BUILD] Reporting enhancements — real-time fraud score, 3DS outcome (top client pain point) | • [BUILD] Dashboard user management — staff permission tiers (invoice/settlement vs VT/PBL) | • [SCALE] Dashboard UK + My Account convergence (TAM portal target — illustrative) | • [LIVE] Merchant Portal — AML forms, reporting consolidation | • [BUILD] Automated refunds from Merchant Portal; all-in-one redirection (xpayu) | • [BUILD] SPOG; Merchant Portal front-end 2.0; gift cards in MP; internal self-service GUI |  |  |  |  | • [BUILD] MyCommerce app ph.1; Partner Portal ph.1; DClaims | • [BUILD] Partner Portal ph.2; Genesis (legacy) — 2027 | • [LIVE] Gaming payouts via Visa Direct / MC Send (RO — Superbet, ~1k devices, €35m yearly) |  |  | • [LIVE] Daily Net Settlement pilot • [LIVE] BI tool — flexible ad-hoc & customizable reporting | • [LIVE] Daily Net Settlement GA |  |  |  |  | • [BUILD] Analytics & reporting — portal/app (discovery) • [BUILD] Paynet API reporting + ApplePay; PH Amex non-BPI settlement |  | • [BUILD] Unified Asia payout solution (explore)